# National Evaluation of the Transition Care Program

RFT 206/0506

Final Evaluation Report

31 May 2008

Jointly funded by the Commonwealth, State and Territory governments

Contents

Acknowledgements	6

Transition Care Working Group  (Current and former members)	7

Summary of Ethics Applications	8

ACT Government	8

Victorian Government	8

Queensland Government	9

NSW Government	10

SA Government	10

Tasmanian Government	10

WA Government	10

NT Government	10

Glossary	11

Executive Summary	12

Key Findings	12

What is Transition Care?	12

What did we do?	12

What did we find?	13

What did we conclude?	14

1. Introduction	16

1.1. Framework for the Evaluation	16

i) Regional Characterization Report	16

ii) Quality Assessment Study	16

iii) Models of Transition Care	16

iv) Recipient Snapshot Study	17

v) Controlled Comparison Study	17

vi) Costs and Effects Study	17

1.2. Implementation of Transition Care in each jurisdiction	19

1.2.1. Australian Capital Territory	20

1.2.2. New South Wales	20

1.2.3. Northern Territory	20

1.2.4. Queensland	20

1.2.5. South Australia	20

1.2.6. Tasmania	20

1.2.7. Victoria	20

1.2.8. Western Australia	21

1.3. Structure of the Final Evaluation Report	21

1.3. Structure of the Final Evaluation Report	21

2. Background and relevant literature	22

2.1. Australian context	22

2.1.1. Innovative Care Rehabilitation Service - Australia	22

2.1.2. 	South Australian randomized controlled trial of a residential transitional care unit	23

2.2. Intermediate Care in the UK	24

2.3. Post Acute Care in the US	25

2.4. 	Methodological difficulties evaluating post acute care and rehabilitation interventions	26

2.5. The heterogeneity of the population targeted by Transition Care	26

2.6. 	What evidence lies behind the models of Transition Care used in Australia?	27

2.6.1. Evidence base for Transition Care in the community setting	28

2.6.2. Evidence base for Transition Care in the residential setting	29

2.6.3. Evidence base for Integrated Systems of Care	30

2.7. Summary	31

3. Transition Care recipients: Characteristics and outcomes	32

Key points	32

Table 3.1: Sample of Transition Care recipients and number of ACAT assessments 1 October 2006 - 31 March 2007	33

3.1. Baseline characteristics of Transition Care recipients	33

Table 3.24:  Baseline characteristics of recipients of Transition Care	34

3.2. Function	35

Table 3.3:  Median (IQR) Modified Barthel Index for all Transition Care recipients by type of Transition Care: Community, Residential, and Combination	36

3.3. Length of stay	37

3.4. Modified Barthel Index Efficiency	38

Figure 3.1: Modified Barthel Index efficiencies by type of Transition Care per jurisdiction	38

3.5. The Transition Care experience	38

3.6. Hospital readmissions	39

Table 3.5: Discharge destination by jurisdiction and type of care	40

Table 3.6: Hospital readmissions, residential aged care admissions, and deaths for Transition Care recipients at three months post ACAT approval	44

3.7. Residential aged care admissions	45

3.8. Survival	46

4. How did variations between Transition Care services affect outcomes?	47

Key points	47

4.1. What affects individual level outcomes?	47

Table 4.1: Risk of hospital readmission in six months post ACAT approval	49

4.2. 	Jurisdictional variations in health and aged care service provision	50

Figure 4.1: Composite indicator of number of aged care places and number of hospital beds per 1,000 older people for 2005/06 period	52

5.  Comparison of Transition Care recipients with other groups of frail older people	53

Key points	53

5.1. External comparison of Transition Care recipients to Australasian Rehabilitation Outcomes Centre and Geriatric Evaluation and Management units	53

Table 5.1: Estimated Modified Barthel Index efficiencies from the Australasian Rehabilitation Outcomes Centre 2006/07	53

5.2. Comparisons based on data linkage	55

Table 5.3: Hospital readmissions, residential aged care admissions, and deaths for Transition Care recipients, Control 1 and Control 2 at three months post ACAT approval	56

5.3. Impact on the hospital system	58

Table 5.5: Hazard of hospital readmission in six months post ACAT approval	58

5.4. Impact on the aged care system	61

Table 5.8: Summary of admission level for Transition Care recipients who were admitted to residential aged care in the six months post ACAT approval	63

5.5. Impact on Aged Care Assessment Processes	65

Table 5.9: Days from Aged Care Assessment Team approval to hospital separation and Transition Care admission	65

6. What are the estimated costs of achieving the outcomes?	67

Key points	67

Figure 6.1: Joint distribution of incremental cost and effects for recipients of Transition Care only in a community setting vs. Control 2 at three months post ACAT approval	68

7. What did the Transition Care services say about quality in Transition Care?	72

Key points	72

8. Issues from each jurisdiction	74

8.1. Australian Capital Territory	74

8.2. New South Wales	74

8.3. Northern Territory	74

8.4. Queensland	74

8.5. South Australia	75

8.6. Tasmania	75

8.7. Victoria	77

8.8. Western Australia	77

9.	Strengths and limitations of the National Evaluation of the Transition Care Program	79

9.1. Regional Characterization Study	79

9.2. Models of Transition Care	79

9.3. Quality Assessment Study	79

9.4. Recipient Snapshot Study	80

9.5. Controlled Comparison Study and Costs and Effects Study	80

9.6. Overall strengths and limitations	82

10. Summary and future directions	83

10.1. Discussion	83

Specific issues identified during the implementation	84

Table 10.1:  Transition Care Program: assumptions behind the model and evidence for these assumptions.	87

10.2. Comparison of the Innovative Care Rehabilitation Services pilot and the National Evaluation of the Transition Care Program	89

Table 10.2: Comparison between the results from the National Evaluation of Innovative Care Rehabilitation Services and the National Evaluation of the Transition Care Program	90

10.3. Areas for future work	91

10.4. Summary	92

11. References	94

Appendix 1: Extracts from From Hospital to home – Improving care outcomes for older people, a National Action Plan for improving the care of older people across the acute-aged care continuum 2004 – 2008	99

Principle 1: Older people have access to an appropriate level of health and aged care 	services that match their changing needs.	99

Principle 5: 	The health and aged care system operate to deliver an integrated suite of  services and care for older people.	100

Appendix 2	102

Appendix 3: Episodes of care definition according to the Meteor data dictionary	104

Hospital service-care type, code N[N].N	104

Value domain attributes	104

# Acknowledgements

This report has been compiled for the National Evaluation of the Transition Care Program on behalf of Flinders Consulting by the Evaluation Management Team: Ms Lynne Giles, Dr Julie Halbert, Ms Jackie Stepien-Hulleman, A/Prof Simon Eckermann, Ms Stacey Masters, Mr Justin Prendergast, A/Prof Craig Whitehead, Ms Fiona Cheney, and Professor Maria Crotty (Chief Investigator).  Professor Ian Cameron of the Rehabilitation Studies Unit at the University of Sydney, Professor Len Gray of the Academic Unit in Geriatric Medicine at the University of Queensland, and Dr Owen Davies of the Department of Rehabilitation and Aged Care at Repatriation General Hospital provided helpful comments on a draft of this report.

A number of people have contributed to this report, and their help and advice is gratefully acknowledged.  Special thanks are due to members of the Modelling, Information, Reporting and Analysis Group (MIRAG) in the Ageing and Aged Care Division of the Australian Government Department of Health and Ageing for facilitating access to the Commonwealth data sets in this report.  In particular, Dr David Cullen, Dr David Martin, Ms Naomi Rogers, Mr Tom Goff, and Mr Carl Hernaman have helped members of the evaluation team to obtain data and updates.  Ms Allison Rosevear, Ms Jane Hanson, Ms Elke Zimmermann, and Ms Jo Broad from the Residential Program Management Branch of the Ageing and Aged Care Division of the Australian Government Department of Health and Ageing have also contributed to this report.

Members of the Transition Care Working Group in each state and territory have facilitated access to the respective hospital morbidity data collections, and we gratefully acknowledge this help.  Staff in Health Information in each state or territory have extracted the data, and we particularly thank the following people: Ms Julie Searle of ACT Health, Mr Gary Inglis of NT Department of Health and Community Services, Mr Peter Brandt, Mr John Agland and Ms Sara Subramanian of NSW Health, Mr James Snodgrass of Queensland Health, Mr Paul Basso and Ms Deborah Brown of SA Department of Health, Mr Peter Mansfield of Tasmanian Department of Health and Human Services, and Dr Vijaya Sundararajan and Mr David Quin of Victorian Department of Human Services.

Dr John Bass of the Data Linkage Group, Curtin University conducted the data linkages for the Australian Capital Territory, New South Wales, Queensland, South Australia, Tasmania, and Victoria.  Staff in the Health Information Linkage Branch of the Western Australian Department of Health (formerly Western Australian Data Linkage Unit) facilitated the linkage of Western Australian records, and we particularly thank Ms Di Rosman, Ms Brooke Baxter, Ms Carol Garfield, and Ms Emma Brook in this regard.  Mr Gary Inglis of the Northern Territory Department of Health and Community Services facilitated the linkage of the Northern Territory hospital records.  Dr John Harding and Ms Khun Zhao of the Australian Institute of Health and Welfare facilitated linkage to the National Death Index.

## Transition Care Working Group  (Current and former members)

| Name | Jurisdiction |
| --- | --- |
| Jane Hanson | Australian Government Department of Health and Ageing |
| Pierre Nijssen | Australian Government Department of Health and Ageing |
| Linda Jackson | Australian Government Department of Health and Ageing |
| David Cullen | Australian Government Department of Health and Ageing |
| David Martin | Australian Government Department of Health and Ageing |
| Therese Gehrig | ACT Health |
| Dagmar Kelly | ACT Health |
| Clare Gardiner | NSW Health |
| Jane Fenn | NSW Health |
| Barbara Anderson | NSW Health |
| Michael Woodhouse | Northern Territory |
| Liz Kasteel | Northern Territory |
| Sue Keys | Northern Territory |
| Loris Semple | Northern Territory |
| Amanda Croker | Queensland Health |
| Shelly Kulperger | Queensland Health |
| Michael Edwards | Queensland Health |
| Ann Crowhurst | Queensland Health |
| Allan Quire | SA Department of Health |
| Mick Urukalo | SA Department of Health |
| Marie DeRieu | SA Department of Health |
| Rachel Newrick (Beisiegel) | SA Department of Health |
| Valerie Whelan | Tasmanian Department of Health and Human Services |
| Fran Thompson | Tasmanian Department of Health and Human Services |
| Sonia Lillico | Tasmanian Department of Health and Human Services |
| Betty Tzouvelis | Victorian Department of Human Services |
| Nicole Doran | Victorian Department of Human Services |
| Carolyn Glover | Victorian Department of Human Services |
| Kathy Stack | WA Department of Health |
| Gail Milner | WA Department of Health |
| Jeanette Plenty | WA Department of Health |
| Professor Leon Flicker | Royal Perth Hospital |
| Dr Paul Varghese | Princess Alexandra Hospital (QLD) |

## Summary of Ethics Applications

| National Applications | Due date | Date submitted | Date of meeting | Final approval |
| --- | --- | --- | --- | --- |
| Department of Health and Ageing Departmental Ethics Committee | 18 Oct 2006 | 18 Oct 2006 | 06 Nov 2006 | 13 Dec 2006 |
| Flinders Clinical Research Ethics Committee | 27 Nov 2006 | 30 Oct 2006 | 11 Dec 2006 | 18 Dec 2006 |

### ACT Government

| National Applications | Due date | Date submitted | Date of meeting | Final approval |
| --- | --- | --- | --- | --- |
| ACT Health and Community Care Human Research Ethics Committee | 28 Nov 2006 | 23 Nov 2006 | 11 Dec 2006 | 26 Feb 2007 |

### Victorian Government

| National Applications | Due date | Date submitted | Date of meeting | Final approval |
| --- | --- | --- | --- | --- |
| Austin Health Human Research Ethics Committee | 28 Nov 2006 | 23 Nov 2006 | 12 Dec 2006 | 28 Feb 2007 |
| Barwon Health Research and Ethics Advisory Committee | 21 Nov 2006 | 21 Nov 2006 | 28 Nov 2006 | 12 Dec 2006 |
| Bundoora Extended Care Centre Human Research Ethics Committee Have asked for project to be overseen by the Northern Human Research Ethics Committee (in same health region) |  | 30 Nov 2006 |  |  |
| Eastern Health Research and Ethics Committee | QA Process | 21 Nov 2006 | 14 Dec 2006 | Not Required |
| Human Research Ethics Committee- A St Vincent's Health Melbourne | QA Process | 21 Nov 2006 | 13 Dec 2006 | Not Required |
| Melbourne Health Human Research Ethics Committee | QA Process | 04 Dec 2006 | 06 Dec 2006 | 18 Jul 2007 |
| Peninsula Health Research & Ethics Committee | 17 Nov 2006 | 16 Nov 2006 | 06 Dec 2006 | 06 Dec 2006 |
| Southern Health Human Research Ethics Committee B | QA Process | 21 Nov 2006 | 14 Dec 2006 | Not required |
| The Alfred Research & Ethics Unit (Bayside) | 20 Nov 2006 | 21 Nov 2006 | 21 Dec 2006 | 02 Jan 2007 |
| Northern Hospital Human Research & Ethics Committee | 17 Nov 2006 | 16 Nov 2006 | 28 Nov 2006 | 30 Nov 2006 |
| Victorian Department of Human Services Human Research Ethics Committee | 22 Nov 2006 | 20 Nov 2006 | 06 Dec 2006 | 19 Dec 2006 |

### Queensland Government

| National Applications | Due date | Date submitted | Date of meeting | Final approval |
| --- | --- | --- | --- | --- |
| Bayside Health Service District Human Research Ethics Committee | 06 Dec 2006 | 29 Nov 2006 | 14 Dec 2006 | 14 Dec 2006 |
| Cairns Base Hospital Ethics Committee | 16 Jan 2007 | 19 Dec 2006 | 01 Mar 2007 | 09 Mar 2007 |
| Gold Coast Health Service District Human Research Ethics Committee | 17 Jan 2007 | 15 Dec 2006 | 31 Jan 2007 | 23 Apr 2007 |
| Mackay Health Service District Human Research Ethics Committee |  | 19 Dec 2006 | 17 Jan 2007 | approved |
| Princess Alexandra Hospital Human Research Ethics Committee | 17 Nov 2006 | 16 Nov 2006 | 05 Dec 2006 | 16 Apr 2007 |
| Queensland Health Research Ethics Committee | 06 Dec 2006 | 28 Nov 2006 | 18 Dec 2006 | 28 Feb 2007 |
| Redcliffe-Caboolture Health Service District Ethics Committee | 17 Jan 2007 | 15 Dec 2006 | 07 Feb 2007 | 04 Apr 2007 |
| Rockhampton Health Service District Human Research Ethics Committee | 7 Feb 2007 | 15 Dec 2006 | 22 Feb 2007 | 01 Mar 2007 |
| Royal Brisbane and Women's Hospital Human Research Ethics Committee | 11 Jan 2007 | 15 Dec 2006 | 19 Feb 2007 | 06 Jun 2007 |
| The Prince Charles Hospital Health Service District Human Research Ethics Committee | 29 Nov 2006 | 28 Nov 2006 | 13 Dec 2006 | 13 Dec 2006 |
| Townsville Health Service District Institutional Ethics Committee | 23 Nov 2006 | 21 Nov 2006 | 07 Dec 2006 | 05 Feb 2007 |
| Toowoomba Health Service District Human Research Ethics Committee | 29 Nov 2006 | 27 Nov 2006 | 14 Dec 2006 | 06 Dec 2006 |
| West Moreton Health Service District Human Research Ethics Committee | 20 Nov 2006 | 17 Nov 2006 | 04 Dec 2006 | 26 Feb 2007 |

### NSW Government

| National Applications | Due date | Date submitted | Date of meeting | Final approval |
| --- | --- | --- | --- | --- |
| NSW Department of Health Human Research Ethics Committee | 23 Nov 2006 | 20 Nov 2006 | 14 Dec 2006 | 01 Feb 2007 |

### SA Government

| National Applications | Due date | Date submitted | Date of meeting | Final approval |
| --- | --- | --- | --- | --- |
| SA Department of Health Human Research Ethics Committee | 26 Oct 2006 | 26 Oct 2006 | 08 Nov 2006 | 09 Feb 2007 |

### Tasmanian Government

| National Applications | Due date | Date submitted | Date of meeting | Final approval |
| --- | --- | --- | --- | --- |
| Southern Tasmania Health & Medical Human Research Ethics Committee | 09 Nov 2006 | 09 Nov 2006 | 11 Dec 2006 | 04 Dec 2006 |

### WA Government

| National Applications | Due date | Date submitted | Date of meeting | Final approval |
| --- | --- | --- | --- | --- |
| Confidentiality of Health Information Committee |  | 29 Jan 2007 | 06 Feb 2007 | 19 Feb 2007 |

### NT Government

| National Applications | Due date | Date submitted | Date of meeting | Final approval |
| --- | --- | --- | --- | --- |
| Central Australia Human Research Ethics Committee | 26 Oct 2006 | 21 Nov 2006 | 23 Nov 2006 | 24 Nov 2006 |
| Human Research Ethics Committee of Northern Territory Department of Health & Community Services and Menzies School of Health Research | 15 Nov 2006 | 14 Nov 2006 | 07 Dec 2006 | 13 April 2007 |

# Glossary

| Glossary | Description |
| --- | --- |
| ABS | Australian Bureau of Statistics |
| ACAT | Aged Care Assessment Team |
| ACCR | Aged Care Client Record |
| ADL | Activity of Daily Living |
| AROC | Australasian Rehabilitation Outcomes Centre |
| CACP | Community Aged Care Package |
| CI | Confidence Interval |
| CTM-3 | Care Transition Measure |
| EACH | Extended Aged Care at Home |
| EachD | Extended Aged Care at Home Dementia |
| FIM | Functional Independence Measure |
| Flexible Care | Means care provided in a residential or community setting through an aged care service that addresses the needs of the care recipients in alternative ways to the care provided through residential care services and community care services |
| GEM | Geriatric Evaluation and Management |
| GP | General Practitioner |
| HACC | Home and Community Care |
| HR | Hazard Ratio |
| ICRS | Innovative Care Rehabilitation Services |
| IQR | InterQuartile Range |
| ISD | Integrated Service Delivery |
| IRR | Incidence Rate Ratio |
| MBI | Modified Barthel Index |
| MCSI | Modified Caregiver Strain Index |
| NETCP | National Evaluation of the Transition Care Program |
| OR | Odds Ratio |
| PAC | Post Acute Care |
| SD | Standard Deviation |
| SLA | Statistical Local Area |
| SNFs | Skilled Nursing Facilities |
| SWIC | Survival without institutional care |
| TC | Transition Care |
| TCP | Transition Care Program |

# Executive Summary

## Key Findings

- The Transition Care Program provided additional treatment and care options following hospitalization that were highly valued by patients and their families.

- Functional improvements occurred.  When compared with similar groups of frail older people discharged from hospital during the same time period, those who received Transition Care had fewer readmissions to hospital and were less likely to move into permanent residential aged care.

- These outcomes are achieved at a comparatively high cost.  For every day a recipient of Transition Care survives without institutional care i.e. without hospital or residential aged care over a six month period it costs $344 per day.  Costs were evaluated during an early phase of the program when they are likely to be high.

- The program was implemented within a health context where older people across Australia have widely variable access to rehabilitation and geriatric hospital beds.  It did not appear that areas which were short of aged care services or subacute beds had been prioritized in the allocation of the first 2,000 Transition Care places.

## What is Transition Care?

Transition Care is a form of flexible care provided to an older person at the end of an inpatient hospital episode in the form of a package of services that includes at least low intensity therapy and either nursing support or personal care.  The care is characterized as goal-oriented, time limited, therapy focused, and necessary to complete the care recipient’s restorative process, optimize their functional capacity, and assist them and their families to make long term arrangements for care.

Transition Care is legislated under the Aged Care Act 1997 and in the 2004-5 Federal Budget the national Transition Care Program was announced as part of the Government Investing in Australia’s Aged Care: More Places, Better Care package.  The Australian Government committed to providing 2,000 flexible aged care places for Transition Care with a proportion allocated to each state and territory broadly in line with their proportion of people aged 70 years and over.

## What did we do?

We carried out six studies to assess the introduction of this new program across Australia:

- The Regional Characterization Report described Commonwealth aged care places and state funded acute and rehabilitation beds for older people across Australia in June 2006.

- The Quality Report summarized 23 reports on the program operation which had been completed by Transition Care services between 28 September 2006 and 18 May 2007, an average of nine months following service commencement.

- The Models of Transition Care Report described the characteristics of Transition Care recipients and the three main types of Transition Care: predominantly community-based services, residential-based services, and services that offered a combination of community-based and residential-based places.

- The Recipient Snapshot Report described the reports of older people and their families on the program three months after their discharge from the Transition Care Program between 1 February and 30 June 2007. No one in either Western Australia or Northern Territory was interviewed.  We interviewed people on the phone (374 interviews with an older person who received Transition Care and 256 with a family member or carer who acted as a proxy) which represented a fifth of those who had received the program.  We asked them about: their living arrangements and use of community care services; their satisfaction with the program; how well the move from Transition Care to the community or residential aged care went (we used an American instrument to measure how successful this had been, the Care Transition Measure); about their level of functional independence (using the Modified Barthel Index); any hospital readmissions; any costs incurred and their self-rated health.  We also asked carers about their experiences.

- Controlled Comparisons, Costs and Effects Report.  We followed 2,443 people who were approved for Transition Care between 1 October 2006 and 31 March 2007 by an Aged Care Assessment Team (ACAT) and who were discharged from Transition Care by 30 September 2007.  In the data linkage component, administrative health records were matched on name (if available), sex, and date of birth, with elements of address used to refine the matches. This enabled us to calculate how many hospital readmissions, transfers into residential aged care and deaths occurred at both three and six months following approval for Transition Care.  We compared their outcomes with two groups of similar older people coming out of hospital at the same time; i) people who were approved for a Transition Care place but who did not receive it (n=879); and ii) people approved for Community Aged Care Packages between 1 October 2006 and 31 March 2007 (n=2,188).  We estimated the costs of providing the program after taking into account any savings achieved by reducing readmissions and movement into permanent residential aged care.

## What did we find?

- We found that the Transition Care Program was identifying people with a need for further care following a stay in hospital and that recovery continued after discharge from hospital.

- Those selected were medically frail and 37% of older people who received the program had returned to hospital at least once by three months.  By six months this proportion had risen to 47%.  Those receiving Transition Care in a community-based setting were more likely to be readmitted (51%) when compared with those who received Transition Care in a residential-based setting (43%).  Despite this, there was little evidence of medication review or medical assessment.

- About a quarter (22%) of people ended up in permanent residential aged care three months after approval and by six months this was 30%.  Those who had received Transition Care in a residential-based setting were more likely to go onto long term care with 58% living in residential aged care at six months. This group were frail and had an average admission score on the Modified Barthel Index of 51.1 out of a possible 100 (a measure of function where higher scores reflect higher levels of function).

- By six months 13% of people who received Transition Care had died.  Of those who received Transition Care only in a residential setting, 20% died and amongst those older than 85 almost a quarter had died by six months.

- When we compared the outcomes of the people who received Transition Care with other frail groups discharged from hospital in the same time period we found that Transition Care reduced the risk of entering an institution (hospital and residential aged care) in the six months post ACAT approval.  The hazard (risk) of a hospital readmission in the six months post ACAT approval was significantly greater in two control groups relative to the Transition Care recipients.  Similarly, the hazard of an admission to residential aged care in the six months post ACAT approval period was lower among Transition Care recipients overall.  However the risk was similar for those who received Transition Care only in a residential setting and those who were approved but did not enter the program.

- Three months after ACAT approval, a recipient of Transition Care only in a community setting had survived an additional 11.8 days without admission into hospital or residential aged care when compared with those in the Control 2 group and the additional cost to achieve this for an individual Transition Care recipient was $888 per day.  At six months this reduced to $344 per day.

- Nursing and allied health hours on the Transition Care services affected outcomes.  The risk of hospital readmission decreased with more nursing hours.  The risk of residential aged care admissions decreased with more allied health hours.

- In the telephone interviews most recipients and carers felt that they had a good understanding of their health issues and that staff had taken their wishes into account when planning services.  Carer’s experiences were assessed in telephone interviews and varied but overall moderate levels of strain (as measured by the Modified Caregiver Strain index) were reported.  The average age of the 386 carers who were interviewed was 63 years and carers were predominantly spouses or daughters.  Carers reported most difficulty with restrictions on their free time, the recent changes to their personal plans and they found it difficult to deal with the degree to which the person they cared for had changed from their former self.

- The Transition Care services reported difficulties engaging GPs but it also appeared the models did not emphasise assessment or management of medical issues.  Few pharmacists or medical specialists (such as geriatricians or medical rehabilitation specialists) were listed as staff in the Quality Reports.

- When we began the National Evaluation of the Transition Care Program in 2006 there were three rehabilitation and geriatric evaluation and management (GEM) beds per 1,000 older persons aged 70 and over compared with 26 acute hospital beds per 1,000 older people, but there was considerable variation across Australia with Victoria having the most rehabilitation beds.

- Transition Care places are making a significant contribution to post acute services in many areas of Australia but the jurisdictions’ approach to allocation was unclear and many areas of service need had not been allocated places.

- While the Transition Care Program was not intended to substitute for rehabilitation services it appeared to take on this role in regions with limited services.  However, it seemed less efficient than conventional rehabilitation programs.  Comparisons between the outcomes from Victorian GEM units and residential-based Transition Care found that the Victorian GEM units admitted more disabled patients and achieved functional improvements more rapidly.

- A similar inefficiency was noted in the use of community-based Transition Care places for people with high Modified Barthel Index scores which suggested that in other jurisdictions they might have received home rehabilitation programs.  Transition Care requires an ACAT assessment to be completed while home rehabilitation services do not.  The delay associated with this extra step i.e. accessing an ACAT assessment may introduce delays in hospital discharge.  Delays of up to a week between ACAT assessment and entry into Transition Care occurred, suggesting people were waiting in hospital for the program.

## What did we conclude?

- At the individual level positive outcomes were achieved.  Transition Care was valued by patients and carers and although it configured very differently across jurisdictions it seemed to increase the options for older people following hospitalization.  Appropriate people were offered the program and improvements in individuals’ function occurred.  When comparisons were made with other frail older people discharged from hospital at the same time, decreases in the risk of transfer back to hospital and permanent residential aged care were seen.

- These positive outcomes were achieved using flexible models and could be implemented in rural settings.  Higher nursing and allied health staffing hours were associated with better outcomes.

- The interface between Transition Care and hospital rehabilitation services needs to be clarified.  The level of access to rehabilitation and geriatric beds in a region influenced recipient selection and in many regions the Transition Care Program appeared to be fulfilling the traditional role of rehabilitation services.  These programs seem less efficient than conventional rehabilitation particularly when providing a substitute for GEM type wards.

- Transition Care provided in a residential-based setting requires more evaluation to clarify which groups will benefit, to explore whether this care should be delivered to a minimum number of co-located recipients, to identify minimum staffing levels and quality measures.  Transition Care provided in a residential-based setting alone did not appear to prevent transfer to residential aged care.

- The economic evaluation of the program suggested that the program was not low cost.  Some of the inefficiencies are probably related to evaluating the early phase of a new program addressing complex policy issues.  Issues that could be examined include: providing incentives to reduce episode costs or rewarding Transition Care services for complex cases e.g. those with dementia.

- Without increasing medical, pharmacy and nursing input into the programs, further reductions in readmissions will be difficult.  Transition Care services struggled with the interface with acute care (communication and support) therefore measures of the quality of transfer from hospital need monitoring.

- Strategies to improve communication from hospitals (such as pay for performance approaches which have been used in the US) should be explored.   Given the shortfall in health and aged care services for older people and the significance of Transition Care places to communities, transparent allocation of Transition Care places should ideally occur.  In the short term priority should be given to areas of service need including rural areas.

- It seems unlikely that simply adding more Transition Care places to regions will change hospital flows if there is an inadequate investment in geriatric rehabilitation beds.  If population based planning benchmarks of the ideal number of rehabilitation beds for older people could be developed in tandem with the expansion of the Transition Care Program, greater effects on flows across care sectors are likely to occur.

- A broader range of interventions and models in the program could be considered.  For example, models for people with dementia could be developed further.  One of the requirements for admission to the Transition Care Program is that patients are medically stable, but one fifth of those in residential based Transition Care had died by six months post ACAT approval.  Thus end-of-life care is an issue faced by Transition Care services, and this may reflect selection issues or the rapid onset of some medical conditions among frail older people.  Evaluation of new models should include an economic evaluation with 12 month follow-up and assess medication costs.

- We demonstrated that using linked datasets is a feasible way of assessing the outcomes of the Transition Care Program.  Cognitive and other health issues can make interviewing a representative sample of older people difficult but this approach allows timely evaluation of a national program at the acute and aged care interface.  Further analyses of linked data sets are likely to assist with future iterations of the Transition Care Program.

# 1. Introduction

## 1.1. Framework for the Evaluation

The Transition Care Program (TCP) provides care that is therapeutic, goal oriented, time-limited and targeted to older people at the conclusion of a hospital episode who require more time and support in a non hospital environment to complete their restorative process and optimize their functional capacity while assisting them and their family or carer to make long term care arrangements.

The six key questions for the National Evaluation of the Transition Care program (NETCP) are:

- Are the outcomes being achieved?

- How are the outcomes at the individual level being achieved?

- How are the outcomes at the system level being achieved?

- What are the costs of achieving the outcomes for the Australian Government, State and Territory Governments, and the care recipient in absolute terms and relative terms?

- What did the Quality Report say about quality in Transition Care (TC) Services?

- How can the TCP design be improved?

To address these questions, a suite of six studies was undertaken for the NETCP.  The six studies and a brief description of the methods employed in each study are presented below.  The timeframe covered by each report is summarized in Table 1.1 on Page 9.

### i) Regional Characterization Report

This report provided a summary of key health services for older people according to Aged Care Assessment Team (ACAT) (known as Aged Care Assessment Service in Victoria) region.  The demographic and health service indicators were derived from data supplied by the Australian Bureau of Statistics (ABS), the Australian Government Department of Health and Ageing, the Australasian Rehabilitation Outcomes Centre (AROC) at the University of Wollongong, and the Lincoln Centre for Ageing and Community Care Research at La Trobe University.  The indicators that were shown in this report were population, provision ratio of aged care places or TC places per 1,000 older people, the number of first-time admissions to residential aged care per 1,000 older people, Home and Community Care (HACC) clients per 1,000 older people, number of ACAT assessments, and number of acute and subacute hospital beds per 1,000 older people.  The data encompassed the period 1 July 2005 to 30 June 2006.  In the Regional Characterization Report, population data were estimated at 30 June 2006; Aged Care places at 31 December 2005 and 30 June 2006; AROC provided data as at 30 June 2006.  Estimates of hospital bed utilization were for the 2005/06 financial year.

### ii) Quality Assessment Study

This study was designed to summarize and identify themes and report suggestions of ways to improve TC services.  Quality Reports were completed between 28 September 2006 and 18 May 2007, an average of nine months following service commencement.  A grounded theory, or inductive, approach was used whereby the themes identified were derived from the text rather than a body of literature.  The reporting of TC services’ responses to the Quality Report focused on a description of responses and, where appropriate, thematic analysis.

### iii) Models of Transition Care

This study was conducted to characterize the types of TC models used by different TC services.  The report drew data from the TC Quality and Quarterly Reports, survey of TC services conducted in November 2006, and information from the Australian Government Department of Health and Ageing administrative database concerning TC Payments for the 2006/07 financial year.

### iv) Recipient Snapshot Study

This study was designed to describe the demographic, residential, and cognitive characteristics, and health service use of TC recipients, three months after completion of TC.  A secondary purpose was to describe the satisfaction of carers with TC and any strain that they reported.  The interviews took place between 1 May and 30 September 2007, corresponding to recipients who were discharged from TC between 1 February and 30 June 2007.

The telephone interview schedule included seven domains concerning the recipient’s experience and outcomes from TC including: i) living arrangements and use of community care services; ii) satisfaction with TC; iii) the quality of the transition from TC to the community or residential aged care (Care Transition Measure, CTM-3); iv) functional independence (Modified Barthel Index; MBI); v) hospital readmissions vi) costs associated with TC and main source of income; and vii) self-rated health.  The number of outcome measures was kept low in order to minimise the respondent burden imposed by the interviews.

A brief carer interview was also administered.  This included carer’s age, relationship to TC recipient, the Modified Caregiver Strain Index (MCSI), carer involvement in decisions, and overall satisfaction with TC.

### v) Controlled Comparison Study

The purpose of this report was to describe the hospital readmissions, residential aged care service utilization, and mortality in the three months and the six months post ACAT approval for individuals who were ACAT assessed for TC between 1 October 2006 and 31 March 2007, and who were discharged from TC by 30 September 2007.  These three outcomes were compared to those for people who were approved for a TC place (who either did not receive TC despite approval or who had not been discharged from TC by 30 September 2007; Control 1) and for people approved for Community Aged Care Packages (CACP); Control 2) with the approvals for both groups occurring between 1 October 2006 and 31 March 2007.

### vi) Costs and Effects Study

This study built on the Controlled Comparison Study to describe the costs and effects of the outcomes of TC recipients relative to the two control groups, and considered both the three and six months post ACAT approval periods.  The impact of regional level variables such as hospital and residential aged care availability on the analyses are considered in a national analysis of admissions to residential aged care and readmissions to hospital in the three months post ACAT approval.  Data linkage of a number of administrative health datasets was undertaken to assess the outcomes.

Both studies were undertaken using a controlled comparison design with three months and six months follow-up from the date of ACAT approval.  Data were extracted from a range of primary sources for the data linkage, the starting point for the linkage was the ACAT approval, and the other datasets were linked into the originating ACAT approval.

Table 1.1: National Evaluation of the Transition Care Program timetable

| Report Name | July - 2005 | August - 2005 | September - 2005 | October - 2005 | November - 2005 | December - 2005 | January - 2006 | February - 2006 | March - 2006 | April - 2006 | May - 2006 | June - 2006 | July - 2006 | August - 2006 | September - 2006 | October - 2006 | November - 2006 | December - 2006 | January - 2007 | February - 2007 | March - 2007 | April - 2007 | May - 2007 | June - 2007 | July - 2007 | August - 2007 | September - 2007 | October - 2007 | November - 2007 | December - 2007 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Regional Characterization Study1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Quality Assessment Study |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Models of Transition Care Study |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Recipient Snapshot Study |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Controlled Comparison Study |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cost and Effects Study |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

1: In the Regional Characterization Study, population data were estimated at 30 June 2006; Aged Care places at 31 December 2005 and 30 June 2006; Australasian Rehabilitation Outcomes Centre provided data as at 30 June 2006

## 1.2. Implementation of Transition Care in each jurisdiction

TC is a new program in Australia and the rollout of TC in each of the Australian states and territories has varied according to the local climate of health service provision.  TC places are flexible care places under the Aged Care Act 1997 which can be used flexibly in either the residential or community setting.  TC services include state funded health services and aged care organizations.  There is heterogeneity in the number and mix of TC places allocated (residential and community), time since the service became operational, model of service delivery and extent of brokerage arrangements.  The allocation of TC places (broken down by type of operational place which can be changed according to needs) is presented in Table 1.2.

Table 1.2: Allocation and operation of Transition Care places as at 30 June 2007

| Jurisdiction | Residential operational | Community operational | Total allocated |
| --- | --- | --- | --- |
| ACT | 15 | 20 | 35 |
| NSW | 81 | 490 | 703 |
| NT | 8 | 0 | 16 |
| QLD | 17 | 240 | 351 |
| SA | 94 | 53 | 176 |
| TAS | 27 | 25 | 57 |
| VIC | 247 | 182 | 502 |
| WA | 50 | 50 | 160 |
| Total | 539 | 1,060 | 2,000 |

As Table 1.3 shows, different proportions of the TC places were delivered in residential-based and community-based settings in each of the jurisdictions.  These cumulative data are drawn from the TCP COGNOS database and cover the period 1 October 2005 to 29 February 2008 (Department of Health and Ageing 2008).

Table 1.3: Cumulative number of discharges by type of Transition Care October 2005 - Feb 2008

| Jurisdiction | Community n (%) | Residential n (%) | Combination n (%) | Total number of discharges |
| --- | --- | --- | --- | --- |
| ACT | 110 (37%) | 87 (30%) | 97 (33%) | 294 |
| NSW | 3,692 (84%) | 631 (15%) | 58 (1%) | 4,381 |
| NT | 0 (%) | 55 (100%) | 0 (0%) | 55 |
| QLD | 1,213 (93%) | 39 (3%) | 52 (4%) | 1,304 |
| SA | 637 (38%) | 914 (54%) | 131 (8%) | 1,682 |
| TAS | 120 (37%) | 188 (52%) | 15 (5%) | 323 |
| VIC | 780 (21%) | 2,569 (70%) | 338 (9%) | 3,687 |
| WA | 214 (25%) | 386 (46%) | 247 (29%) | 847 |
| Total | 6,766 (54%) | 4,869 (39%) | 938 (7%) | 12,573 |

To understand the evolution and national roll-out of the TCP, a description of the implementation of TC in each jurisdiction is presented in the subsections that follow.

### 1.2.1. Australian Capital Territory

The ACT has a single TC service which has been in operation since December 2005, making it one of the most mature TC services in the TCP.  ACT Health Transition Care Program had all 35 allocated places operational at 30 June 2007.  Of these 15, were operating as residential-based places and 20 were operating as community-based places.

### 1.2.2. New South Wales

NSW has 28 TC services located in metropolitan, regional, and rural areas throughout the state.  At June 2007 571 of the 703 allocated places were operational, with seven TC services yet to commence operations.  The majority of NSW places operate in a community-based setting (86% at 30 June 2007).  The first TC services in NSW began providing services in January 2006 (Richmond Valley Transitional Aged Care service, Transitional Aged Care Program - Prince of Wales Community Health Service, Tweed Transitional Aged Care Service) and TC has continued to be rolled out in the state since then.  Newer TC services have begun operation in 2008 in Dubbo and Lower Hunter.

### 1.2.3. Northern Territory

TC places have been allocated to three TC services in the Northern Territory with only one TC service (Katherine Transition Care Program) operational at 30 June 2007.  Both of the Alice Springs and Darwin services commenced operation in 2008.  Of the 16 allocated places, eight were operational at 30 June 2007 and all of these were residential-based places.  Katherine Transition Care Program has been operational since February 2007.

### 1.2.4. Queensland

Queensland has 12 operational services located in metropolitan, regional, and rural areas.  Gold Coast Transition Care Program, Bayside Transition Care, Brisbane South Transition Care, and West Moreton Transition Care were the earliest services to begin offering TC services in June - August 2006. At 30 June 2007 all but three TC services had commenced operations and these were located in rural areas of Queensland (Mackay, Tablelands, and Innisfail).  A total of 257 of the 351 allocated places were operational at 30 June 2007, and 240 (93%) of these were used as community-based places.

### 1.2.5. South Australia

There are four TC services in South Australia.  Country Health SA Transition Care Program delivers 26 places across rural and remote South Australia and the remaining places operate in the metropolitan area.  SA has two services that have been in operation for the longest period, commencing in October 2005.  In contrast to other jurisdictions, the flexibility of the TCP has led to 40 of the SA TC places being designated as residential-based and the remainder as 'mixed' so that they can be used as either community-based or residential-based places dependent on need.  At 30 June 2007, 147 of the 176 allocated places were operational.

### 1.2.6. Tasmania

Tasmania has two TC services that began operations in July and December 2006, respectively.  At June 2007 52 of the 57 allocated places were operational with 27 residential-based and 25 community-based places at this time.

### 1.2.7. Victoria

Victoria has 12 operational services and the second largest allocation of TC places.  Unlike other jurisdictions, more than half of the 424 operational places were used as residential-based TC places (n=247; 58%) at 30 June 2007.  This reflects that older people living in Victoria have access to a broad range of health services under the sub-acute system, and the Victorian TCP appears to service a more disabled group of people than programs in other jurisdictions.

### 1.2.8. Western Australia

Two TC services began delivery of services in Perth in 2006, with 100 places operational at 30 June 2007, half of which delivered TC in a residential-based setting.  An additional 60 places were allocated to the Western Australian Country Health Service with distinct operations in the Midwest and South West of this state.

## 1.3. Structure of the Final Evaluation Report

The current national and international literature is first reviewed, to place the operation of the Australian TCP in context. Each of the six key evaluation questions is then addressed in separate chapters of this report.

A discussion of the limitations in the evaluation methodology is then presented in Chapter 9.  The report concludes in Chapter 10 with a summary chapter and recommendations.

## 1.3. Structure of the Final Evaluation Report

The current national and international literature is first reviewed, to place the operation of the Australian TCP in context. Each of the six key evaluation questions is then addressed in separate chapters of this report.

# 2. Background and relevant literature

## 2.1. Australian context

Older people, those aged 70 years or older, accounted for about 31% of non-same day hospital episodes in 2004/05.  Demand for hospital services increases with age, with 353.5 non-same day hospital separations in 2004/05 for every 1,000 people aged 70 to 74 compared to 753.7 non-same day hospital separations in 2004/05 for every 1,000 people aged 85 or over (Australian Institute of Health and Welfare 2007).

Older people are also consumers of aged care services and again consumption increases with age.  About 4% of men aged 80 and 6% of women aged 80 are receiving permanent residential aged care at any one time, while at the peak of usage (age 96) 22% of men and 41% per cent of women are receiving permanent residential aged care at any one time.  Moreover, such cross-sectional data tends to understate the likelihood that an individual will require permanent residential aged care at some time in their life.  Life table analysis shows that, at age 65, an individual woman who has never received permanent residential aged care has a lifetime risk of entry to permanent residential aged care of 50% (32% for a man) (Liu, Braun et al. 2001).

Australian governments already contribute considerable resources to the provision of hospital and aged care services.  In 2004/05, for example, they provided $20 billion for public hospitals and $7.3 billion for aged care services (Steering Committee for the Review of Government Service Provisions 2007).  As the demand for hospital and aged care services increase with age, the ageing of Australia's population will see this expenditure increase significantly in real terms over the coming decades.  Commonwealth aged care expenditure alone is projected to increase from 0.8% of GDP in 2006/07 to 2.0% of GDP by 2046/47, while Commonwealth expenditure on public hospitals and private health insurance is projected to increase from 1.2% of GDP to 2.3% of GDP over the same period (Australian Government Department of Health and Ageing 2007).

Improving the allocative efficiency of both the hospital and aged care sectors, so that older people do not wait unnecessarily in hospital for a residential aged care place, and conversely so that older people are not prematurely discharged to residential aged care before they receive appropriate rehabilitation services to address reversible disability, will therefore become of increasing importance both for the health/aged care system as a whole as well as for the welfare of the individuals concerned.  The need to address these issues has been recognized by governments at all levels (Dwyer and Jackson 2001).  In 2004 the National Action Plan for improving the care of older people across the acute-aged care continuum 2004-2008 was endorsed by state and federal health ministers (Australian Health Ministers' Advisory Council 2004).  The TCP is an action which has emerged from Principle 4 of the plan and is provided as a form of flexible care under legislation from the Aged Care Act 1997.

### 2.1.1. Innovative Care Rehabilitation Service - Australia

The design of the TCP was informed by a series of pilots - The Innovative Care Rehabilitation Service (ICRS) pilot program (Department of Health and Ageing 2005).  Twelve pilots were established in 2001 to explore new approaches to the care of older people who had experienced a period of acute hospitalization.  In an evaluation of 11 of these pilots 1,640 completed episodes were examined and it was estimated that the interventions returned a high proportion of older people to the community with cost savings (Department of Health and Ageing 2005).

The pilots were directed at older people, who had completed their acute treatment phase, had been assessed for admission to long term residential aged care, and who were thought likely to benefit from a phase of rehabilitation.  The average entry MBI was 67.3 (77 in the community-based and 61 in the residential-based setting), the average age was 81.5 years, and 58% were living alone.  Their outcomes were generally positive with a hospital readmission rate of 18.1%.  Three months post discharge 87.7% of those who could be contacted were still residing in the community.  Six months post discharge 84% of those who could be contacted were still residing in the community.  An important finding was that 69 people (4.2%) entered residential aged care as low care after having an ACAT assessment and being assessed as requiring high level care.  The report addressed the issue of whether the program should be offered to the dementia population but noted that many pilots had excluded dementia and the overall numbers were so small (3.1% of the ICRS client group) that they could not draw conclusions.

The estimated daily cost of the residential-based episode was $236 per day ($10,500 per ICRS episode) and in the community-based setting costs were estimated as $86 per day ($5,300 per ICRS episode).  Based on a total expenditure of $16 million, the cost/benefit analysis suggested that $4.7 million dollars of savings were achieved under the strong assumption that those who received ICRS services would have otherwise had residential aged care for the same duration.  However, no controls were available to permit accurate assessments of what might have happened in the absence of TC.

While there were differences between the 11 pilot sites in terms of medical (both geriatrician and GP), allied health, and nursing input overall they demonstrated an increase in physical function and a significant return home rate. However, there were no control groups in this evaluation so the design did not allow robust assessment of the additive benefits that TC recipients had made to the individual over and above natural recovery. An important limitation the evaluators faced was the difficulty tracking individuals to establish outcomes so the results were biased towards detecting positive outcomes.

In summary, the ICRS evaluation suggested significant cost savings were associated with the new model of care. However, without a control group and with incomplete follow-up data estimates were difficult.

### 2.1.2. 	South Australian randomized controlled trial of a residential transitional care unit

In 2003/04 as part of the Commonwealth's National Demonstration Hospitals Program Phase IV, 320 older people admitted to a public hospital in Adelaide participated in a randomized controlled trial after a decision was made that they should go to residential aged care (i.e. after receiving an ACAT assessment).  Participants were randomized to either stay in hospital to await transfer to a residential aged care facility or move to an offsite facility run by an aged care organization and were provided with therapists and doctors from the local hospital (Crotty, Whitehead et al. 2005). Everyone in the hospital who had received an ACAT assessment and was waiting on residential aged care was eligible for transfer and was approached to take part in the trial.  At four months there were no differences in outcomes (deaths, function, or readmissions) and hospital beds had been emptied.  The approach was less efficient overall as those who moved to the offsite facility took three weeks longer (total hospital and transitional care days) to reach their final residential aged care bed than those who remained in hospital.  However the hospital gained a median of 11 bed days by moving the older adults out of an acute bed which allowed them to admit someone else.

While 7% of those in the group who went into the transitional care unit went home after the ACAT assessment, a similar number went home without any intervention underlining the fact that some people will recover with no intervention at all.  The design of this study eliminated the selection bias which confounds evaluations of these programs and once the selection bias was removed, the assessment of outcomes (return home, improvement in function) was less positive than seen in the ICRS pilots.

Probably the most important finding in this study was that there was no increase in adverse outcomes such as deaths and the transitional care unit did not appear unsafe which had been a major concern of clinicians.  While this program allowed "unblocking" of beds and cost shifting to the Commonwealth from the acute sector, an assessment of the total time to care highlighted the potential inefficiencies of this approach to overall flows. No cost study was included but it is unlikely that overall cost savings were achieved as the older people who moved to the offsite facility faced additional costs given that they paid a contribution fee.

A qualitative adjunct study was also undertaken with 31 carers, which found that although the transitional care unit did not reduce the stress experienced by carers when they searched for a permanent residential aged care facility it was an acceptable alternative to waiting in hospital (Daff, Stepien et al. 2006).

Very little work has been published since the NETCP began.  In July 2006 an audit was conducted at three sites of the first 30 participants in three new TC services based in Adelaide and Sydney.  The audit confirmed that the residential-based services were taking more complex medical cases than the community-based services and there was heterogeneity amongst clients (Cameron and Davies 2007).

## 2.2. Intermediate Care in the UK

Intermediate Care has influenced the TC model.  It was evaluated in the UK using a comparative case study design to look at the program from different stakeholder perspectives at different levels (system, service, individual levels) (Godfrey, Keen et al. 2005).  The evaluation was undertaken by researchers at the University of Leeds and the economic analyses by researchers form the University of York.  Quantitative patient data for 7,452 service users admitted to Intermediate Care over one year were analysed together with data for a cohort admitted in a month (n=153) who were tracked for six months.  Sixty-four users were interviewed and 247 interviews were conducted with staff.

The evaluation found Intermediate Care included diverse programs such as conventional rehabilitation programs as well as programs in the Emergency Department aimed at preventing admission.  There was no core data set used by services which made evaluation difficult as there were no common outcomes across services.

Observational data suggested that there had been changes in the structure of service delivery, largely a shift in providers' culture to a focus on client centred goals.  There was movement toward cross agency, multidisciplinary working but the extent of this was variable.  The patient level evaluation suggested that the experience of "recovery" was much longer than the Intermediate Care episode.  Finally, the evaluation concluded that the programs needed more medical involvement at strategic and operational levels to improve the quality and effectiveness of the service which implied the program had struggled to get engagement in the early phase.  The researchers identified three elements of "good user centred Intermediate Care" which defined its quality:

- Enabling ethos which boosted individual's confidence

- Partnership with informal support networks to maintain and sustain recovery

- Links into ongoing practical, clinical and social support services

Given the research approach, the researchers were cautious about committing to whether Intermediate Care "worked".  The major conclusion of the report was to describe the nature of the program in conceptual terms.  Essentially it was described as "cloud-like", as a program which cannot be reduced to individual service components but should be "conceived of as a system of care in the space between locations, sectors, and states". Importantly it was noted that there was wide variation in the allocation of resources and the expenditure of the various programs.

Intermediate Care has fostered an outcomes focused approach in community settings with a strong emphasis on change outcomes (Glendinning, Clarke et al. 2008).  Qureshi et al. identified three types of outcomes desirable in older people (Qureshi, Patmore et al. 1998). Change outcomes describing improvements in physical, mental, and emotional functioning.  Maintenance outcomes prevent or delay deterioration in health well being or quality of life.  These include: living in a clean environment, having access to social contact, control over everyday life and there are consistencies between these outcomes and older people's definitions of quality of life (Walker and Hennessy 2004).  Finally, process outcomes refer to the experience of seeking, obtaining, and using services.  These include feeling valued and respected, being treated as an individual having control over how and when services are provided.  Intermediate Care is focused on change outcomes and this has led to some debate (Glendinning, Clarke et al. 2008).

## 2.3. Post Acute Care in the US

In the US post acute care (PAC) is seen as an extension of hospital care but there is a high dependence on nursing home facilities for its provision. Medicaid is the primary public payer for long-term care and Medicare the primary payer for acute care and in 2005 Medicare spent $42 billion on PAC services which represents 13% of all Medicare benefit spending.  Acute hospital stays in US hospitals are short and PAC has a number of venues, which include formal inpatient rehabilitation facilities, skilled nursing facilities, long term care hospitals, and home health care.  Overall, one third of Medicare patients leaving acute care hospitals in 2002 received some form of PAC (Buntin 2007) but non-clinical factors play a large part in the deciding which patient groups access which post acute service.  Among the non-clinical factors affecting use of PAC is geographic location with those in rural areas less likely to access any PAC (Kane, Lin et al. 2002). The US is currently reviewing PAC approaches recognising that the payment policies have focused on the phase of illness rather than care needs and services, and although patient characteristics may be similar the payments across PAC setting are different.  In January 2008 a demonstration program was established which will run for a three year period and report to Congress with recommendations on changes.  The aims are to standardize patient assessment information, use the data to inform payment policy and develop a reimbursement policy that is patient-focused rather than facility-focused.  However, there is also an emphasis on improving the management of transitions between care settings and increasing consumer choice and control (Centers for Medicare and Medicaid Services 2006).

Many US evaluations use outcomes research approaches taking advantage of large administrative data bases (Neu, Harrison et al. 1989; Kane, Finch et al. 1996; Kane, Chen et al. 1998; Chen, Kane et al. 2000). In a comparison of joint replacement management across settings in the US it was found that 30% of people who had joint replacements went to Subacute Nursing Facilities (SNFs), 35% to inpatient rehabilitation facilities and 35% directly home with home care, outpatient therapy, or no care (Kaplan 2007).  The outcomes from these sites differed but it is unclear to what extent this is a result of case selection or interventions offered.  In rehabilitation facilities, of those discharged 14 or more days after admission, 1% walk independently at admission while 76% walk independently at discharge.  For SNF patients 9% walk independently at admission but only 31% walk independently at discharge.  The differences are not in the case mix but those patients in SNFs are older with more co-morbidities, and the reimbursement in SNFs is lower so again it remains unclear the degree to which the type of care provided is contributing to outcomes.

Lack of clinical consensus about where various conditions should be treated e.g. whether hip fractures should be treated in rehabilitation units or nursing home units in the US has made the choice of PAC sites highly vulnerable to the influence of financial factors (Kramer, Steiner et al. 1997; Parker, Bhakta et al. 2000; Buntin 2007).  Outcomes are emphasised and innovations which include bundled payments and pay for performance (e.g. adherence to protocols, avoidance of adverse outcomes) have focused on improving outcomes such as reduction of hospital readmission and reduction of falls.

New consumer directed approaches (e.g. Cash and Counselling) which increase the level of consumer choice and control over Medicaid funds for obtaining personal care services and home and community based services have been assessed for provision of long term care services.  Evaluations have been undertaken to see whether an approach where the allowance is directly made to the consumer will improve outcomes of beneficiaries and carers without increasing Medicaid costs per recipient (Dale and Brown 2007).  Recipients can use funds allocated to them to pay family members to provide home-care or pay agencies or purchase equipment and home modifications.  The initial evaluations of these programs found high levels of satisfaction and improvements in caregiver well-being but a Medicaid cost increase which has resulted in further iterations of the program to reduce the costs of consumer direction and increase levels of monitoring (Dale and Brown 2007).

The US SNFs appear similar to residential-based TC units set up in some Australian states although the US facilities have medical directors and more medical involvement.  They are also designed to accommodate a mix of long term care and acute patients so have appropriate equipment such as gyms.  Little work has been undertaken on the effects of multidisciplinary care models within the SNF environment (Kauh, Polak et al. 2005).

In summary, very short lengths of stay and a high demand for PAC have led to blurred lines between rehabilitation and PAC.  This has been compounded by the lack of evidence on the cost effectiveness of various settings.  Economic incentives resulting from different payment systems have led to non patient-centred decisions about types of PAC offered and to payments based on site of care rather than type of care, so a large demonstration project is underway to inform a reform process.  The major lessons from the US outcomes literature are the need for: cost effectiveness studies for different models of post acute care for different conditions, the importance of common assessment tools, and the utility of outcome data sets to monitor selection practices, outcomes and costs.

## 2.4. 	Methodological difficulties evaluating post acute care and rehabilitation interventions

Assessing the effects of rehabilitation type interventions involves assessing the change the intervention made to a clinical trajectory over time while recognising the significant role in recovery of environment, informal care, and socio-economic status (Kane 2007).  Issues that are problematic are the timing of measurement, identifying which outcomes to measure, how to measure the intervention, whose perspective the evaluation undertakes, and controlling for case-mix.  Finally, there is an ascertainment bias where the evaluators will focus on outcomes which they have knowledge of and will investigate these issues more thoroughly.

Of particular importance in evaluations of post acute care interventions is the confusion between settings and services  and the subsequent confusion about the quality of the outcomes from these sites (Stone 2000).  If a clinical intervention which is delivered in a specialist setting (e.g. rehabilitation unit) has better outcomes than the same intervention being offered in a non specialist setting (e.g. residential aged care) then it may be the staff mix and not the location that is the important difference (Parker, Bhakta et al. 2000).  The inefficiencies associated with differing sites of care are often related less to the sites than to the staffing patterns.  Even within hospitals, short hospital lengths of stay are associated with increased readmission rates of older people.  However, higher staff intensity ratios can compensate for this (Heggestad 2002).  More acute care (such as IV antibiotics, wound care, ventilation) is now provided in non-hospital settings particularly in the US but the funding source rather than the goals of the care or the characteristics of the recipient have primarily determined whether the care is considered acute.

## 2.5. The heterogeneity of the population targeted by Transition Care

The frail population of older adults who make high use of hospitals are described as generally 75 years or older, disabled in Activities of Daily Living (ADL) and instrumental ADL, with acute and chronic medical problems, having impaired social networks, making frequent transitions (community, residential aged care, hospital), and needing complex combinations of medical and social services.  The concept of frailty is used widely in the care of older people and although controversy still surrounds the definition it is conceptualized as a state of increased vulnerability to stressors which results from decreased physiologic reserves and dysregulation of multiple systems (Fried, Ferrucci et al. 2004).

One difficulty in providing post hospitalization services is the overlap between chronic care, transitional care, and end of life care and although it is not always apparent to TC services which group of patients they are treating, the service needs, and priorities of care differ.  A NSW study found that in 2002 10.3% of all hospital days and 8.9% of all hospital inpatients costs were used by people aged 65 and older in their last year of life (Kardamanidis, Lim et al. 2007).  The palliative care literature describes three trajectories for individuals with chronic and eventually fatal illness (Lunney, Lynn et al. 2002; Murray, Kendall et al. 2005) and while interventions with older people are often targeted at those most likely to face readmission and movement into supported care (Naylor, Brooten et al. 1999) services are being provided to people on different trajectories and the interventions need to be individualized.  While geriatric rehabilitation and palliative care services are rarely provided by the same group of providers, the client group may overlap.

Figure 2.1: Prototypical trajectories of the disablement process (Freedman, Hodgson et al. 2006)

In this model of end of life three possible groups of older people are apparent.  The first trajectory represents someone typically associated with end of life care e.g. a solid tumour with a short period of rapid, relatively predictable decline (Lunney, Lynn et al. 2002).  The other trajectories may well be picked up in programs for older people such as TC.  The second trajectory represents chronic organ system failure with a gradual decline marked by exacerbations and hospitalization. Chronic heart failure, emphysema, and renal failure are typical and 25% of deaths in the US fit into this category (Lunney, Lynn et al. 2002).  The third trajectory is poor long term functioning with slow decline.  Very old patients with frailty, dementia, and multiple comorbidities fit into this category.  Around 40% of individuals in the US belong to this group (Lunney, Lynn et al. 2002). There can be a shift between hospitals and aged care services during these trajectories.  For example in NSW, hospital end of life costs decrease with increasing age at death with those over 85 less likely to die in hospital.  The decline in hospital costs is offset by an increase in the costs carried by residential aged care.  To date there has been no complete assessment of the "cost of dying" in Australia or on the amount of the costs shared by these sectors (Kardamanidis, Lim et al. 2007).

## 2.6. 	What evidence lies behind the models of Transition Care used in Australia?

TC has used two major models of service delivery: community-based places which support frail older adults or residential-based places located either in residential aged care facilities or in hospitals.  The evidence behind these service models in use in the Australian program will be summarized:

- Packages of care to support remaining independent in the community

- Low cost beds in residential aged care which provide an alternative to a hospital bed Many demonstration projects assessing home packages and discharge supports have been evaluated and comprehensive meta-analyses of these community based programs are starting to emerge which summarise the effects (Beswick, Rees et al. 2008).  The literature behind the provision of alternate settings for beds is limited and generally poorer in quality (Carpenter, Gladman et al. 2002).

- Integrated care models attempt to move away from silo project assessments towards evaluations of system level change.  There is less literature in this area which merges with evaluations of government health service innovations and is often difficult to access.

### 2.6.1. Evidence base for Transition Care in the community setting

A large base of primary trials inform this approach ranging from discharge planning interventions such as home visits, to geriatric assessment approaches.  Several important systematic reviews have been undertaken over the last decade to summarise the evidence on home-based care (Hughes, Ulasevich et al. 1997), early discharge programs (Shepperd and Iliffe 1998) and best place of care (Parker, Bhakta et al. 2000).

The most comprehensive systematic review examining interventions to improve function and maintain independent living in older people included 89 trials covering 97,984 people and found multi-factorial interventions could improve function, reduce hospital admission, falls, and residential aged care admission but not death (Beswick, Rees et al. 2008).  The effects however, were small with a reduction in hospital readmissions from 40.5% to 38.2%, a reduction in transfer to residential aged care of 10.6% to 9.2% over six months and a very small shift in function (Beswick, Rees et al. 2008).  There are few economic assessments of these interventions but the authors concluded that given the high costs of hospital and residential aged care compared to community care, small reductions are likely to offset the costs of interventions (Chappell, Dlitt et al. 2004).

In the face of the very high hospital readmission rates noted internationally in this frail older group there has been a shift away from models which do not include medical assessment as part of multi-factorial care (Black 2007) and towards programs which include an accurate medical diagnosis as part of the intervention to identify potentially reversible causes of falls and disability and increase the chances of effect (Stott, Langhorne et al. 2008).

While many programs are set up using a traditional rehabilitation approach which emphasises physical reconditioning, the population who benefit is not limited to those with physical disability.  Given the comparatively modest functional gains noted in systematic reviews and the lack of evidence emerging for a "dose" effect i.e. the intensity of the programs are not related to the level of improvement, there has also been a call for inclusion of patients with dementia in these types of programs.  While rehabilitation programs have historically been wary of patients with dementia and excluded them from inclusion there are now studies confirming benefits (Tappen, Roach et al. 2000; Rolland, Pillard et al. 2007) and it is probable that those most likely to gain from intervention are those at highest risk of admission to hospital or residential aged care which includes those with dementia (Stott, Langhorne et al. 2008).

Improved discharge planning and reorganized PAC with more active medical oversight and active involvement of physicians during transitions is associated with lower readmissions into acute care (Naylor, Brooten et al. 1999).  A systematic review examining discharge planning found that coordinated discharge of elderly people across hospital-community interfaces reduces hospital readmissions by 17% (Parker, Lee et al. 2004). Case management is a popular strategy but is been only weakly associated with preventing hospital readmission (Hutt, Rosen et al. 2004).  In 2002, the UK pilots were funded in 10 primary care units known as the UK Evercare program to evaluate combined nurse led assessment and intensive case management in the community.  They focused on older people at risk of readmission and an initial assessment in 2005 found that the benefits were mostly in terms of quality of care (United Health Europe 2005).  A later evaluation found no effects on emergency admissions, emergency bed days, or mortality (Gravelle, Dusheiko et al. 2007).  Despite this evaluation "community matrons" who are trained in care coordination, patient communication, and advocacy have been introduced in the UK with the goal of achieving a 5% reduction in hospital admission.  It is hoped that they will bridge social and clinical needs of patients. While it is anticipated that they will be popular with older people and increase access to care, it is thought unlikely that they will affect hospital readmissions without further system redesign e.g. strengthening of primary care (Gravelle, Dusheiko et al. 2007).

Importantly there are risks associated with assessment approaches in older people.  In a 1996 Australian trial assessing the impact of preventive health assessments for older veterans and war widows (Byles, Tavener et al. 2004), small positive improvements were demonstrated in quality of life amongst those who remained resident in the community.  However, there was no effect on mortality or hospital admission and disturbingly there was an increase in the movement into residential aged care presumably because the comprehensive assessments uncovered problems.

Trials attempting to improve the coordination of care without system redesign have also been associated with ambiguous results.  In 1997 the Australian Government funded nine national trials of Coordinated Care to test new models of service delivery for chronic conditions and many of these trials included older people (Council of Australian Government 1995).  The hypothesis was that the better coordination of people with chronic or complex needs would reduce hospitalization and the savings would cover the cost of coordination. The results found no improvements in health and no savings were demonstrated.  Three trials showed reductions in hospital readmission rates and most trials went into deficit.  Numerous reasons were put forward to explain the weak effects (often by the trialists) including: "the constraints of a controlled trial and a rigid hypothesis driven national evaluation", patient heterogeneity, short term follow-up (Battersby, Harvey et al. 2007), and poor outcome selection (Esterman and Ben-Tovim 2002).  Victoria's post acute program included an implementation trial which examined the effects of case management, post acute nursing, and community services on 654 older people following hospital discharge (Lim, Lambert et al. 2003) and was unable to show reductions in hospital readmissions but over six months found reductions in days in hospital.

A key message that these ambitious Australian trials highlight is the risk of overemphasising assessment. Uncovering unmet needs in complex older people without the capacity to then provide services or interventions to address those needs has been in an issue in several care coordination studies (Weaver, Hickey et al. 2008).  The hope is that more utilization of services in the short term will be offset by longer stays in the community, but long term evaluations have not been undertaken to test this assumption.  In addition, the trials demonstrate the difficulty in re-engineering the Australian health system from an acute to a chronic focus is apparent and the likelihood of achieving, at best, very small effects if follow-up periods are short.

### 2.6.2. Evidence base for Transition Care in the residential setting

Pressures on hospitals have reduced the lengths of stays in many countries.  Between 1982 and 1993 length of stay for geriatric patients in England dropped by 60% and in Australia between 1992 and 2002 specialist geriatric beds decreased by 24.8% (Gray, Dorevitch et al. 2002).  The evidence for alternative sites of care (e.g. nurse led wards, nursing home sites) to treat older people who often need more time to recover has been reviewed (Parker, Peet et al. 2002).  The review concludes that the quality of trials on nurse led beds is poor and there is considerable uncertainty about both costs and outcomes of these alternate approaches.  A more positive message is that there is no evidence that alternate settings adversely affect mortality.

As a result of the poor evidence on nurse led trials, debate has occurred in both the UK and more recently Australia around the "opportunity cost" of funding bed substitution programs (Black 2007; Gray, Travers et al. 2008).  The weak results from trials evaluating these interventions has been contrasted with the lack of investment in inpatient rehabilitation which remains the only intervention firmly associated with reduced mortality and institutionalization rates as well as improved functional rates (Stuck, Siu et al. 1993; Evans, Connis et al. 1995).  However, this debate is often fuelled by an emphasis on substitution approaches as a form of cost cutting, which distracts from the important discussion about where is the correct place of care for older people to receive treatment.

### 2.6.3. Evidence base for Integrated Systems of Care

Demonstration approaches are often defined by where the projects are delivered (e.g. at home, in residential aged care facilities).  However, when implemented as health programs where the emphasis is on flows across a system, the focus tends to shift away from individual outcomes towards measures of integration across services areas and towards measures which indicate improving coordination.  Once programs enter the health system governance issues, payment incentives, and sector alignments become more significant.  Although there are very limited rigorous analyses of effects and in particular on the cost effectiveness in these programs a group of programs known as integrative service delivery (ISD) programs have been developed to improve continuity and increase efficiency.

ISD programs aim to improve continuity and efficiency of services and have been defined as "a discrete set of techniques and organizational models designed to create connectivity, alignment, and collaboration within and between the cure and care sectors at the funding administrative and/or provider levels" (Kodner and Kyriacou 2003).  These models have shown variable levels of success in reducing movement into permanent aged care and they have struggled to engage primary care physicians.  Three levels of integration are recognized: linkage, coordination, and full integration (Leutz 1999).  Full integration models include PACE (Program of All inclusive Care for the Elderly) projects (Branch, Coulam et al. 1995; Gross, Temkin-Greener et al. 2006), Social Health Maintenance Organization (S/HMO) in the US (Harrington, Cassel et al. 1991), and SIPA (systeme de services integers pour personnes agees en perte d'autonomie) in Montreal (Beland, Bergman et al. 2006).  Capitation budgeting is usually a key component of these programs which attempt to integrate acute and longer term care delivery and financing to provide alternatives to nursing home placement. Co-ordination models such as PRISMA (Program of Research to Integrate the Services for the Maintenance of Autonomy)  are established at the strategic level (governance) of health care, social services, and community agencies where the decision makers agree on the policies and orientation then at the management levels, with a service co-ordination committee and at the operational level (Hebert, Durand et al. 2003). PACE is provided for frail elders eligible for Medicaid and nursing home certifiable. It uses an ISD model with adult day care as the focal point and vigorously attempts to keep individuals out of nursing homes (Branch, Coulam et al. 1995).  The US Department of Veteran Affairs most recently has evaluated three models of providing All-Inclusive Care for frail elderly veterans who meet the criteria for nursing home placement and found days in SNFs increased but rates of permanent institutionalization decreased (Weaver, Hickey et al. 2008).

Lack of integrated systems of care for older people with both medical issues (such as co-morbidities, physical, and psychological health) and social factors (including support and housing) may adversely influence their ability to live independently in the community (Stuck, Walthert et al. 1999; Ayis, Gooberman-Hill et al. 2006).  Reform programs which enhance clinical integration include innovations such as: the pooling of health and social service resources, establishment of new cross-border roles to assist patients and families e.g. transition managers (Coleman, Boult et al. 2003) and case managers (Gravelle, Dusheiko et al. 2007).  This area of research is evolving and overlaps with the work on coordination.  A 2007 report from the Organization for Economic and Co-operation and Development (Hofmarcher, Oxley et al. 2007) summaries four key areas for policy reform faced by all countries attempting to enhance the capacity of health care systems to better coordinate care:

- Better patient information systems to allow transfer between providers and across institutional boundaries.

- Review of the share of overall resources allocated to ambulatory care settings.

- Issues around how payment arrangements can be aligned to incentivise integration.

- Concerns about how best to break down barriers between care "silos".  The issue was noted to be particularly important for transitions into long term care where problems are most fragmented.

## 2.7. Summary

The TCP was developed by policy makers to address political issues while the literature emerges from predominantly clinical practice interventions focused on maintaining frail older people in the community.  The research literature tends to focus on evidence for efficacy, effectiveness, safety and cost benefit but there is very little information on effective ways to achieve system change for older people.  The evidence for multifaceted interventions delivered by multidisciplinary teams in the community suggests functional gains are obtainable and small reductions in levels of re-hospitalization and transfer to aged care are possible.  The literature on using alternative sites to hospitals as beds is poor and there is little to suggest that it is efficient. US models of PAC have identified case selection and payment incentives as important but there are very few assessments of the cost effectiveness of various post acute programs for different conditions. Comprehensive data capture across care sectors is required to drive quality improvement and improve payment efficiency. Finally, the literature confirms that many western countries are engaged in an iterative redesign process as they attempt to reorient away from acute care towards chronic care and improve the integration of health and social services.

# 3. Transition Care recipients: Characteristics and outcomes

## Key points

- The sample of 2,443 linked records for TC recipients represents 76.2% of the 3,206 approvals for TC between 1 October 2006 and 31 March 2007.

- Sixty-four percent of the TC recipients were female, TC recipients had an average age of 82.2 years and 41% had a co-resident carer.

- Overall, the mean MBI at admission to TC was 64.5 units and at discharge was 75.7 units.  Those who received community-based TC had admission and discharge mean MBIs of 75.2 and 86.0 units, while those who received residential-based TC had lower physical functioning with mean 51.6 and 62.3 units at admission and discharge, respectively.

- The median length of stay in TC was 71.3 days, overall, shorter for recipients of TC only in a residential setting (38.0 days) in comparison with recipients of TC only in a community setting (58.0 days).

- Both recipients and carers reported high levels of satisfaction with TC.  However, one third did not know the purpose for taking their medications.

- During the three months following ACAT approval, 37% of recipients were readmitted to hospital, higher amongst those who received community-based TC (39%) than residential-based TC (35%).  Twenty-two percent had a permanent admission to residential aged care and 8% died.

- By six months post ACAT approval, the hospital readmission rate had increased to 47% for all recipients, again higher for community-based versus residential based TC (51% versus 43%).  Twenty eight percent had a permanent admission to residential aged care and 14% died.

Outcomes at three month post-ACAT assessment for a cohort of 5,510 older people (2,443 TC recipients, 879 Control 1 and 2,188 Control 2) were reported previously in the Controlled Comparison Study and Costs and Effects Study (National Evaluation of the Transition Care Program 2008).  Aggregated data for individual level outcomes were also reported in the Models of Transition Care Report (National Evaluation of the Transition Care Program 2007a) and Recipient Snapshot Study (National Evaluation of the Transition Care Program 2007b).  In this section, these findings are synthesised and some additional findings in terms of hospital readmissions, residential aged care admissions, and deaths at six months post ACAT approval are also presented.  Data are also drawn from the Australian Government Department of Health and Ageing COGNOS database concerning TC to supplement existing data.

Three groups were compared in Controlled Comparison and Costs and Effects Study.  The groups were defined as follows:

- TC recipients - People who were ACAT assessed in an acute or other hospital setting between 1 October 2006 and 31 March 2007, were approved to receive TC, and subsequently completed a TC episode by 30 September 2007.

- Control 1 - People who were ACAT assessed in an acute or other hospital setting between 1 October 2006 and 31 March 2007, were approved to receive TC, but with no TC episode by 30 September 2007. This group did not progress to the program despite approval.

- Control 2 - People who were ACAT assessed in an acute or other hospital setting between 1 October 2006 and 31 March 2007, were approved for CACP but not TC.

As shown in Table 3.1, there were 3,206 ACAT approvals for TC where assessment took place in the acute or other inpatient setting between 1 October 2006 and 31 March 2007.  Table 3.1 presents a comparator of the number of TC recipients from each state included in the data linkage sample versus the number of approvals for TC in the same period.  A further comparison can be drawn from the number of people admitted to TC in the same period.  TCP COGNOS admissions data show that 3,418 people were admitted to TC between 1 October 2006 and 31 March 2007.  The data linkage sample appears to have captured the majority of TC recipients in all jurisdictions with the exception of NSW.

### Table 3.1: Sample of Transition Care recipients and number of ACAT assessments 1 October 2006 - 31 March 2007

Data linkage

| State | Data Linkage TC recipients | ACAT assessment | TCP admissions data |
| --- | --- | --- | --- |
| ACT | 69 | 114 | 91 |
| NSW | 630 | 1,194 | 1,219 |
| NT | 12 | 20 | 12 |
| QLD | 273 | 300 | 309 |
| SA | 289 | 403 | 354 |
| TAS | 98 | 111 | 104 |
| VIC | 934 | 1,435 | 1,098 |
| WA | 138 | 290 | 231 |
| Overall | 2,443 | 3,206 | 3,418 |

## 3.1. Baseline characteristics of Transition Care recipients

Baseline characteristics of TC recipients from the cohort in the linked data set (i.e. n=2,443 TC recipients) are presented in Table 3.2.  As this table shows, the average age of recipients was more than 80 years and slightly more than one third of recipients were male.  The average improvement in MBI was slightly more than 10 points on average.  Not unexpectedly, the MBI at admission was higher among the community-based TC recipients than the residential-based TC recipients.  The data concerning indigenous status from the Aged Care Client record (ACCR) suggested that 0.2% of recipients identified as Aboriginal or Torres Strait Islander or both.  More than three quarters of TC recipients were in private residences prior to TC admission, and almost half of TC recipients lived alone prior to their ACAT assessment.  A total of 41% had a coresident carer at the time of ACAT assessment.

Twenty three percent of TC recipients elected to be treated as private hospital patients.  Election status at the index hospitalization was unavailable for recipients in Victoria and Tasmania.  The data concerning election status was derived from different variables for each of the hospital morbidity data collections.  In Western Australia it was derived from insurance status while in South Australia, Queensland, and New South Wales it was based on payment at separation.

Of the 2,443 TC recipients, 1,204 (49%) received TC only in a community setting, 1,026 (42%) received TC only in a residential setting, and 213 (9%) received TC in both a community-based and a residential-based setting.

### Table 3.24:  Baseline characteristics of recipients of Transition Care

| Recipients | All | Community | Residential | n | Data source |
| --- | --- | --- | --- | --- | --- |
| Age mean (SD) | 82.2 (8.0) | 81.0 (7.7) | 83.2 (8.3) | 2,443 | ACCR/Medicare |
| Gender % male | 36% | 35% | 37% | 2,443 | ACCR/Medicare |
| Number of ACAT assessments mean (SD) | 1.07 (0.26) | 1.08 (0.28) | 1.06 (0.24) | 2.443 | ACCR/Medicare |
| MBI on admission mean (SD) | 64.5 (24.2) | 75.2 (18.0) | 51.6 (25.1) | 2,443 | TC program |
| MBI on discharge mean (SD) | 75.7 (25.3) | 86.0 (17.5) | 62.3 (27.7) | 2,443 | TC program |
| Length of stay in TC (median, IQR) | 52 (28-75) | 58 (37-78) | 38 (19-62) | 2,443 | TC program |
| Length of stay in TC ex. Deaths, d/c to hospital (median, IQR) | 57 (35-78) | 65 (46-81) | 41 (22-66) | 2,443 | TC program |
| Indigenous status % | 0.20% | 0.30% | 0 | 2,158 | ACCR |
| Usual client accommodation setting % |  |  |  | 2,158 | ACCR |
| Private residence owned or rental | 79% | 86% | 73% |  |  |
| Independent living in retirement village | 6% | 6% | 5% |  |  |
| Supported community | 2% | 0.20% | 5% |  |  |
| Residential aged care – Low Level Care | 4% | 0.30% | 8.40% |  |  |
| Residential aged care – High Level Care 0 | 0 | 0 |  |  |  |
| Other | 8% | 7% | 7% |  |  |
| Usual client living arrangements % |  |  |  | 2,158 | ACCR |
| Lives alone | 49% | 46% | 50% |  |  |
| Lives with family | 43% | 51% | 38% |  |  |
| Lives with others | 2% | 2% | 3% |  |  |
| Not applicable/not stated | 5% | 1% | 10% |  |  |
| Coresident carer % | 41% | 45% | 39% | 1,984 | ACCR |
| Measure of cognition % cognitively impaired | 24% | 14% | 34% | 2,157 | ACCR |
| Primary health condition at admission to TCP |  |  | 2,158 | ACCR |  |
| Infectious and parasitic disease | 0.50% | 0.50% | 0.50% |  |  |
| Neoplasms | 3.60% | 2.80% | 4.50% |  |  |
| Blood, blood forming organs & immunological disorders | 0.30% | 0.30% | 0.30% |  |  |
| Endocrine, nutritional and metabolic diseases | 2.30% | 2.10% | 2.60% |  |  |
| Mental and behavioural disorders | 12.40% | 6.40% | 18.40% |  |  |
| Diseases of the nervous system | 4.20% | 4.80% | 3.80% |  |  |
| Diseases of the eye and adnexa | 0.70% | 0.70% | 0.60% |  |  |
| Disease of the ear and mastoid process | 0.10% | 0.00% | 0.20% |  |  |
| Diseases of the circulatory system | 23.40% | 25.20% | 22.50% |  |  |
| Diseases of the respiratory system | 4.60% | 4.60% | 5.00% |  |  |
| Diseases of the digestive system | 2.80% | 3.80% | 1.90% |  |  |
| Diseases of the skin and subcutaneous tissue | 0.90% | 0.90% | 1.10% |  |  |
| Diseases of musculoskeletal system & connective tissue | 4.60% | 5.90% | 3.40% |  |  |
| Diseases of the genitourinary system | 2.10% | 2.80% | 1.70% |  |  |
| Congenital malformations, deformations 0% | 0% | 0% |  |  |  |
| Injury, poisoning and other consequences of ext. trauma | 24.10% | 26.40% | 20.30% |  |  |
| Symptoms, signs not otherwise classified 11.00% | 9.60% | 12.10% |  |  |  |
| Time from ACAT to TCP admission median (IQR) days | 4 (1-8) | 4 (2-8) | 4 (1-8) | 2443 | ACCR/TCP |
| Main language spoken at home |  |  |  |  |  |
| English | 87% | 89% | 85% |  |  |
| German | 1% | 0.30% | 1% |  |  |
| Greek | 2% | 1% | 3% |  |  |
| Italian | 3% | 3% | 3% |  |  |
| Polish | 1% | 0.30% | 2% |  |  |
| Other | 6% | 6% | 6% |  |  |
| Patient election status at initial referral1 % private | 23% | 20% | 22% | 1,169 | Hospital morbidity collections |

1: based on ACT, NSW, QLD, SA, WA

## 3.2. Function

Evidence for a functional outcome of the TCP is based on the MBI, and this outcome has been considered in each of the three aforementioned reports.

The Models of Transition Care Report (National Evaluation of the Transition Care Program 2007a) demonstrated that overall the average MBI at admission to TC was 64.3 units and at discharge was 76.9 units, representing a change of 12.5 units.  It is important to note that those who died or were discharged to hospital are coded as '0' in the TCP Program Management Data Set, and these cases have been excluded in the calculation of the discharge MBI (National Evaluation of the Transition Care Program 2007a).  When expressed as MBI change per day of stay, this gives an MBI efficiency of 0.26 units.  For TC delivered only in a community setting, the average MBI at admission was 73.7 and discharge 84.8, representing a change of 11.1 units. The change from admission to discharge MBI among TC delivered only in a residential setting was greater, being 51.1 at admission and 65.0 at discharge, with a change of 13.8 units.

This finding must be interpreted bearing in mind the considerable diversity both between and within states or territories in terms of client profile and functional capacity.  Telephone-based interviews with recipients of TC at three months post TCP-discharge showed a mean MBI of 84.5 (SD 22.1) units, and this was higher among the recipients receiving TC only in a community setting (88.7 SD 17.0) than those who received TC only in a residential setting (74.0 SD 29.1).  Among the group of TC recipients for whom linked data was available (n=2,443), the average MBI on admission to TC was 64.5 units (SD 24.2) and on discharge was 75.7 units (SD 25.3).  This can be further decomposed to type of TC received, which showed that those who received TC only in a community setting entered with an average MBI of 75.2 units (SD 18.0) and were discharged with an average MBI of 86.0 (SD 17.5).  For those who received TC only in a residential setting, the mean MBI on admission to TC was 51.6 units (SD 25.1) and the mean MBI at discharge from TC was 62.3 (SD 27.7).  Those who received a combination of community-based and residential-based TC services were intermediate between these average values.  The mean MBI on admission for the combination group was 63.0 (SD 21.1) and on discharge was 78.8 (SD 22.7).

### Table 3.3:  Median (IQR) Modified Barthel Index for all Transition Care recipients by type of Transition Care: Community, Residential, and Combination

| State / Territory | n | Modified Barthel Index - On Admission | Modified Barthel Index - On Discharge |
| --- | --- | --- | --- |
| ACT - Community | 24 | 80 (73-84) | 98 (87-98) |
| ACT - Residential | 16 | 72 (64-80) | 86 (71-95) |
| ACT - Combination | 29 | 74 (69-80) | 98 (94-100) |
| NSW - Community | 531 | 80 (66-89) | 94 (85-100) |
| NSW - Residential | 94 | 60 (45-76) | 86 (75-95) |
| NSW - Combination* | 5 | 68 (59-84) | 97 † |
| NT - Residential | 12 | 38 (27-45) | 53 (33-58) |
| QLD - Community | 265 | 83 (74-89) | 97 (88-100) |
| QLD - Residential** | 3 | 89 † | 77 † |
| QLD - Combination*** | 5 | 78 (69-90) | 84 (78-93) |
| SA - Community | 110 | 77 (65-86) | 84 (72-92) |
| SA - Residential | 140 | 56 (34-70) | 80 (60-88) |
| SA - Combination | 39 | 67 (49-83) | 86 (74-90) |
| TAS - Community | 34 | 70 (62-79) | 90 (74-95) |
| TAS - Residential | 58 | 63 (54-75) | 94 (81-98) |
| TAS - Combination | 6 | 57 (42-69) | 89 (69-94) |
| VIC - Community | 205 | 75 (55-85) | 84 (65-93) |
| VIC - Residential | 646 | 48 (26-69) | 56 (30-78) |
| VIC - Combination | 83 | 56 (37-74) | 68 (45-90) |
| WA - Community | 35 | 84 (74-91) | 92 (90-96) |
| WA - Residential | 57 | 59 (34-78) | 76 (52-92) |
| WA - Combination | 46 | 71 (61-82) | 95 (90-97) |

Median (IQR)

* only 5 recipients of Combination TC in NSW

** only 3 recipients of Residential TC in QLD

*** only 5 recipients of Combination TC in QLD

† IQR not calculable as too few observations

## 3.3. Length of stay

The median length of stay in TC differed according to type of TC received.  Those who were on the residential-based program had a shorter length of stay in the program than those who received community-based TC. When those who were discharged to hospital or died on the program were excluded, the length of stay increased by several days for both types of TC.

Table 3.4: Length of stay and adjusted length of stay excluding those discharged to hospital or death for all Transition Care recipients

| State / Territory | n | Length of Stay - Median | Length of Stay - IQR | Adjusted Length of Stay - Median | Adjusted Length of Stay - IQR |
| --- | --- | --- | --- | --- | --- |
| ACT - Community | 24 | 79 | 54.5 – 84 | 81 | 57 – 84 |
| ACT - Residential | 16 | 28.5 | 9.5 – 41 | 32 | 12.5 – 44 |
| ACT - Combination | 29 | 60 | 47 – 84 | 59 | 45.3 – 84 |
| NSW - Community | 531 | 56 | 35 – 72.6 | 58 | 43 – 78 |
| NSW - Residential | 94 | 47 | 28 – 65 | 49 | 29.5 – 66.5 |
| NT - Residential | 12 | 45.5 | 23.6 – 57.5 | 45.5 | 18.3 – 58.3 |
| QLD - Community* | 265 | 57.0 | 41 – 78 | 62 | 45.3 – 79.8 |
| SA - Community | 110 | 50.2 | 29 – 80.2 | 68 | 37 – 82.2 |
| SA - Residential | 140 | 51.5 | 30.6 – 72.6 | 56 | 36.5 – 76.1 |
| SA - Combination | 39 | 66 | 53.5 – 80.7 | 70 | 53.5 – 84.1 |
| TAS - Community | 34 | 78.5 | 41.2 – 84 | 80 | 64 – 85 |
| TAS - Residential | 58 | 53 | 28 – 80 | 59 | 34 – 82 |
| TAS - Combination | 6 | 80.5 | 54 – 85 | 80.5 | 46 – 86.1 |
| VIC - Community | 205 | 70 | 38 – 80 | 74 | 52 – 82 |
| VIC - Residential | 646 | 32 | 16 – 56 | 74.035.0 | 18 – 58 |
| VIC - Combination | 83 | 69 | 45 – 81.1 | 74.13 | 50.5 – 84 |
| WA - Community | 34 | 75.2 | 46 – 84 | 80 | 59.6 – 84.5 |
| WA - Residential | 57 | 52 | 30.2 – 72.2 | 59 | 31.6 – 78.6 |
| WA - Combination | 46 | 83 | 69.2 – 84 | 83 | 68 – 84 |
| National - Community | 1,204 | 58 | 37 – 78.25 | 65 | 46 – 81 |
| National - Residential | 1,026 | 38 | 19 – 62.3 | 41 | 22 – 66 |
| National - Combination | 213 | 71.3 | 48 – 83.1 | 76.6 | 51.3 – 84 |

* 265 of the 273 TC recipients in Queensland received community based services and therefore only results for this group are presented for this state.

## 3.4. Modified Barthel Index Efficiency

MBI efficiencies (i.e. change in function per day of stay) for the 2006/07 financial year were calculated in each jurisdiction according to type of care (Community, Residential or Combination), and this is shown in Figure 3.1. These data were drawn from the TCP COGNOS database maintained by the Department of Health and Ageing.

In terms of MBI efficiency, the overall figures for TC in the community and residential setting were 0.15 (i.e. change of 9.2 units in 61.1 days) and 0.24 (i.e. change of 10.3 units in 42.3 days), respectively.  As Figure 3.1 demonstrates, TC delivered only in a residential setting had greater MBI efficiency for the majority of jurisdictions, with the exception of Victoria.  The combination of community-based and residential-based TC also appears to be more efficient in terms of functional gain per day than TC only in a community setting.

### Figure 3.1: Modified Barthel Index efficiencies by type of Transition Care per jurisdiction

## 3.5. The Transition Care experience

Telephone interviews with 630 TC recipients and 386 carers three months post-discharge from TC (National Evaluation of the Transition Care Program 2007b) showed that overall 93% of recipients (or their proxy) were satisfied or very satisfied with TC.  Furthermore, 93% of carers were satisfied or very satisfied with the TC their relative/friend received.  However, there was an issue concerning the lack of information provided to potential TC recipients so that they knew what to expect from TC.  As noted in the Recipient Snapshot Study Report (National Evaluation of the Transition Care Program 2007b), it is unclear whether this reflected a lack of communication with the recipient or their proxy from the acute hospital service or from the TC services.

The quality of the transition to TC was measured in the Recipient Snapshot Study using the CTM-3; (Coleman, Mahoney et al. 2005).  The CTM-3 includes three major domains that have been deemed as critically important to an individual's experience of a change in care setting, namely how well recipients understood their own responsibilities in managing their health, the purpose for each of their medications, and whether family/carer preferences were taken into account.  The CTM-3 is scored between 0 and 100, with higher scores indicating a better transition.  Scores around 66.67 indicate TC recipients strongly agreed with two of the three domains.  The Recipient Snapshot Study (National Evaluation of the Transition Care Program 2007b) showed the average CTM-3 score at three month follow-up was 68.6 (SD 13.8) and this was similar to the average reported by Coleman et al. (Coleman, Mahoney et al. 2005) in their US-based study of the quality of care transitions.  The greatest difficulty that was reported by recipients was in understanding the purpose of each of their medications, and 32% of the respondents in this study did not know the purpose for taking all of their medications.

The Recipient Snapshot Study also highlighted the differences between jurisdictions, noting a significantly lower average CTM-score among the Victorian TC recipients than in other states or territories.  This appears to correlate with the lower average MBI scores at admission to TC in Victoria than in other parts of Australia.

## 3.6. Hospital readmissions

In terms of hospital readmissions, the Final Report of the Controlled Comparison Study and Costs and Effects Study (National Evaluation of the Transition Care Program 2008) showed that 37% of TC recipients overall were readmitted one or more times during the three months post ACAT approval.  The readmission rate was slightly higher among the recipients of TC only in a community setting (39%) than among either recipients of TC only in a residential setting or those who received a combination of community-based and residential-based TC services (35% in each).  The Models of Transition Care Report (National Evaluation of the Transition Care Program 2007a) reported that overall 22% of TC recipients were discharged from the TCP to hospital in 2006/07.  It is noteworthy that the discharge to hospital rate was somewhat higher in New South Wales and Queensland, which have a large component of community-based TC places (exclusively community in Queensland at the time of writing this report).  A breakdown of discharge reason by jurisdiction and type of care is presented in Table 3.5.

### Table 3.5: Discharge destination by jurisdiction and type of care

| Jurisdiction | Type of Care | Death | Hospital | Nursing Home | Hostel | Other | To the Community - With no support | To the Community - HACC | To the Community - CACP | To the Community - EACH | Move to other TC service | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ACT | Community Only | 0 | 8 | 0 | 1 | 2 | 17 | 9 | 6 | 2 | 0 | 45 |
| ACT | % | 0 | 17.8 | 0 | 2.2 | 4.4 | 37.8 | 20 | 13.3 | 4.4 | 0 |  |
| ACT | Residential Only | 0 | 14 | 1 | 6 | 4 | 17 | 1 | 6 | 0 | 1 | 50 |
| ACT | % | 0 | 28 | 2 | 12 | 8 | 34 | 2 | 12 | 0 | 2 |  |
| ACT | Combination | 0 | 7 | 5 | 3 | 7 | 22 | 9 | 16 | 1 | 0 | 70 |
| ACT | % | 0 | 10 | 7.1 | 4.3 | 10 | 31.4 | 12.9 | 22.9 | 1.4 | 0 |  |
| ACT | Total | 0 | 29 | 6 | 10 | 13 | 56 | 19 | 28 | 3 | 1 | 165 |
| ACT | % | 0 | 17.6 | 3.6 | 6.1 | 7.9 | 33.9 | 11.5 | 17 | 1.8 | 0.6 |  |
| NSW | Community | 14 | 458 | 18 | 26 | 162 | 472 | 487 | 244 | 29 | 6 | 1,916 |
| NSW | % | 0.7 | 23.9 | 0.9 | 1.4 | 8.5 | 24.6 | 25.4 | 12.7 | 1.5 | 0.3 |  |
| NSW | Residential Only | 2 | 74 | 14 | 61 | 25 | 22 | 67 | 25 | 3 | 9 | 302 |
| NSW | % | 0.7 | 24.5 | 4.6 | 20.2 | 8.3 | 7.3 | 22.2 | 8.3 | 1 | 3 |  |
| NSW | Combination | 1 | 8 | 2 | 4 | 3 | 3 | 2 | 4 | 0 | 1 | 28 |
| NSW | % | 3.6 | 28.6 | 7.1 | 14.3 | 10.7 | 10.7 | 7.1 | 14.3 | 0 | 3.6 |  |
| NSW | Total | 17 | 540 | 34 | 91 | 190 | 497 | 556 | 273 | 32 | 16 | 2,246 |
| NSW | % | 0.8 | 24 | 1.5 | 4.1 | 8.5 | 22.1 | 24.8 | 12.2 | 1.4 | 0.7 |  |
| NT | Community | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| NT | % |  |  |  |  |  |  |  |  |  |  |  |
| NT | Residential Only | 1 | 4 | 3 | 5 | 1 | 0 | 7 | 1 | 0 | 0 | 22 |
| NT | % | 4.5 | 18.2 | 13.6 | 22.7 | 4.5 | 0 | 31.8 | 4.5 | 0 | 0 |  |
| NT | Combination | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| NT | % |  |  |  |  |  |  |  |  |  |  |  |
| NT | Total | 1 | 4 | 3 | 5 | 1 | 0 | 7 | 1 | 0 | 0 | 22 |
| NT | % | 4.5 | 18.2 | 13.6 | 22.7 | 4.5 | 0 | 31.8 | 4.5 | 0 | 0 |  |
| QLD | Community Only | 6 | 120 | 4 | 3 | 32 | 94 | 177 | 62 | 2 | 2 | 502 |
| QL | % | 1.2 | 23.9 | 0.8 | 0.6 | 6.4 | 18.7 | 35.3 | 12.4 | 0.4 | 0.4 |  |
| QL | Residential Only | 1 | 7 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 10 |
| QL | % | 10 | 70 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 |  |
| QL | Combination | 0 | 1 | 0 | 0 | 2 | 2 | 4 | 0 | 0 | 0 | 9 |
| QL | % | 0 | 11.1 | 0 | 0 | 22.2 | 22.2 | 44.4 | 0 | 0 | 0 |  |
| QL | Total | 7 | 128 | 4 | 4 | 34 | 97 | 181 | 62 | 2 | 2 | 521 |
| QL | % | 1.3 | 24.6 | 0.8 | 0.8 | 6.5 | 18.6 | 34.7 | 11.9 | 0.4 | 0.4 |  |
| SA | Community Only | 3 | 66 | 6 | 7 | 6 | 58 | 57 | 53 | 5 | 2 | 263 |
| SA | % | 1.1 | 25.1 | 2.3 | 2.7 | 2.3 | 22.1 | 21.7 | 20.2 | 1.9 | 0.8 |  |
| SA | Residential Only | 6 | 69 | 75 | 60 | 24 | 44 | 41 | 25 | 4 | 23 | 371 |
| SA | % | 1.6 | 18.6 | 20.2 | 16.2 | 6.5 | 11.9 | 11.1 | 6.7 | 1.1 | 6.2 |  |
| SA | Combination | 0 | 4 | 0 | 0 | 2 | 19 | 12 | 6 | 0 | 0 | 43 |
| SA | % | 0 | 9.3 | 0 | 0 | 4.7 | 44.2 | 27.9 | 14 | 0 | 0 |  |
| SA | Total | 9 | 139 | 81 | 67 | 32 | 121 | 110 | 84 | 9 | 25 | 677 |
| SA | % | 1.3 | 20.5 | 12 | 9.9 | 4.7 | 17.9 | 16.2 | 12.4 | 1.3 | 3.7 |  |
| TAS | Community Only | 0 | 15 | 0 | 0 | 10 | 8 | 16 | 5 | 3 | 0 | 57 |
| TAS | % | 0 | 26.3 | 0 | 0 | 17.5 | 14 | 28.1 | 8.8 | 5.3 | 0 |  |
| TAS | Residential Only | 2 | 22 | 8 | 3 | 7 | 22 | 37 | 7 | 0 | 2 | 110 |
| TAS | % | 1.8 | 20 | 7.3 | 2.7 | 6.4 | 20 | 33.6 | 6.4 | 0 | 1.8 |  |
| TAS | Combination | 0 | 1 | 1 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 8 |
| TAS | % | 0 | 12.5 | 12.5 | 0 | 37.5 | 0 | 25 | 12.5 | 0 | 0 |  |
| TAS | Total | 2 | 38 | 9 | 3 | 20 | 30 | 55 | 13 | 3 | 2 | 175 |
| TAS | % | 1.1 | 21.7 | 5.1 | 1.7 | 11.4 | 17.1 | 31.4 | 7.4 | 1.7 | 1.1 |  |
| VIC | Community Only | 5 | 133 | 7 | 12 | 59 | 20 | 110 | 26 | 14 | 1 | 387 |
| VIC | % | 1.3 | 34.4 | 1.8 | 3.1 | 15.2 | 5.2 | 28.4 | 6.7 | 3.6 | 0.3 |  |
| VIC | Residential | 85 | 210 | 639 | 159 | 42 | 24 | 26 | 16 | 8 | 7 | 1,216 |
| VIC | % | 7 | 17.3 | 52.5 | 13.1 | 3.5 | 2 | 2.1 | 1.3 | 0.7 | 0.6 |  |
| VIC | Combination | 4 | 29 | 26 | 14 | 4 | 16 | 31 | 10 | 3 | 0 | 137 |
| VIC | % | 2.9 | 21.2 | 19 | 10.2 | 2.9 | 11.7 | 22.6 | 7.3 | 2.2 | 0 |  |
| VIC | Total | 94 | 372 | 672 | 185 | 105 | 60 | 167 | 52 | 25 | 8 | 1,740 |
| VIC | % | 5.4 | 21.4 | 38.6 | 10.6 | 6 | 3.4 | 9.6 | 3 | 1.4 | 0.5 |  |
| WA | Community Only | 2 | 21 | 1 | 0 | 6 | 41 | 18 | 13 | 2 | 0 | 104 |
| WA | % | 1.9 | 20.2 | 1 | 0 | 5.8 | 39.4 | 17.3 | 12.5 | 1.9 | 0 |  |
| WA | Residential Only | 3 | 59 | 68 | 33 | 25 | 9 | 2 | 6 | 2 | 0 | 207 |
| WA | % | 1.4 | 28.5 | 32.9 | 15.9 | 12.1 | 4.3 | 1 | 2.9 | 1 | 0 |  |
| WA | Combination | 0 | 12 | 2 | 18 | 5 | 37 | 40 | 20 | 0 | 0 | 134 |
| WA | % | 0 | 9 | 1.5 | 13.4 | 3.7 | 27.6 | 29.9 | 14.9 | 0 | 0 |  |
| WA | Total | 5 | 92 | 71 | 51 | 36 | 87 | 60 | 39 | 4 | 0 | 445 |
| WA | % | 1.1 | 20.7 | 16 | 11.5 | 8.1 | 19.6 | 13.5 | 8.8 | 0.9 | 0 |  |
| TOTAL | Total | 135 | 1,342 | 880 | 416 | 431 | 948 | 1,155 | 552 | 78 | 54 | 5,991 |
| TOTAL | % | 2.3 | 22.4 | 14.7 | 6.9 | 7.2 | 15.8 | 19.3 | 9.2 | 1.3 | 0.9 |  |

Tables 3.6 and 3.7 summarise hospital readmissions at three and six months post ACAT approval at a jurisdictional and national level for recipients of TC only in a community setting versus those who received TC only in a residential setting.

At three months post ACAT approval, 37% of TC recipients had at least one readmission to hospital, and this was higher among those who received TC only in a community setting (38%) versus those who had TC only in a residential setting (35%).

At six months post ACAT approval, 47% of TC recipients had at least one readmission to hospital, and this readmission rate was higher among those who received TC only in a community setting (51%) versus those who received TC only in a residential setting (43%).  These high levels of readmission reinforce the frailty of the TC recipients.

### Table 3.6: Hospital readmissions, residential aged care admissions, and deaths for Transition Care recipients at three months post ACAT approval

| State Territory | TC Recipient | Hospital Readmissions - n (%) | Hospital Readmissions - LOS (IQR) | Residential Aged Care - n (%) | Residential Aged Care - LOS (IQR) | Dead at Three Months - n (%) |
| --- | --- | --- | --- | --- | --- | --- |
| ACT | Community | 7 (35%) | 13 (3–29) | 0 (0%) | - | 0 (0%) |
|  | Residential | 10 (71%) | 35 (9–53) | 4 (25%) | 9 (2–62) | 4 (25%) |
| NSW | Community | 167 (38%) | 13 (4–26) | 25 (5%) | 29 (14–54) | 26 (5%) |
|  | Residential | 28 (36%) | 12 (1–36) | 22 (23%) | 30 (15–43) | 8 (9%) |
| NT | Residential | 2 (25%) | - | 1 (8%) | - | 0 (0%) |
| QLD | Community | 73 (34%) | 10 (3–22) | 5 (2%) | 37 (6–42) | 7 (3%) |
| SA | Community | 37 (40%) | 9 (5–31) | 6 (6%) | 27 (3–39) | 5 (5%) |
|  | Residential | 39 (36%) | 9 (4–27) | 37 (26%) | 28 (12–36) | 10 (7%) |
| TAS | Community | 21 (62%) | 12 (2–23) | 2 (6%) | - | 1 (3%) |
|  | Residential | 54 (93%) | 52 (31–81) | 5 (9%) | 45 (19–61) | 3 (5%) |
| VIC | Community | 68 (41%) | 9 (3–20) | 8 (4%) | 22 (16–31) | 12 (6%) |
|  | Residential | 123 (26%) | 12 (4–23) | 378 (59%) | 49 (28–66) | 111 (17%) |
| WA | Community | 9 (26%) | 5 (2–40) | 0 (0%) | - | 3 (9%) |
|  | Residential | 25 (44%) | 31 (10–45) | 13 (23%) | 28 (8–47) | 4 (7%) |
| National | Community | 382 (38%) | 12 (4–25) | 46 (4%) | 29 (14–44) | 54 (4%) |
|  | Residential | 283 (35%) | 17 (6–43) | 460 (45%) | 45 (25–63) | 141 (14%) |

#### Table 3.7: Hospital readmissions, residential aged care admissions, and deaths for Transition Care recipients at six months post ACAT approval

| State Territory | TC Recipient | Hospital Readmissions - n (%) | Hospital Readmissions - LOS (IQR) | Residential Aged Care - n (%) | Residential Aged Care - LOS (IQR) | Dead at Three Months - n (%) |
| --- | --- | --- | --- | --- | --- | --- |
| ACT | Community | 12 (60%) | 13 (5–51) | 1 (4%) | - | 2 (8%) |
| ACT | Residential | 10 (71%) | 35 (10–55) | 7 (44%) | 70 (28–91) | 6 (38%) |
| NSW | Community | 217 (50%) | 17 (6–35) | 48 (9%) | 89 (47–120) | 49 (9%) |
| NSW | Residential | 36 (47%) | 16 (4–45) | 36 (38%) | 94 (43–124) | 16 (17%) |
| NT | Residential | 2 (25%) | - | (0%) | - | 1 (8%) |
| QLD | Community | 98 (46%) | 6 (2–22) | 13 (5%) | 77 (43–97) | 15 (6%) |
| SA | Community | 45 (48%) | 9 (5–27) | 7 (6%) | 95 (67–127) | 11 (10%) |
| SA | Residential | 51 (47%) | 9 (3–27) | 65 (46%) | 91 (50–119) | 18 (13%) |
| TAS | Community | 24 (75%) | 15 (2–25) | 3 (9%) | - | 3 (9%) |
| TAS | Residential | 54 (98%) | 58 (35–84) | 11 (19%) | 86 (28–139) | 3 (5%) |
| VIC | Community | 90 (54%) | 14 (3–37) | 14 (7%) | 104 (67–114) | 21 (10%) |
| VIC | Residential | 152 (32%) | 12 (5–33) | 450 (70%) | 125 (83–150) | 155 (24%) |
| WA | Community | 16 (47%) | 10 (1–21) | 1 (3%) | - | 5 (14%) |
| WA | Residential | 33 (60%) | 34 (13–64) | 26 (46%) | 90 (48–115) | 9 (16%) |
| National | Community | 502 (51%) | 13 (3–31) | 87 (7%) | 92 (55–120) | 106 (9%) |
| National | Residential | 340 (43%) | 18 (6–49) | 595 (58%) | 116 (72–145) | 209 (20%) |

## 3.7. Residential aged care admissions

A total of 22% of TC recipients were admitted to residential aged care in the three months post ACAT approval (National Evaluation of the Transition Care Program 2008), and not unexpectedly this was 4% among recipients of TC only in a community setting and 45% among the recipients of TC only in a residential setting. This agrees very closely with the national discharge destination data from the Models of Transition Care Report (National Evaluation of the Transition Care Program 2007a) which showed that overall 14.8% of TC recipients were discharged to high level residential aged care, and 7.0% of TC recipients were discharged to low-level residential aged care.  There was a strong positive correlation observed between the proportion of TC places that were allocated to residential-based TC and the rate of admissions to residential aged care.  The state with the largest residential-based TC component, Victoria, also had the highest rate of discharge to residential aged care (49.4%), whereas Queensland had only 1.6% of TC recipients discharged to residential aged care.

As shown in Table 3.6, at six months post ACAT approval, 28% of TC recipients had been admitted to residential aged care, and this rate was much higher among those who received TC only in a residential setting (58%) than those who received TC only in a community setting (7%).

## 3.8. Survival

The Final Report of the Controlled Comparison Study and Costs and Effects Study (National Evaluation of the Transition Care Program 2008) also demonstrated that 8% of TC recipients died within three months of the ACAT approval for TC, and this was significantly higher among those who received TC only in a residential setting (14%) versus those who received TC only in a community setting (5%) or a combination of service types (4%).  This death rate is markedly higher than the 2.2% of TC recipients who had a discharge reason of 'death' reported in the Models of Transition Care Report (National Evaluation of the Transition Care Program 2007a).  It is possible that a sizeable proportion of TC recipients who were discharged from TC to hospital died during the hospital readmission that directly followed their stay in TC.

By six months post ACAT approval, 14% of TC recipients had died, and this was greater among those who received TC only in a residential setting (20%) than those who received TC only in a community setting (9%; see Table 3.6).  The proportion of deaths by six months post ACAT approval was greater among the recipients aged 85 years or more (16%) than among the recipients aged less than 85 years (11%).  When further broken down by type of TC received, the difference between age group was more striking.  Among those who received TC only in a community setting, the proportion of recipients who had died was 8% among the younger recipients and 10% among the older recipients.  In contrast, among the recipients who received TC only in a residential setting, 18% of those aged less than 85 years were dead at six months and 23% of those aged 85 years or more were dead at six months suggesting that for almost a quarter of those moving to residential-based TC end of life management issues needed to be addressed.

# 4. How did variations between Transition Care services affect outcomes?

## Key points

- Recipients of TC only in a community setting had better physical functioning both at admission to and discharge from TC, they were more likely than recipients of TC only in a residential setting or combination TC recipients to have a hospital readmission, and less likely to have an admission to residential aged care during the 3 and 6 months post ACAT approval.

- Length of stay in TC appeared to have only a weak relationship with changes in physical functioning for all types of TC.

- Analyses that adjusted for the effects of jurisdictional, regional, service and individual level characteristics demonstrated that greater nursing and allied health staffing provisions per person per week reduced the risk of hospital readmissions and residential aged care admissions, respectively, among TC recipients in the six months post ACAT approval.

## 4.1. What affects individual level outcomes?

Service characteristics during the TC episode appeared to have an impact on the outcomes for TC recipients.  The setting of the TC place (community/residential or a combination of both) had a distinct impact on function, as measured by the MBI.  Those recipients who received TC only in a community setting entered with an average MBI of 75.2 units (SD 18.0) and were discharged with an average MBI of 86.0 (SD 17.5). For those who received TC only in a residential setting, the mean MBI on admission to TC was 51.6 units (SD 25.1) and the mean MBI at discharge from TC was 62.3 (SD 27.7).  Those who received a combination of community-based and residential-based TC services were intermediate between these average values.  The mean MBI on admission for the combination group was 63.0 (SD 21.1) and on discharge was 78.8 (SD 22.7).  While there were some difficulties with the recording of discharge destination, there was also a strong positive correlation between the proportion of TC places that were residential-based TC and the rate of admissions to residential aged care.  The percentage of hospital readmissions was also influenced by the type of TC.  Recipients of community-based places were more likely to have a hospital readmission by three months (39% versus 35% for residential or combination places) and by six months (51% versus 43% for residential places).  Admissions to residential aged care were more likely for recipients of residential-based TC places than community-based TC places at both three months (45% versus 4%) and six months (58% versus 7%).

In order to examine the characteristics of each service and their effects on the outcomes for recipients, services were grouped into three clusters based on 14 variables including regional, service, recipient, and staffing characteristics (National Evaluation of the Transition Care Program 2007a).  There appeared to be no significant difference between the clusters for physical functioning, as measured by admission or discharge MBI, the change in the MBI score or MBI efficiency.  Differences were found for discharge destination with the highest proportion of recipients discharged to the community from the predominantly community cluster (P<0.001).  Similarly, the proportion of recipients discharged to hospital was highest from the predominantly community cluster while the proportion discharged to residential aged care was the lowest from the same group.

There were significant yet weak relationships between length of TC stay and the change in physical functioning (MBI) for the recipients of TC only in a community setting (r=0.186), recipients of TC only in a residential setting (r=0.266), and the recipients of combination places (r=0.261).

Those recipients who received TC only in a community setting and were readmitted to hospital during the three months post ACAT approval had a shorter length of stay in TC (45 versus 62 days), had a lower MBI score at admission (72 versus 76 units), had lower MBI score at discharge (80 versus 87 units) and a smaller improvement in their MBI score from admission to discharge (8 versus 11 units) in comparison to those with no hospital readmission.  In contrast, recipients of TC only in a residential setting who were admitted to hospital during the three months post ACAT approval had higher MBI scores on admission (53 versus 49 units) and discharge (67 versus 61 units), with no differences in length of TC stay or the change in MBI from admission to discharge.  For recipients of combination TC places, those who had a hospital readmission during the follow-up period had a shorter length of stay in TC than those who did not go to hospital (59 versus 70 days), but they were not different in terms of physical functioning.

Regardless of the setting of TC (community-based, residential-based or a combination), recipients who were admitted to residential aged care by three and six months post ACAT approval had a significantly shorter length of stay in TC, significantly lower physical functioning (MBI) at admission to and discharge from TC and a significantly smaller increase in physical functioning at discharge from TC (all p <0.05).  Recipients who died had a shorter TC length of stay and lower MBI at admission to and discharge from TC.

The presence of a co-resident carer appeared to have no impact on admissions to residential aged care or readmissions to hospital at either the three or six months post ACAT approval, regardless of the type of TC.  More recipients of TC only in a residential setting with a co-resident carer died in the six month post ACAT approval period than their contemporaries without a carer (17% vs. 12%).

Multiple logistic regression models were fit to assess the effects of jurisdictional, regional, service and individual level characteristics on the incidence of hospital readmissions and residential aged care admissions in the six months post ACAT approval among the 2,443 TC recipients.  The variables that were considered as possible predictors of the two outcomes were drawn from the Regional Characterization, Models of Transition Care, and Data Linkage Components reports from the evaluation (National Evaluation of the Transition Care Program 2007a; National Evaluation of the Transition Care Program 2007c; National Evaluation of the Transition Care Program 2008).  The variables were:

Individual level 
- Age at approval 
- Gender 
- MBI at admission 
- Type of TC (community, residential or combination)

Service level 
- Sub-contractor 
- Location (major city vs. other) 
- Service delivery (team vs. non-team) 
- Service location (hospital vs. non-hospital) 
- Model of TC (predominantly community, residential, mixed) 
- Size of service (<40, >40) 
- Allied health hours per place per week 
- Nursing hours per place per week

Regional level 
- Number of hospital beds per 1,000 older people 
- Number of residential aged care places per 1,000 older people

Jurisdictional level 
- State

The variables drawn from the Models of Transition Care deserve elaboration.

'Sub-contractor' refers to the sub-contracting arrangements that were reported by TC services in the Quality Reports and/or supplied by the Department of Health and Ageing (National Evaluation of the Transition Care Program 2007a).  The location of each TC service was classified as major city, inner regional, outer regional, remote, or very remote and collapsed to major city or other due to the smaller number of services located in non-metropolitan regions.  Team service delivery reflected employed staff making team decisions about the care of each TC recipient or other.  Non-team service delivery reflected TC services which purchased nursing, allied health or personal care services as necessary without team-based decision making.  Service location was based on the physical location of the service and was classified as hospital-based or non-hospital based.  The model of TC was based on the cluster solution presented in the Models of Transition Care Report, in which services clustered according to three main groups, namely predominantly community, residential, and mixed.  The size of the service related to the number of operational places, and this was collapsed to two groups of <20 places and >20 places.  Variables that represented the provision of total allied health hours per operational place per week and total nursing hours per operational place per week, as presented in the Quarterly Reports, were also included in the analyses (National Evaluation of the Transition Care Program 2007a).

Because of notable differences in the residential aged care admissions between Victoria and the other states, the Victorian residential aged care admissions were excluded from the model.  Similarly, the pattern of hospital readmissions appears to differ in Tasmania and elsewhere and therefore the effects of the variables on hospital readmissions were examined without the Tasmanian hospital data.

In terms of hospital readmissions, males, services with subcontracting arrangements, and lower nursing hours per place per week were associated with an increased risk of hospital readmission over the six months post ACAT approval, as described in Table 4.1.

### Table 4.1: Risk of hospital readmission in six months post ACAT approval

| Variable | OR | 95%CI |
| --- | --- | --- |
| Sex |  |  |
| Male (referent) | 1 |  |
| Female | 0.71 | 0.57 – 0.89 |
| Nursing hours per place per week | 0.96 | 0.94 – 0.98 |
| Subcontractor2 |  |  |
| No (referent) | 1 |  |
| Yes | 1.37 | 1.11 – 1.69 |

OR - Odds ratio

As summarized in Table 4.2, residential aged care admissions were affected by a number of different variables.  Increasing age, a lower MBI at admission to TC, and receiving TC only in a residential setting increased the risk of a residential aged care admission.  The TC services that offered residential-based or both residential-based and community-based places were associated with an increased risk of residential aged care admission.  Another service characteristic that affected the risk of residential aged care admission was the provision of allied health hours, such that risk of residential aged care admission decreased by 21% for every additional hour of allied health services per place per week.  The ACAT regions with a greater number of hospital beds per 1,000 older people were associated with a reduced risk of residential aged care admissions.  The risk was also significantly lower in New South Wales and Queensland than in the other jurisdictions, probably reflecting the large community components of the TC programs in these states.

#### Table 4.2: Risk of residential aged care admission in the six months post ACAT approval

| Variable | OR | 95%CI |
| --- | --- | --- |
| Age | 1.05 | 1.02–1.07 |
| MBI on admission2 | 0.99 | 0.98–0.99 |
| Type of TC |  |  |
| Community (referent) | 1 |  |
| Residential | 6.93 | 3.81–12.6 |
| Combination | 1.05 | 0.46–2.41 |
| Model of TC |  |  |
| Predominantly community | 1 |  |
| Residential | 5.58 | 2.11–14.75 |
| Mixture | 6.65 | 2.4–18.39 |
| Total allied hours per place per week | 0.79 | 0.67–0.94 |
| Total hospital beds per 1,000 older people | 0.99 | 0.98–1 |
| State |  |  |
| ACT | 1 |  |
| NSW | 0.15 | 0.04–0.54 |
| QLD | 0.12 | 0.03–0.52 |
| SA | 0.55 | 0.21–1.42 |
| TAS | 0.67 | 0.25–1.83 |
| VIC | - |  |
| WA | 1.76 | 0.7–4.42 |

## 4.2. 	Jurisdictional variations in health and aged care service provision

At a jurisdictional level, estimates of the residential aged care provision ratio, acute beds and rehabilitation/geriatric evaluation and management beds per 1,000 older people are presented in Table 4.3 for the 2005/06 period.  This table highlights the differences between states and territories in terms of the provision of acute and rehabilitation/Geriatric Evaluation and Management (GEM) beds in particular.  The more extensive services for older people in Victoria contrasts with Tasmania and Queensland where there are fewer rehabilitation and GEM beds but more acute beds per 1,000 older people.  It is important to bear in mind that in Table 4.3, the older population in NT was estimated from a composite of the number of Aboriginal or Torres Strait Islander Australians aged at least 50 years, and non-Aboriginal Australians aged 70 years or more.  In other jurisdictions and for the national figure, 70 years was used as the lower limit for older age.

Table 4.3: Distribution of population, aged care places, and hospital beds per 1,000 older people by state/territory for the 2005/06 period

| State Territory | Total population1 | % Population Older | Residential aged care provision ratio | Acute beds / 1,000 older people | Rehabilitation + GEM beds / 1,000 older people2 | Allocated Transition Care places / 1,000 older people |
| --- | --- | --- | --- | --- | --- | --- |
| ACT | 328,817 | 6.7 | 72.1 | 32.8 | 2.6 | 1.58 |
| NSW | 6,827,694 | 9.9 | 82.8 | 24.7 | 2.8 | 1.04 |
| NT | 206,688 | 7.8 | 27 | 41.2 | 0.9 | 0.99 |
| QLD | 4,053,444 | 8.5 | 84.6 | 26.8 | 2.2 | 1.02 |
| SA | 1,554,656 | 11.2 | 90.3 | 25.2 | 2.7 | 1.01 |
| TAS | 488,948 | 10.3 | 86.3 | 26 | 1.7 | 1.13 |
| VIC | 5,091,666 | 9.8 | 85.1 | 24.9 | 4.2 | 1.01 |
| WA | 2,050,884 | 8.3 | 80.9 | 26 | 2.4 | 0.94 |
| Total | 20,602,797 | 9.4 | 84.2 | 25.7 | 3 | 1.03 |

1: Includes estimated resident population in unknown area; NSW=1,170; NT=33,184; SA-4,881; VIC=466.

2: Includes rehabilitation and Geriatric Evaluation and Management beds

So as to aid in the identification of ACAT regions that were relatively well or poorly serviced in terms of aged care places and hospital beds, Figure 4.1 displays a composite of the total number of mainstream and flexible aged care places per 1,000 older people and the total number of hospital beds per 1,000 older people for the 2005/06 period (National Evaluation of the Transition Care Program 2007c).  To create this figure, a score of 1 was assigned to the ACAT regions in the lowest quintile of aged care places per 1,000 older people, a score of 2 assigned to those in the second quintile, and so on through to a score of 5 for those in the top quintile.  A similar scoring regime was used for the number of hospital beds per 1,000 older people.  These two sets of scores were then summed to give a composite indicator of aged care places and estimated hospital beds per 1,000 older people, which ranged between 2 and 10.  Areas which were in the lowest quintile for both aged care places and hospital beds per 1,000 older people scored 2 (represented as green areas on the map) while areas that were in the highest quintile for both indicators scored 10, shown as pink areas on the map in Figure 4.1.

It is important to note that the definition of a rehabilitation episode of care includes psychiatric rehabilitation which appears to have led to some differences in reporting approaches from jurisdictions (Australian Institute of Health and Welfare 2005).

### Figure 4.1: Composite indicator of number of aged care places and number of hospital beds per 1,000 older people for 2005/06 period

# 5.  Comparison of Transition Care recipients with other groups of frail older people

## Key points

- Comparison of outcomes for those who received TC only in a residential setting with outcomes from Victorian GEM units showed GEM units admitted more disabled people and achieved shifts in the MBI more rapidly than residential-based TC.

- Older people in both control groups had a higher risk of hospital readmission in the six months post ACAT approval than the TC recipients.

- Older people in both control groups had a greater hazard (risk) of a residential aged care admission in the six months post ACAT approval than those who received TC only in a community setting.

- Older people who received TC only in a residential setting had a seven fold increase in hazard of residential aged care admission compared with those who received TC only in a community setting.  TC in a residential-based setting alone did not prevent an aged care admission.

## 5.1. External comparison of Transition Care recipients to Australasian Rehabilitation Outcomes Centre and Geriatric Evaluation and Management units

Evidence was drawn from several sources to ascertain how the outcomes for recipients of TC compared to the outcomes for other older people who were approved for other post acute care and aged care programs.

The first external comparison was made with data concerning rehabilitation units, extracted by the Australian Rehabilitation Outcomes Centre (AROC).  Data for persons aged 65 years or more who were admitted for a reason of Debility in the 2006/07 year were analysed.  This admission condition represents older people who were selected to enter rehabilitation units on the basis of their functional ability and their anticipated capacity to make functional gains.  It is reasonable to assume that this group is fitter than those ACAT assessed and approved for TC.

Two points must be borne in mind in interpreting Table 5.1.  Rehabilitation units have higher staffing to patient ratios than TC units and this contributes to the apparently better MBI efficiency.  A second point that must be considered is that the Functional Independence Measure (FIM) and not MBI is reported to the AROC by contributing rehabilitation units.  The FIM averages were converted to MBI by use of the formula:

Estimated MBI = (FIM - 18)/0.67 (Eagar, Gordon et al. 2001).

It is important to note that this conversion is based on a regression equation and the random error associated with the conversion is not taken into account.

The TC Program data were drawn from the Australian Government Department of Health and Ageing COGNOS database for the 2006/07 financial year, to cover the same period as the AROC data. As Table 5.1 demonstrates, those in rehabilitation units make larger gains more quickly than those in TC.  It confirms that in general the TC group were different to the rehabilitation group, as indeed is appropriate given the selection criteria for TC.

### Table 5.1: Estimated Modified Barthel Index efficiencies from the Australasian Rehabilitation Outcomes Centre 2006/07

| Age Group | Admission MBI | Discharge MBI | Change in MBI | LOS | MBI Efficiency |
| --- | --- | --- | --- | --- | --- |
| 65-69 | 52.2 | 71.2 | 19 | 23.3 | 0.82 |
| 70-74 | 53.7 | 76 | 22.3 | 21.2 | 1.05 |
| 75-79 | 53.7 | 76 | 22.3 | 21 | 1.06 |
| 80-84 | 51.6 | 70.6 | 19 | 21.4 | 0.89 |
| 85-89 | 52.7 | 71.8 | 19.1 | 19.8 | 0.97 |
| 90-94 | 48.4 | 68.8 | 20.4 | 20.3 | 1.01 |
| 95+ | 48.4 | 60.1 | 11.7 | 20.9 | 0.56 |
| Overall | 52.1 | 72.1 | 20 | 20.9 | 0.96 |
| TC1 | 66.8 | 76.9 | 10.1 | 54.7 | 0.18 |

1 Cumulative data from COGNOS 2006/07 year

A second external comparison was between the MBI efficiencies of the Victorian GEM units and TC delivered only in a residential setting, to examine the efficiency of the TC model relative to the GEM units.  Data were drawn from the TC Program Management Data Set managed by the Australian Government Department of Health and Ageing (the COGNOS database) for the 2006/07 financial year, to cover the same period as the GEM efficiency data (pers comm. N Doran 2008).

As Table 5.2 demonstrates, the GEM units have greater efficiency in terms of functional gain per day.  It also suggests that the Victorian GEM units are taking more disabled older people than the TC in residential-based programs in some states.  This does raise the possibility that TC delivered in a residential-based setting is being used as a substitute for GEM programs.  The lower efficiencies seen in most TC programs which are likely to be associated with poorer flows through hospitals also raise questions about whether this approach is cost effective.  It is possible that increases in staffing numbers at these sites would increase the efficiencies by reducing the time taken to achieve functional gains.

The efficiencies for the Tasmanian and NSW recipients of TC only in a residential setting appeared closest in efficiency to the Victorian GEM units, while the WA residential model and NT residential model appeared least efficient.  However, the length of time of operation of the TCP in each jurisdiction is not taken into account in this finding, and this may explain the lower efficiencies among jurisdictions with newer services.  The Victorian TC services accepted more disabled older people than other jurisdictions and appear to have focused on avoiding functional decline and optimizing discharge outcomes rather than on returning home.

There are limitations in making these comparisons using administrative data and then drawing conclusions about the quality of services.  It is unclear at what point on the trajectory of recovery the individuals in each group have reached when the comparisons are drawn and they may be at different points.  The time post event is thought to be an important predictor of outcome.  Timing of measurement may be more important than site of care in explaining differences in outcomes.  As we do not have the timing since first presentation we may be measuring outcomes at different times at each site of care.  Nevertheless this is the only evidence currently available.

Table 5.2: Modified Barthel Index efficiency at jurisdictional level for Victorian Geriatric Evaluation and Management units vs. Transition Care delivered only in a residential setting for 2006/07 period

| MBI | MBI Admission | MBI Discharge | MBI Change | LOS | Efficiency |
| --- | --- | --- | --- | --- | --- |
| VIC GEM | 47.3 | 59.3 | 12 | 26.7 | 0.45 |
| ACT residential | 71.3 | 84.5 | 13.2 | 36 | 0.37 |
| NSW residential | 64.5 | 80.2 | 15.7 | 38.9 | 0.4 |
| NT residential | 48.4 | 59.9 | 11.5 | 34.9 | 0.33 |
| SA residential | 55 | 73.9 | 18.9 | 55.2 | 0.34 |
| TAS residential | 66.8 | 88.9 | 22.1 | 51.5 | 0.43 |
| VIC residential | 50.3 | 54.7 | 4.4 | 36.2 | 0.12 |
| WA residential | 54.7 | 65.7 | 11 | 54.5 | 0.2 |

## 5.2. Comparisons based on data linkage

The Controlled Comparison and Costs and Effects Study (National Evaluation of the Transition Care Program 2008) used two other groups of frail older people recently discharged from hospital to assess the impact of the program.  These comparisons suggested that the TCP offered some prevention of readmission and movement into residential aged care.

The two groups that were compared to the TC recipients in the data linkage study (National Evaluation of the Transition Care Program 2008) were drawn from the ACAT assessments of people between 1 October 2006 and 31 March 2007 that took place in the hospital setting (acute care or other inpatient care).  The two groups were:

Control 1: People who were approved for a TC place with their ACAT assessment taking place in hospital but had not been discharged from TC by 30 September 2007 and

Control 2: People who were approved for a CACP only.  Note that this does not distinguish between those who actually received a CACP and those who were approved but did not receive a CACP.

Tables 5.3 and 5.4 summarise hospital readmissions and residential aged care admissions at three and six months post ACAT approval at a jurisdictional and national level for TC recipients versus Control 1 and Control 2. The results from this table are discussed below.

### Table 5.3: Hospital readmissions, residential aged care admissions, and deaths for Transition Care recipients, Control 1 and Control 2 at three months post ACAT approval

| State / Territory | Control | Hospital readmissions - n (%) | Hospital readmissions - LOS (IQR) | Residential aged care - n (%) | Residential aged care - LOS (IQR) | Dead at three months - n (%) |
| --- | --- | --- | --- | --- | --- | --- |
| ACT | TC | 28 (48%) | 15 (4–37) | 5 (7%) | 15 (3–28) | 4 (6%) |
| ACT | Control 1 | 24 (64%) | 11 (5–24) | 3 (7%) | 42 (23–63) | 3 (7%) |
| ACT | Control 2 | 15 (52%) | 12 (7–23) | 5 (13%) | 36 (31–40) | 5 (13%) |
| NSW | TC | 198 (38%) | 12 (4–26) | 48 (8%) | 29 (15–47) | 35 (6%) |
| NSW | Control 1 | 41 (40%) | 14 (3–30) | 14 (11%) | 48 (29 – 77) | 12 (9%) |
| NSW | Control 2 | 306 (42%) | 11 (5–23) | 166 (16%) | 41 (25–64) | 115 (11%) |
| NT | TC | * | * | * | * | (0%) |
| NT | Control 1 | * | * | * | * | (0%) |
| NT | Control 2 | * | * | * | * | (0%) |
| QLD | TC | 80 (36%) | 7 (1–20) | 5 (2%) | 37 (11–41) | 9 (3%) |
| QLD | Control 1 | 7 (35%) | 25 (10–31) | 4 (14%) | 71 (53–87) | 1 (3%) |
| QLD | Control 2 | 74 (42%) | 14 (3–28) | 0 (0%) | - | 26 (9%) |
| SA | TC | 89 (38%) | 7 (1–23) | 44 (15%) | 28 (12–35) | 15 (5%) |
| SA | Control 1 | 44 (54%) | 12 (4–25) | 26 (25%) | 36 (21–53) | 16 (16%) |
| SA | Control 2 | 95 (47%) | 10 (5–17) | 42 (17%) | 41 (25–61) | 25 (10%) |
| TAS | TC | 81 (83%) | 39 (14–65) | 8 (8%) | 51 (39–61) | 4 (4%) |
| TAS | Control 1 | 6 (55%) | 4 (2–5) | 1 (9%) | 89 | 0 (0%) |
| TAS | Control 2 | 15 (60%) | 14 (10–52) | 4 (16%) | 59 (37–77) | 2 (8%) |
| VIC | TC | 210 (30%) | 10 (3–21) | 107 (44%) | 48 (27–66) | 129 (14%) |
| VIC | Control 1 | 113 (36%) | 11 (4–27) | 261 (60%) | 77 (56–85) | 75 (17%) |
| VIC | Control 2 | 107 (47%) | 18 (8–29) | 93 (30%) | 63 (37–77) | 27 (9%) |
| WA | TC | 43 (31%) | 14 (2–38) | 16 (12%) | 32 (12–44) | 7 (5%) |
| WA | Control 1 | 55 (44%) | 8 (4–33) | 29 (23%) | 46 (24–75) | 3 (2%) |
| WA | Control 2 | 113 (51%) | 22 (8–39) | 45 (20%) | 51 (20–69) | 14 (6%) |
| National | TC | 731 (37%) | 13 (4–31) | 534 (22%) | 43 (23–63) | 203 (8%) |
| Nation | Control 1 | 287 (42%) | 11 (4–28) | 339 (39%) | 71 (46–84) | 111 (13%) |
| Nation | Control 2 | 1744 (45%) | 14 (6–28) | 356 (16%) | 45 (26–69) | 215 (10%) |

* Too few individuals to present results without compromising identifiability

#### Table 5.4: Hospital readmissions, residential aged care admissions, and deaths for Transition Care recipients, Control 1 and Control 2 at six months post ACAT approval

| State Territory | Control | Hospital readmissions - n (%) | Hospital readmissions - LOS (IQR) | Residential aged care - n (%) | Residential aged care - LOS (IQR) | Dead at three months - n (%) |
| --- | --- | --- | --- | --- | --- | --- |
| ACT | TC | 34 (59%) | 18 (4–49) | 9 (13%) | 70 (31–105) | 8 (12%) |
| ACT | Control 1 | 24 (73%) | 20 (8–32) | 3 (7%) | - | 3 (7%) |
| ACT | Control 2 | 21 (72%) | 12 (6–42) | 8 (21%) | 121 (30–130) | 7 (18%) |
| NSW | TC | 257 (50%) | 17 (6–35) | 85 (14%) | 92 (42–122) | 66 (11%) |
| NSW | Control 1 | 56 (54%) | 22 (7–35) | 20 (16%) | 120 (58–151) | 16 (13%) |
| NSW | Control 2 | 391 (54%) | 16 (6–31) | 242 (23%) | 103 (54–137) | 184 (18%) |
| NT | TC | * | * | * | * | 1 (8%) |
| NT | Control 1 | * | * | * | * | 1 (11%) |
| NT | Control 2 | * | * | * | * | 1 (6%) |
| QLD | TC | 105 (48%) | 6 (2–23) | 13 (5%) | 77 (43–97) | 17 (6%) |
| QLD | Control 1 | 11 (55%) | 12 (3–26) | 6 (21%) | 145 (60–178) | 3 (10%) |
| QLD | Control 2 | 99 (56%) | 15 (8–42) | 0 (0%) | - | 41 (15%) |
| SA | TC | 111 (47%) | 9 (4–27) | 76 (26%) | 92 (56–120) | 32 (11%) |
| SA | Control 1 | 46 (56%) | 17 (8–31) | 33 (32%) | 117 (64–139) | 24 (23%) |
| SA | Control 2 | 122 (60%) | 13 (5–24) | 58 (24%) | 113 (62–137) | 35 (14%) |
| TAS | TC | 84 (90%) | 41 (17–75) | 15 (15%) | 110 (51–148) | 6 (6%) |
| TAS | Control 1 | 7 (70%) | 4 (1–5) | 1 (9%) | - | 0 (0%) |
| TAS | Control 2 | 20 (83%) | 21 (2–52) | 7 (28%) | 109 (53–163) | 4 (16%) |
| VIC | TC | 268 (38%) | 13 (4–37) | 494 (53%) | 122 (81–148) | 184 (20%) |
| VIC | Control 1 | 126 (40%) | 14 (6–37) | 272 (63%) | 162 (118–176) | 106 (25%) |
| VIC | Control 2 | 132 (58%) | 22 (9–43) | 114 (36%) | 133 (77–167) | 50 (16%) |
| WA | TC | 68 (50%) | 15 (2–35) | 31 (23%) | 93 (55–117) | 16 (12%) |
| WA | Control 1 | 68 (54%) | 9 (3–36) | 45 (36%) | 99 (58–155) | 12 (10%) |
| WA | Control 2 | 139 (65%) | 30 (9–49) | 56 (25%) | 107 (64–154) | 35 (16%) |
| National | TC | 929 (47%) | 14 (4–37) | 723 (30%) | 112 (71–142) | 330 (14%) |
| National | Control 1 | 338 (49%) | 15 (5–34) | 381 (43%) | 149 (88–173) | 165 (19%) |
| National | Control 2 | 925 (58%) | 17 (7–37) | 486 (22%) | 110 (60–151) | 357 (16%) |

* Too few individuals to present results without compromising identifiability

## 5.3. Impact on the hospital system

Nationally the risk of hospital readmission during the three months post ACAT approval was between one third and one half greater for the two control groups compared with the TC recipients (Control 1 IRR 1.3; 95%CI 1.1 - 1.6; Control 2 IRR 1.5; 95%CI 1.3 - 1.8).  There was no difference in the incidence of any hospital readmissions between those who received TC only in a community setting and those who received TC only in a residential setting.  When the hospital readmissions during the six months post ACAT approval were considered, the analyses showed a significant effect of group on hospital readmissions over the six months post ACAT approval, such that there was an increased risk of readmission among the Control 2 group (IRR 1.17; 95%CI 1.11 - 1.24) in comparison to the TC recipients.

A Cox proportional hazards model was fit to examine the hazard of a hospital readmission over the six months post ACAT approval.  The response variable was time to first hospital readmission.  Age, availability of aged care places and total hospital beds per 1,000 older people, jurisdiction, and type of TC or group (TC community, TC residential, TC combination, Control 1, Control 2) were included in the analysis.  The results showed that there were significant effects of all of these variables, as shown in Table 5.5.  Control 1 group had a 17% increased risk of hospital readmission and Control 2 group had a 35% increased risk of hospital readmission relative to those who received TC only in a community setting.

### Table 5.5: Hazard of hospital readmission in six months post ACAT approval

| Variable | HR | 95%CI |
| --- | --- | --- |
| Age | 0.99 | 0.98–1 |
| Type of TC/Group |  |  |
| Community (referent) | 1 |  |
| Residential | 0.98 | 0.84 – 1.14 |
| Combination | 0.95 | 0.75 – 1.21 |
| Control 1 | 1.17 | 1.01 – 1.36 |
| Control 2 | 1.35 | 1.21 – 1.51 |
| Aged care places per 1,000 older people | 1 | 0.99 – 1 |
| Total hospital beds per 1,000 older people | 1 | 1 – 1.01 |
| State |  |  |
| ACT (referent) | 1 |  |
| NSW | 0.67 | 0.53 – 0.86 |
| NT | 0.37 | 0.12 – 1.19 |
| QLD | 0.67 | 0.51 – 0.87 |
| SA | 0.78 | 0.6 – 1.01 |
| TAS | 2.49 | 1.85 – 3.36 |
| VIC | 0.61 | 0.48 – 0.78 |
| WA | 0.77 | 0.6 – 1 |

The median time to hospital readmission among those who were readmitted was 42 days (IQR 15-88) among the recipients of TC only in a community, 23 days (IQR 3-61) among the recipients of TC only in a residential setting, 27 days (IQR 3-76) among the recipients of combination TC, 20 days (IQR 5 - 56) among the Control 1 group and 28 days (8 - 76) among the Control 2 group.  Figure 5.1 presents the cumulative hazard function for the TC recipients and control groups adjusted for the other variables included in the Cox proportional hazards model.

Figure 5.1: Hazard of hospital readmission in six months post ACAT approval

Figure 5.2 presents the proportion of readmissions in each state by type of TC.

Figure 5.2: Proportion of people with one or more hospital readmissions by jurisdiction in the six months post ACAT approval

* No community places in NT; residential data not presented for Queensland as too few cases

The data linkage component of the National Evaluation showed that 23% of the TC recipients elected to be treated as private patients during their index hospitalization.  However, it must be noted that election status for TC recipients in Northern Territory, Tasmania, and Victoria was not available in the evaluation.  For the other jurisdictions, the proportion of TC recipients who elected to be treated as private patients differed slightly according to the type of TC received, with 24% of recipients of TC only in a community setting, 19% of recipients of TC only in a residential setting and 24% of those who received a combination of community-based and residential-based TC services having an election status of private for their index hospitalization.

The median length of stay for the index hospitalization varied considerably between jurisdictions (see Table 5.6). Nationally, the length of stay of the index hospitalization was shorter in the Control 2 group than the other groups, and the length of stay was also longer in the Control 1 group (28 days) than in the other groups.  At a jurisdictional level the variations in length of stay between groups were less clear.  For example, in ACT the median length of stay was similar for the TC recipients and control groups, whereas in SA the Control 2 group had a clearly shorter median length of stay than the TC recipients or the Control 1 group.  The opposite held in Tasmania, although the numbers were small in each group for this state.

#### Table 5.6: Median length of stay of index hospitalization by group

| Jurisdiction | Group | n | LOS Median (IQR) |
| --- | --- | --- | --- |
| ACT | TC - Community | 20 | 14 (7–40) |
| ACT | TC - Residential | 14 | 13 (9–20) |
| ACT | TC - Combination | 24 | 16 (9–24) |
| ACT | Control 1 | 33 | 16 (11–28) |
| ACT | Control 2 | 29 | 15 (9–34) |
| NSW | TC - Community | 435 | 20 (13–34) |
| NSW | TC - Residential | 77 | 19 (13–31) |
| NSW | TC - Combination | 4 | 19 (11–58) |
| NSW | Control 1 | 103 | 25 (14–40) |
| NSW | Control 2 | 727 | 18 (9–32) |
| NT | TC - Residential | 8 | 17 (10–20) |
| NT | Control 2 | 1 | * |
| QLD | TC | 213 | 26 (15–43) |
| QLD | TC - Residential | 3 | * |
| QLD | TC - Combination | 5 | 21 (19–77) |
| QLD | Control 1 | 20 | 40 (27–76) |
| QLD | Control 2 | 176 | 22 (13–45) |
| SA | TC - Community | 93 | 21 (15–35) |
| SA | TC - Residential | 109 | 21 (16–31) |
| SA | TC - Combination | 33 | 25 (17–35) |
| SA | Control 1 | 82 | 25 (17–34) |
| SA | Control 2 | 202 | 16 (9–24) |
| TAS | TC - Community | 32 | 25 (15–36) |
| TAS | TC - Residential | 55 | 11 (6–19) |
| TAS | TC - Combination | 6 | 26 (10–37) |
| v | Control 1 | 10 | 14 (9–20) |
| TAS | Control 2 | 24 | 33 (16–47) |
| VIC | TC - Community | 166 | 27 (17–42) |
| VIC | TC - Residential | 478 | 27 (17–38) |
| VIC | TC - Combination | 61 | 26 (17–40) |
| VIC | Control 1 | 312 | 30 (20–43) |
| VIC | Control 2 | 226 | 20 (12–29) |
| WA | TC - Community | 34 | 31 (21–48) |
| WA | TC - Residential | 55 | 26 (16–52) |
| WA | TC - Combination | 46 | 17 (10–24) |
| WA | Control 1 | 126 | 28 (16–41) |
| WA | Control 2 | 215 | 21 (13--33) |
| National | TC - Community | 993 | 23 (14–38) |
| National | TC - Residential | 799 | 23 (15–36) |
| National | TC - Combination | 179 | 21 (14–35) |
| National | Control 1 | 686 | 28 (17–41) |
| National | Control 2 | 1,600 | 19 (10–32) |

* data not shown as too few cases

In terms of total length of hospital stay during the six months post ACAT approval, there was no difference between the former public versus former private patients, with an average length of stay of 25.6 (SD 43.5) among the public patients and 27.2 (SD 32.5) among those who elected to be treated as private patients at their index hospitalization.

## 5.4. Impact on the aged care system

The risk of using residential aged care during the three months post ACAT approval was shown in the Final Report of the Controlled Comparison and Costs and Costs and Effects Study (National Evaluation of the Transition Care Program 2008) to be greater among the two control groups than among the TC recipients (Control 1 OR 1.9; 95%CI 1.5 - 2.3; Control 2 OR 1.2; 95%CI 1.0 - 1.4).

A separate Cox proportional hazards model was fit for the hazard of a residential aged care admission over the six months post ACAT approval.  Age, availability of aged care places and total hospital beds per 1,000 older people, jurisdiction, and type of TC or group (TC community, TC residential, TC combination, Control 1, Control 2) were included in the initial model.  The results showed there were no effects of the availability of aged care places or hospital beds, but significant effects of increasing age, type of TC or Group, and jurisdiction.  The hazard of a residential aged care admission was greatest among those who received TC only in a residential setting or Control 1 (a seven fold increase in risk) when compared with the recipients of TC only in a community setting.  The hazard ratios from the final model are shown in Table 5.7.  It must be borne in mind that the reference group used is those who received TC only in a community setting but this does not affect the size of the differences.  If Control 1 were used as the reference group instead Figure 5.3 would appear identical to that shown.

Table 5.7: Summary of hazard of residential aged care admission in six months post ACAT approval

| Variable | HR | 95%CI |
| --- | --- | --- |
| Age | 1.02 | 1.01 – 1.03 |
| Community (referent) | 1 |  |
| Residential | 7.36 | 5.84 – 9.28 |
| Combination | 1.99 | 1.37 – 2.91 |
| Control 1 | 6.99 | 5.52 – 8.86 |
| Control 2 | 3.48 | 2.77 – 4.38 |
| ACT (referent) | 1 |  |
| NSW | 1.89 | 1.2 – 2.98 |
| NT | 0.33 | 0.08 – 1.42 |
| QLD | 0.38 | 0.2 – 0.71 |
| SA | 1.95 | 1.22 – 3.11 |
| TAS | 1.09 | 0.6 – 2 |
| VIC | 5.03 | 3.22 – 7.85 |
| WA | 1.93 | 1.2 – 3.09 |

The median time to first admission to residential aged care among those who were admitted was 83 days (IQR 57-119) among those who received TC only in a community setting, 55 days (IQR 31 - 89) among those who received TC only in a residential setting, 69 days (IQR 45-96 days) among those who received a combination of TC services, 17 days (IQR 7-51) among the Control 1 and 59 days (IQR 28-95) among the Control 2 group. The cumulative hazard function is illustrated in Figure 5.3.

Figure 5.3: Hazard of residential aged care admission in six months post ACAT approval

The level at which TC recipients go on to enter residential aged care in the six months post ACAT approval is summarized in Table 5.8.  As this table shows, those who received TC only in a community setting were more likely to enter TC at low-level care according to the Residential Classification Scale (i.e. S5, S6 or S7), although this did not hold in Victoria or New South Wales.  In contrast, those who received TC only in a residential setting generally entered residential aged care at a higher level (i.e. S1, S2, S3, or S4), although New South Wales was an exception to this.

### Table 5.8: Summary of admission level for Transition Care recipients who were admitted to residential aged care in the six months post ACAT approval

| State / Territory | No. S1 | No. S2 | No. S3 | No. S4 | No. S5 | No. S6 | No. S7 | No. Total | % S1 | % S2 | % S3 | % S4 | % HLC1 | % S5 | % S6 | % S7 | % LLC2 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ACT Community | 0 | 0 |  |  | 1 |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 100 |
| ACT Residential | 2 | 4 |  |  | 0 |  | 1 | 7 | 28.6 | 57.1 | 0 | 0 | 85.7 | 0 | 0 | 14.3 | 14.3 |
| ACT Combination | 0 | 0 |  |  | 1 |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 100 |
| ACT Total | 2 | 4 |  |  | 2 |  | 1 | 9 | 22.2 | 44.4 | 0 | 0 | 66.7 | 22.2 | 0 | 11.1 | 33.3 |
| NSW Community | 9 | 18 | 9 | 2 | 5 | 4 | 1 | 48 | 18.8 | 37.5 | 18.8 | 4.2 | 79.2 | 10.4 | 8.3 | 2.1 | 20.8 |
| NSW Residential | 0 | 10 | 2 | 2 | 13 | 7 | 2 | 36 | 0 | 27.8 | 5.6 | 5.6 | 38.9 | 36.1 | 19.4 | 5.6 | 61.1 |
| NSW Combination | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 |
| NSW Total | 10 | 28 | 11 | 4 | 18 | 11 | 3 | 85 | 11.8 | 32.9 | 12.9 | 4.7 | 62.4 | 21.2 | 12.9 | 3.5 | 37.6 |
| QLD Community | 2 | 3 | 3 |  | 1 | 4 |  | 13 | 15.4 | 23.1 | 23.1 | 0 | 61.5 | 7.7 | 30.8 | 0 | 38.5 |
| QLD Total | 2 | 3 | 3 |  | 1 | 4 |  | 13 | 15.4 | 23.1 | 23.1 | 0 | 61.5 | 7.7 | 30.8 | 0 | 38.5 |
| SA Community | 1 | 2 | 1 | 0 | 2 | 1 | 0 | 7 | 14.3 | 28.6 | 14.3 | 0 | 57.1 | 28.6 | 14.3 | 0 | 42.9 |
| SA Residential | 19 | 16 | 9 | 6 | 12 | 2 | 1 | 65 | 29.2 | 24.6 | 13.8 | 9.2 | 76.9 | 18.5 | 3.1 | 1.5 | 23.1 |
| SA Combination | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 4 | 25 | 25 | 0 | 0 | 50 | 25 | 0 | 25 | 50 |
| SA Total | 21 | 19 | 10 | 6 | 15 | 3 | 2 | 76 | 27.6 | 25 | 13.2 | 7.9 | 73.7 | 19.7 | 3.9 | 2.6 | 26.3 |
| TAS Community | 1 | 0 | 0 |  |  | 2 | 0 | 3 | 33.3 | 0 | 0 | 0 | 33.3 | 0 | 66.7 | 0 | 66.7 |
| TAS Residential | 1 | 7 | 2 |  |  | 0 | 1 | 11 | 9.1 | 63.6 | 18.2 | 0 | 90.9 | 0 | 0 | 9.1 | 9.1 |
| TAS Combination | 0 | 1 | 0 |  |  | 0 | 0 | 1 | 0 | 100 | 0 | 0 | 100 | 0 | 0 | 0 | 0 |
| TAS Total | 2 | 8 | 2 |  |  | 2 | 1 | 15 | 13.3 | 53.3 | 13.3 | 0 | 80 | 0 | 13.3 | 6.7 | 20 |
| VIC Community | 4 | 4 | 2 | 0 | 4 | 0 | 0 | 14 | 28.6 | 28.6 | 14.3 | 0 | 71.4 | 28.6 | 0 | 0 | 28.6 |
| VIC Residential | 164 | 139 | 54 | 10 | 45 | 21 | 17 | 450 | 36.4 | 30.9 | 12 | 2.2 | 81.6 | 10 | 4.7 | 3.8 | 18.4 |
| VIC Combination | 10 | 11 | 1 | 1 | 4 | 2 | 1 | 30 | 33.3 | 36.7 | 3.3 | 3.3 | 76.7 | 13.3 | 6.7 | 3.3 | 23.3 |
| VIC Total | 178 | 154 | 57 | 11 | 53 | 23 | 18 | 494 | 36 | 31.2 | 11.5 | 2.2 | 81 | 10.7 | 4.7 | 3.6 | 19 |
| WA Community | 0 | 0 | 0 |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 100 |
| WA Residential | 10 | 5 | 5 |  | 3 | 3 | 0 | 26 | 38.5 | 19.2 | 19.2 | 0 | 76.9 | 11.5 | 11.5 | 0 | 23.1 |
| WA Combination | 0 | 0 | 0 |  | 1 | 2 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 25 | 50 | 25 | 100 |
| WA Total | 10 | 5 | 5 |  | 5 | 5 | 1 | 31 | 32.3 | 16.1 | 16.1 | 0 | 64.5 | 16.1 | 16.1 | 3.2 | 35.5 |
| Overall Community | 17 | 27 | 15 | 2 | 14 | 11 | 1 | 87 | 19.5 | 31 | 17.2 | 2.3 | 70.1 | 16.1 | 12.6 | 1.1 | 29.9 |
| Overall Residential | 196 | 181 | 72 | 18 | 73 | 33 | 22 | 595 | 32.9 | 30.4 | 12.1 | 3 | 78.5 | 12.3 | 5.5 | 3.7 | 21.5 |
| Overall Combination | 12 | 13 | 1 | 1 | 7 | 4 | 3 | 41 | 29.3 | 31.7 | 2.4 | 2.4 | 65.9 | 17.1 | 9.8 | 7.3 | 34.1 |
| Overall Total | 225 | 221 | 88 | 21 | 94 | 48 | 26 | 723 | 31.1 | 30.6 | 12.2 | 2.9 | 76.8 | 13 | 6.6 | 3.6 | 23.2 |

1: Entered High Level Care; 2: Entered Low Level Care

As demonstrated in the Models of Transition Care Report (National Evaluation of the Transition Care Program 2007a), 22% of the TC recipients overall were discharged to low level or high level care.  The discharge to residential aged care was highest in Victoria (49%), with South Australia (22%) and Western Australia (27%) also having relatively high discharge to residential aged care, in keeping with the proportion of places that operated only in a residential setting in these states.  The TCP administrative data also demonstrated that overall 16% of the TC recipients were discharged to the community with no support, while 19% were discharged with HACC services, 9% with CACP services, and 1% with an Extended Aged Care at Home (EACH) package.

The telephone interview component of the National Evaluation (National Evaluation of the Transition Care Program 2007b) showed that 47% of the interviewed sample accessed community services prior to receiving TC. Of those who were living in the community at the time of the follow-up interview, 55% were accessing community services at follow-up.  Assistance with meals and personal care were the most commonly accessed community services.  Recipients also had great difficulty in distinguishing the source of the services they received, and mixtures of providers such as local councils, HACC services, and services accessed through Department of Veteran's Affairs were all reported.

## 5.5. Impact on Aged Care Assessment Processes

As noted in the Models of Transition Care Report (National Evaluation of the Transition Care Program 2007a), there were 6,716 persons admitted to TC in the 2006/07 year.  The location of the ACAT assessment was classified as 'Acute care setting' in 63% of assessments, 'Other hospital inpatient setting' for 30% of assessments, 'Residential aged care service' for 0.7% of assessments, 'Other location' for 6% of assessments or 'Unknown' for 0.7% of assessments.  Thus while the TCP guidelines stipulate that people assessed for TC must have the assessment in a hospital or other acute care setting, assessments are occurring outside of this environment.

Based on the data linkage component of the evaluation, the median length of time to enter TC following ACAT approval was 4 days (IQR 1-8 days), as shown in Table 5.9.  NSW and the ACT appeared to have the fastest entry to TC, while recipients of TC in SA and WA faced the longest wait from approval to entry to TC.  This may be partly explained by the occupancy rates at a jurisdictional level.  As shown in Figure 5.4, the occupancy over the 2006/07 year varied considerably between jurisdictions, and ranged from minima of 46% in Queensland and 51% in Tasmania to a high of 84% in South Australia.  However, the ACT and New South Wales had fairly high occupancy rates, at 75% and 71% respectively.  Thus the length of time to enter TC following ACAT approval was affected by other factors aside from occupancy rates in TC services.

### Table 5.9: Days from Aged Care Assessment Team approval to hospital separation and Transition Care admission

Days from ACAT Approval to:

| State / Territory | Hospital Separation - median | Hospital Separation - IQR | Transition Care Admission: median | Transition Care Admission: IQR |
| --- | --- | --- | --- | --- |
| ACT Community | 1 | (0 – 6.0) | 3.5 | (2.0 – 9.0) |
| ACT Residential | 1 | (0 – 5.0) | 2 | (1.0 – 5.0) |
| ACT Combination | 3 | (1.0 – 8.0) | 3.5 | (2.0 – 9.5) |
| NSW Community | 2.5 | (1.0 – 5.0) | 3 | (1.0 – 7.0) |
| NSW Residential | 1 | (0 – 2.0) | 1 | (0 – 3.0) |
| NSW Combination | 0.5 | (0 – 3.5) | 2 | (1.0 – 4.0) |
| NT Residential | 2 | (1.5 – 3.5) | - | - |
| QLD Community | 3.5 | (1.5 – 6.0) | 4.5 | (2.0 – 7.0) |
| SA Community | 7 | (5.0 – 10.0) | 7 | (5.0 – 12.0) |
| SA Residential | 7 | (3.0 – 11.0) | 7 | (4.0 – 12.0) |
| SA Combination | 5 | (2.0 – 8.0) | 5 | (2.0 – 9.0) |
| TAS Community | 5 | (3.0 – 6.0) | 6 | (4.0 – 8.0) |
| TAS Residential | 1 | (0.5 – 3.0) | 1 | (1.0 – 3.0) |
| TAS Combination | 2 | (1.0 – 3.0) | 1.5 | (0 – 2.0) |
| VIC Community | 4 | (1.0 – 7.0) | 4 | (1.0 – 10.0) |
| VIC Residential | 4 | (1.0 – 8.0) | 4 | (1.0 – 8.0) |
| VIC Combination | 3 | (1.0 – 7.0) | 4 | (1.0 – 9.0) |
| WA Community | 6 | (4.0 – 13.0) | 6 | (3.5 – 12.5) |
| WA Residential | 6 | (2.5 – 14.5) | 7 | (3.0 – 19.0) |
| WA Combination | 2 | (1.0 – 5.0) | 3 | (1.0 – 5.0) |
| National Community | 4 | (1.0 – 6.0) | 4 | (2.0 – 8.0) |
| National Residential | 3 | (1.0 – 7.0) | 4 | (1.0 – 8.0) |
| National Combination | 3 | (1.0 – 6.0) | 4 | (1.0 – 7.0) |
| National Overall | 3 | (1.0 – 7.0) | 4 | (1.0 – 8.0) |

#### Figure 5.4: Occupancy by jurisdiction, 2006/07

# 6. What are the estimated costs of achieving the outcomes?

## Key points

- At six month post ACAT approval, a recipient of TC only in a community setting had survived an additional 28.9 days without being admitted into hospital or residential aged care when compared with those in the Control 2 group and the additional cost to achieve this for an individual TC recipient had reduced to $344 per day.

- For every day a recipient of TC survives without institutional care i.e. without hospital or residential aged care over a six month period it costs $344 per day.

Several of the reports in the evaluation of the TCP have considered different aspects of the costs of the program, including costs from an individual perspective (Recipient Snapshot Study (National Evaluation of the Transition Care Program 2007b)), jurisdictional perspective (Models of Transition Care Report (National Evaluation of the Transition Care Program 2007a)) and the Cost and Effects Study (National Evaluation of the Transition Care Program 2008).  Further evidence concerning costs and effects of the TCP relative to Control 2 are also presented in this section.

Information concerning the costs incurred by recipients of TC was collected in the telephone interviews with recipients (National Evaluation of the Transition Care Program 2007b).  Recipients were asked about the daily charge for receiving TC that was levied by the TC service and any out of pocket costs they had incurred in relation to equipment or home modifications as a result of receiving TC.  Of the interviewed recipients who received TC only in a community setting, 39% reported that their co-payment fees were waived.  Among those who made a co-payment, the weekly average was $35.36 (SD $11.48), less than the capped amount of $45.95 that prevailed at the time of the interviews.  A total of 32% of the recipients of TC only in a residential setting reported their co-payment fees were waived, and the reported average weekly fee was $178.97 (SD 91.51) among those who made a co-payment, again less than the capped fee of $223.17.  Close to one half of respondents reported additional costs were incurred as a direct result of receiving TC, and the median expenditure was $200.  The reported costs were predominantly for equipment and home modifications.

Economic modelling in health technology assessment considers costs relative to effects of alternative strategies in a defined population.  From a government perspective, costs need to encompass program delivery, hospital costs, and residential aged care costs.  Analyses at three months post ACAT approval have been reported previously and are summarized here.  Additional analyses that examine the cost effectiveness of TC at six months post ACAT approval are also reported here.

A national analysis that concentrated on the cost effectiveness of TC for recipients of TC only in a community setting compared to Control 2 was undertaken at three months post ACAT approval as part of the Costs and Effects Study (National Evaluation of the Transition Care Program 2008).  This analysis demonstrated that recipients of TC only in a community setting had an average of 11.8 days more of survival without institutional care (SWIC) - that is, residential or hospital care - in comparison to the Control 2 group.  Total costs for the TC recipients over the three months post ACAT approval were estimated to be $10,461 greater than those for the Control 2 group.  Thus the incremental cost per day of SWIC for the TC recipients was estimated $10,461/11.8 = $888 per day, with an estimated 95% CI of $737 - $1,135.  This is illustrated in Figure 6.1.

### Figure 6.1: Joint distribution of incremental cost and effects for recipients of Transition Care only in a community setting vs. Control 2 at three months post ACAT approval

It is important to note that the incremental costs varied considerably between jurisdictions, and ranged from $557 per day in Victoria to $1,140 per day in New South Wales (National Evaluation of the Transition Care Program 2008).  This suggests that the different ways of implementing TC have very different costs.

At six months from the time of ACAT approval, the cost effectiveness of TC delivered only in a community setting versus Control 2 was analysed.  This showed that recipients of TC only in a community setting were estimated to have an additional 28.9 days of SWIC in comparison with Control 2 (156.4 vs. 127.4 days).

The average costs for the recipients of TC only in a community setting were estimated to be $9,942 greater per recipient than those for people in the Control 2 group over the six months post ACAT approval.  This was attributable to $12,094 greater direct payments ($12,949 vs. $855), less $1,226 for reduced hospitalization ($6,523 vs. $7,749) and $926 for reduced residential aged care use ($511 vs. $1,437).  Table 6.1 summarises these results.

#### Table 6.1: Summary of national incremental costs and effects at six months post ACAT approval in recipients of Transition Care only in a community setting vs. Control 2

| Item | Community TC | Control 2 | Difference |
| --- | --- | --- | --- |
| Direct costs | $12,949 | $855 | $12,094 |
| Hospital costs | $6,523 | $7,749 | -$1,226 |
| Residential aged care costs | $511 | $1,437 | -$926 |
| Total costs | $19,983 | $10,041 | $9,942 |
| Days of survival without institutional care | 156.4 | 127.4 | 28.9 |

Comparing national unadjusted effects and costs data for recipients of TC only in a community setting versus Control 2 at six months, an incremental cost per day of SWIC (hospital or residential) is estimated at $344 (i.e. $9,942/28.9).  Uncertainty around this point estimate is shown in Figure 6.2, which demonstrates the 95%CI around this estimate to be $279 - $420.

#### Figure 6.2: Joint distribution of incremental cost and effects for recipients of Transition Care only in a community setting vs. Control 2 at six months post ACAT approval

Given the joint distribution displayed in Figure 6.2, the probability that receiving TC only in a community setting is cost effective relative to Control 2 with six months post ACAT approval is shown in the cost effectiveness acceptability curve (Figure 6.3).  This figure informs decision makers of the probability that TC is cost effective relative to Control 2 for plausible decision maker threshold values for an additional day of SWIC.

Figure 6.3: National cost effectiveness acceptability curve for recipients of Transition Care only in a community setting vs. Control 2 at six months post ACAT approval

Figure 6.3 indicates that based on six month follow-up data from the time of ACAT approval there is a 50% probability that receiving TC only in a community setting is cost effective relative to Control 2 at a value of $344 per day of additional SWIC, given evidence of the distribution of costs and effects in Figure 6.2.  At $279 the probability is 2.5%, rising to 97.5% at $420 per day SWIC.

Figure 6.4 shows the expected incremental net benefit over six months post ACAT approval of receiving TC only in a community setting relative to Control 2, dependant on threshold values for effects (additional days of SWIC).

#### Figure 6.4: National net benefit curve for recipients of Transition Care only in a community setting vs. Control 2 at six months post ACAT approval

Figure 6.4 demonstrates that restricted to evidence from six months of follow-up, the expected value of receiving TC only in a community setting is equivalent to that of Control 2 at a value of $344 per additional day of SWIC. For values above this threshold, TC delivered only in a community setting has a higher expected value, while for values below $344 Control 2 have higher expected value.  More generally, the difference in expected value at any given decision threshold value can be measured on the horizontal axis in monetary terms.

It is important to note that the analyses presented here are restricted to six months of follow-up data post ACAT approval.  The direct costs of investing in TC are borne in the first three months post ACAT approval. However, benefits in terms of health outcomes and associated cost offsets from reduced residential aged care may continue beyond six months.  Therefore an analysis of the costs and effects of TC relative to other comparison groups over 12 months (to remove any seasonal effects) may provide further insight into the medium term effects of the TCP.

Finally, a point to bear in mind is that the economic analyses have used days of survival without institutional care as the effect.  Other important outcomes, such as the cost to achieve a one unit improvement in function (MBI) or quality of life, were not possible to examine as the data were not available.

# 7. What did the Transition Care services say about quality in Transition Care?

## Key points

- There was collaborative learning at state and regional levels and local service development.

- Formalizing agreements between hospitals and community aged care providers is emerging as best practice in TC.

- There is a clear workforce issue with all staff needing training in a restorative/rehabilitative model.

- Engaging General Practice in care planning and review remains challenging, and very few teams have succeeded in establishing a working relationship with medical specialists with expertise in elderly care (geriatricians, rehabilitation physicians, and psychogeriatricians).

- The role of community pharmacists in medication review requires clarification.

We found evidence from the 23 Quality Reports that service delivery was goal oriented, time limited and incorporated low intensity therapies aimed at maximising client independence.  Individualized care planning inclusive of the client, family members and other stakeholders involved in the client's longer term care was evidenced.  It was apparent that the requirements of TC, which centre on teamwork, case management, a restorative model of care, and efficient management of allocated TC places, require considerable adjustment for staff trained in clinical and residential aged care models.

Less well evidenced were GP, medical and pharmacist involvement in care planning and review, although this varied across services and regions.  Case managers were identified as having a key role in facilitating GP involvement in care planning and review.  The barriers to GP involvement in care planning and case conferencing are well documented (Shortus, Coulson et al. 2005; Preen, Bailey et al. 2006), although Commonwealth initiatives to enhance GP involvement in residential aged care have had some success (Gadzhanova and Reed 2007).  Home Medication Management Reviews (Rigby 2006; Pit, Byles et al. 2007) were not noted in the Quality Reports assessed as part of this study.  Very few services were systematically involving a medical specialist in elderly care such as a geriatrician or rehabilitation physician in TC.

It was reported that personal care staff were less familiar with the restorative/rehabilitation focus of TC and additional training opportunities were sought.  Timely transfer of information from the acute/sub-acute setting was not always achieved.  Similarly, waiting lists for HACC, CACP and EACH packages sometimes resulted in less than optimal care at the conclusion of the TC episode.

We examined the first batch of quality reports submitted to state/territory Approved Providers and the Australian Government Department of Health & Ageing.  The reports were completed on average nine months after commencement of the service and, with the exception of the pilot sites for the Innovation Care Rehabilitation Services (ICRS) program (Department of Health and Ageing 2005), reflect the early development of service teams and partnership or brokerage models of service delivery.

The TCP objectives, strategies, and service characteristics provide the conceptual framework for a set of key requirements against which services are required to self-assess in their first year of operation.  Self-assessment is part of a broader approach to quality improvement and monitoring, which also involves the selection of TC services, a Plan-Do-Study-Act cycle of continuous quality improvement, and an external complaints mechanism.  The Transition Care Quality Improvement and Monitoring Framework (Australian Government Department of Health and Ageing 2005) proposes external assessment and stakeholder feedback as additional checks of compliance with the requirements, although strategies to implement review team visits have yet to be agreed.

The key requirements focus on those aspects of care specific to the TCP.  TC services are provided by health and aged care organizations and subject to various accreditation and external regulatory processes. Although most Quality Reports have two or more signatories and are reviewed by state/territory Approved Providers before submission to the Department of Health and Ageing, there is currently no mechanism for direct external peer assessment.

The key requirements specify the expectations of TC services but do not prescribe how the requirements are to be met. This approach allows for flexibility, innovation and the tailoring of strategies to meet local needs.  On the flipside, this lack of prescription contributes to ambiguity in the interpretation of the key requirements, as do subtle differences in the wording of the requirements and relevant sections of the TCP guidelines.  Some of the key requirements comprised numerous criteria which presented an additional challenge.  Few services responded to the criteria in a systematic way and this detracted from the confidence with which performance against a specific criterion could be reported.

It is anticipated that additional sources of information such as site visits and discussions with stakeholders are required to expand on the evidence cited in the Quality Reports, particularly those areas where compliance is currently not well evidenced.  Site visits, or an alternative mechanism for external peer assessment would also benefit the program more broadly.

Some services had been pilot sites for the ICRS program implemented in 2001/02 (Department of Health and Ageing 2005).  This experience was reflected in the maturity of service delivery processes and partnerships apparent in responses to the Quality Report.

Quality in the TCP is inextricably concerned with care processes to support transfer between locations (hospital to home or alternative care environment); between sectors (acute, primary, community, residential); and between individual states (illness, frailty or disability to optimal independence and quality of life) (Godfrey, Keen et al. 2005).  Responses to the Quality Report highlight emerging best practice in TC with respect to service agreements with referring hospitals that include protocols for the transfer of client information and agreed processes concerning referral and response times.  The analysis of the Quality Reports also noted difficulties in providing for clients' ongoing needs once TC has finished and suggestions of less than optimal ongoing care arrangements in some instances.

In summary, the Quality Reports demonstrated there was collaborative learning at state and regional levels and local service development.  Formal agreements such as Memorandums of Understanding with hospitals and community aged care providers are emerging as best practice in TC.  All staff require training in a restorative/rehabilitative model.  Engaging General Practice in care planning and review remains challenging, while the role of community pharmacists in medication review requires clarification.  Finally, very few teams have succeeded in establishing a working relationship with medical specialists with expertise in elderly care such as geriatricians, psychogeriatricians, or rehabilitation physicians.

# 8. Issues from each jurisdiction

Each jurisdiction was invited by the evaluators to contribute to this section concerning implementation and issues around TC in each state and territory.  The following subsections are the submissions that were provided by the TCWG in response to that invitation.

## 8.1. Australian Capital Territory

In December 2005, the ACT operationalized ten TC places.  Following the end of the Intermittent Care Service Pilot on 1 July 2006, an additional 25 TC places were allocated and operationalized.  The ACT currently has 15 residential and 20 community TC places and operates as the ACT Transitional Therapy and Care Program.

Since the start of the ACT Transitional Therapy and Care Program a new purpose built sub and non-acute facility was officially opened in February 2007, improving the capacity in the ACT to meet the needs of older people across the acute-aged care continuum.  The new facility added 28 new sub and non-acute beds to the existing 12 geriatric evaluation management beds at the Calvary Hospital.

## 8.2. New South Wales

To date, NSW has 31 Transitional Aged Care Services serving a population of people aged 70 years and over numbering approximately 676,000.  The majority of services offer community-based places and NSW is seeking to expand its facility-based component over the next four years.

Given the increasing demands placed on ACATs following the introduction of this new service, it is pleasing to see that in 2006/07 NSW had a median length of time to enter TC following ACAT approval of three days and is reported as sharing with the ACT the "fastest entry to TC".

NSW supports the researchers' recommendations around the need for more work on quality indicators for this type of service, on a detailed economic analysis of the different configurations and delivery approaches, and on more investigation of the benefits and outcomes of experiencing facility-based or community-based services or a combination of the two.

## 8.3. Northern Territory

The small number of clients assisted through the TCP in the Northern Territory makes it difficult to draw conclusions from the data.  Based on the evidence in this report, future expansion of TC in the NT should concentrate on establishing community based responses.

## 8.4. Queensland

Queensland Health received 351 places under the TCP from 2005 to 2007.  These places were approved in three tranches - 106 places in 2004/05, 167 places in 2005/06, and 78 places in 2006/07.  Queensland's Implementation Plan advised that these 351 places would be operationalized across both residential and

community settings depending upon the availability of unused and unfunded beds in residential aged care facilities.

In recognition that there would be inherent difficulties in implementing TC in residential aged care facilities, Queensland Health established higher subsidy rates for residential placements over community placements.

Despite this very significant higher subsidy rate, there were barriers to implementing TC in residential aged care facilities.  These barriers included a lack of spare bed capacity in residential aged care facilities to take on TC and difficulties in recruiting the additional workforce required in residential aged care facilities to provide restorative care.  As a result approximately only 25% of the places were operationalized in residential settings.

All 351 TC places will have been operationalized by 30 June 2008.

Rather than fund the TC places on an occupied bed basis as per the Australian Government arrangements, Queensland Health fully funded its participating Health Service Districts on an annual basis at the beginning of each financial year.  The effect of this arrangement has been that Health Service Districts were able to employ a number of allied health staff on an ongoing basis to support the roll-out of TC through State funding. The funding available from unoccupied places was able to be used for infrastructure support.

Overall the TCP has been successful in Queensland and has delivered improvements in terms of hospital readmissions, delayed transfer of older people to residential care and functional gain.

## 8.5. South Australia

South Australia has placed a strong focus on re-organising our acute systems towards effective processes for timely assessment and screening of potential TCP clients.  We have a strong emphasis on early focussed intensive service delivery.

South Australia has less clients participating in the program with cognitive impairment due to the need to develop clearer care pathways for this group.  Models of care are being developed that will result in easy to access pathways of care for people with cognitive impairment and stronger integration of pre-acute, sub acute and primary care based services.

The longer median waiting time from ACAT approval to TC admission in South Australia is a factor of availability of residential care places.  It is also a result of the need for improvements in patient flow across the acute- aged care interface, which is being addressed by work associated with developing improved models of care.

## 8.6. Tasmania

Tasmania has two TC services, located in the south and north of the state, which became operational in July and December 2006, respectively.  As at 1st October 2007, all 57 places allocated to Tasmania were operational.

Transition Care South 
The TCP South is coordinated from the Royal Hobart Hospital operating 47 flexible care packages.  The program followed on from the previous Intermittent Care Service Pilot.  The program offers flexible packages in both the residential and community setting delivered through a mix of service provision sourced from private providers and the Tasmanian Department of Health and Human Services.

Residential Packages 
TCP South currently provides a total of 27 residential TC packages.  Twenty-four residential packages are provided at the department's Karingal facility located approximately 15 kms from the Royal Hobart Hospital (RHH) campus.  A comprehensive tender process was undertaken for a TC service to provide nursing, personal care, and hotel services in accordance with the TCP Guidelines.  The successful tenderer was awarded the contract for a period of three years to manage the facility and provide residential TC services to recipients.  The Department has responsibility for the maintenance and upkeep of the facility, all equipment requirements, together with the provision of all Allied Health services,  Geriatrician support to the facility is provided through weekly clinics.  The medical needs of the recipients are managed under the direction of a General Practitioner.  The remaining three residential packages are provided from the Repatriation Centre, located approximately 2 kms from the RHH campus.  An area of this building has recently been converted into two non-acute wards, providing both TC and geriatric evaluation services.  These packages are staffed by departmental staff from all health disciplines.

Community Packages 
The RHH currently operates 20 community packages.  A tender process was undertaken for a TC service to undertake the provision of this service in accord with the TCP Guidelines.  The successful tenderer was awarded the contract for a period of three years.  All referrals for community TCP come from the RHH Rehabilitation and Aged Liaison Team (RASL).  A case manager is appointed by the TC service at the commencement of the program.  The TC service is responsible for all discharge planning and referrals for additional support on completion of TCP.

Transition Care North 
Currently the Launceston General Hospital operates 10 Transition Care packages which are all community based. The catchment of the service is at the current time within a 20 minute radius of Launceston CBD.  At the current time all clients for the program are referred from the Launceston General Hospital.  Clients are assessed by the hospital Aged Care Assessment Team (ACAT) according to the Commonwealth guidelines.

The program is staffed by Launceston General Hospital which comprises, nursing, allied health and support staff. Brokerage of services for support is coordinated by the TCP team on the basis of client need and may include personal care, meal preparation, transport, nursing assessment, physiotherapy and occupational therapy assessment, planning and intervention.  The Service is staffed from 7.30 am to 8 pm with all clients provided with out of hours support through the Launceston General Hospital.

All clients are case managed by a registered nurse, physiotherapist, occupational therapist, or social worker.  Client meetings are conducted weekly to discuss progress and modify care provision as required  On discharge from the program referrals to appropriate services are made or reconnection with previous services are arranged.

The client's General Practitioner (GP) is informed on acceptance and discharge to the program and as required during the duration of the program.  General information sessions are also provided to GP practices as required.

Key Issues 
The cost of providing the program continues to be a key factor for Tasmania both in terms of direct funding and in kind contribution and the corporate and local costs associated with the administrative burden of managing the program.  During the first year of implementation Tasmania's contribution represented 75% of the total program funding compared to the Australian Governments 25% contribution.

Tasmania's experience following the first year of operation demonstrates that the program would benefit from changes to the current guidelines in relation to increased flexibility for patients to enter the program from settings other than acute inpatient care, for example Department of Emergency Medicine and from the Community on General Practitioner referral.

The lack of appropriate leave provisions to exit and re-enter TC without readmission to hospital and ACAT reassessment has been found to be a significant hindrance to the smooth operation of the program and similarly the requirement for ACAT assessment for entry on to the program has also been found to cause delays and blockages in the system, due to long wait times for ACAT approvals to be completed.

The evaluation results identified high readmission rates for TCP recipients in Tasmania when compared to other states and territories.  Whilst it is recognized that there were many limitations with the data set and the data only represented a three month snapshot, this is a matter for further investigation, and further data analysis at 12 months would be useful.

## 8.7. Victoria

Victoria has led the way in Australia with a well-developed sub-acute service system.  It has a strong focus on inpatient and ambulatory sub-acute rehabilitation services and is becoming increasingly integrated within the acute service system.  Sub-acute services aim to maximise independence for patients of all ages, by providing goal oriented (and in most instances, time-limited) interventions aimed at assessing, treating and frequently managing complex conditions to maximise independence.

Victoria made a commitment, via the Australian Health Ministers Advisory Council, to implement the National Action Plan for improving the care of older people across the acute-aged care continuum, 2004-2008. Part of this commitment included the development of planning guides regarding the availability and mix of inpatient and ambulatory services for sub-acute services for older people.  In addition to this, Victoria engaged the services of Aspex Consulting to develop a Sub-acute Planning Framework, which would ensure that adequate levels of service were being provided.  The final report will be available in June 2008.

The availability of TC services has allowed Victoria to bring the best elements of previous Commonwealth and State funded service support initiatives (such as Innovative Care Rehabilitation Service and Intermittent Care pilots and Interim Care) together under a single program, with capacity to tailor the service around the needs of the individual.  It also allowed broader and more systematic coverage across the state and serves to complement Victoria's acute and sub-acute service system.  The intended outcome of this care provision approach is to minimise the number of older people who experience inappropriate extended hospital lengths of stay and/or may be prematurely admitted to residential aged care.  TC services are located at the interface between the acute/sub-acute and aged care sectors.

The TCP aims to provide an older person with the treatment and care that best suits their individual requirements and in so doing, places the older person at the centre of their care.  Older people may access TC services from an acute or sub-acute service depending on the need of the individual.  Consistent with the Department of Human Services assuming the role of approved provider, Victoria's TCP is operating as a single program, although multiple Health Services are involved in the delivery of TC services.

The effectiveness of the TCP is reliant on the recipient's capacity to 'transition' to a long-term care environment, be it in the community or in a residential care setting.  This requires access to care resources (for example, Home and Community Care, Community Aged Care Packages, Extended Aged Care Packages, Disability Support Services and residential care places) that can sustain and build on the goals achieved by the client during the TCP episode of care.  Imperative to the efficiency of the service is the close working relationship between TCP personnel and Aged Care Assessment Teams.  The use of multidisciplinary teams to deliver the TCP has proven successful in utilising the required skills and knowledge each member contributes to the development and refinement of the care plan and service.  The use of geriatrician intervention has supported the general practitioner in effectively managing the needs of an older person. TCP has been a great example to date of effective teamwork in achieving a common purpose:  better health and care outcomes for older Australians.

## 8.8. Western Australia

Western Australia (WA) was keen to continue the model successfully established through the Aged Care Innovative Pool, national pool of flexible care places.

WA planned during 2006 - 2008, within the first year the establishment of a metropolitan wide TCP with north and south locations providing a community/residential mix, and by 30 June 2008 to further expand the model to include flexible places in three rural locations.

A total of 160 TC places were requested to support the development of a program in WA:

a) 50 TC places operationalized by 1 January 2006 
The initial 50-place allocation mainstreamed the Innovative Care Rehabilitation Service Pilot operating in the north metropolitan region.  The 50 flexible places consist of 20 residential places and 30 flexible community packages.

b) 50 TC places operationalized by 1 July 2006 
The next 50-place allocation mainstreamed the Intermittent Care Service Pilot operating in the south metropolitan region.  The 50 places consist of 30 residential places and 20 flexible community packages.

c) 60 TC places operationalized by 01 May 2008 
The next 60-place allocation provided TC to three separate rural locations, South West, Midwest, and Great Southern regions through equal distribution of 20 flexible community places/packages at each site.

The model has a single point of entry for each program with local arrangements to suit the primary public health services in the area.  The most appropriate service for the client, community or residential, is determined following professional assessment by the Service Care Coordinator in the region in consultation with the referring treatment team.  The service has strong links with the teaching hospitals and with the Departments of Geriatric Medicine, Aged Care Assessment Teams, and general practice.

The model of care and services are focussed on metropolitan clientele but access opportunities are broadened to offer options statewide.  Rural residents are able to access the residential aspects of the metropolitan program should it be assessed that this is an appropriate service for the client and should appropriate supports and discharge planning arrangements be available for the client to return to their local area.

# 9.	Strengths and limitations of the National Evaluation of the Transition Care Program

The framework for the evaluation necessitated a descriptive approach, and a series of studies that gave snapshots in time of different aspects of the TCP were conducted.  This approach has both strengths and limitations, and in this section we recap briefly on the limitations in each of the six studies before commenting on the strengths and limitations of the NETCP as a whole.

## 9.1. Regional Characterization Study

To calculate the provision of health and aged care services for older people in each ACAT region, estimates of the resident population in each region were made.  Because the estimated resident population in each Statistical Local Area (SLA) by age group was not available as at 30 June 2006 in time for submission of the report for the Regional Characterization Study, the population in each SLA by age group was projected from the estimated resident population at 30 June 2005.  Thus a state level increase in population was applied at a smaller geographic area level, and the actual growth in each SLA will have varied slightly from the overall state growth in each age group.  However, it is expected that this would have had a minor impact on the reported availability of health and aged care services.

There were also differences in the timing of the concordance mappings for SLAs, ACAT regions and postcodes that were used in this study.  The concordance mapping between SLAs and ACAT region is based on 2001 SLAs.  However, the estimated resident population uses 2005 SLAs.  The suburb and SLA concordance is based on 2003 SLAs.  The concordance between 2001 and 2006 SLAs was used in the few instances where SLAs from later years did not map to ACAT regions.  Any differences in SLA boundaries between years are expected to have negligible effects when aggregated to the ACAT regional level, but nonetheless some effects were possible.

In the ACAT-SLA concordance file, two of the SLAs in New South Wales map to more than one ACAT region.  South Sydney (C) maps to both South Eastern Sydney/Illawarra and Sydney South West.  The former was assumed in the Regional Characterization Report.  Similarly the SLA of Sydney (C) - Remainder maps to both South Eastern Sydney/Illawarra and Sydney South West.  The latter has been assumed throughout this report.

## 9.2. Models of Transition Care

Two main limitations were evident in the derivation of models of TC.  The first main limitation related to the asynchrony of data that were used in the report.  In the main, data for this report were drawn from the TCP database COGNOS, administered by the Department of Health and Ageing, and covered the 2006/07 financial year.  The characteristics of ACAT regions drew on data from the 2005/06 financial year, while a survey of TC services that was also analysed in this report was carried out in November 2006. Quarterly Reports completed by the services generally were completed for the April-June 2007 period, but there was wide variation in the length of time that services had been operational when they submitted their Quarterly Report.

The second limitation related to the integrity of some of the TCP administrative data, especially those drawn from the TC Claim Form.  This report identified some issues in the reporting of discharge reason on the TC Claim Form, which possibly led to an underestimate of the proportion of TC recipients discharged to the community.

## 9.3. Quality Assessment Study

From an evaluation perspective, the analysis of the Quality Reports presented challenges.  Quality Reports were provided in a variety of electronic formats including Microsoft Word, portable document format, or images embedded within Word, and with variable security settings which prevented the easy manipulation of data. A further challenge arose from the combination of descriptive responses and multiple criteria embedded within the reporting structure.  Few services responded to the criteria in a systematic way and this detracted from the confidence with which performance against a specific criterion could be reported.  Other quality review mechanisms, such as those proposed by the Department of Health and Ageing as part of the Transition Care Quality Improvement and Monitoring Framework are required to validate and expand on the findings of Quality Assessment Study.

## 9.4. Recipient Snapshot Study

The sample of interviewed TC recipients represented one fifth of the population of TC recipients who were discharged from TC in the timeframe of the Recipients Snapshot Study.  The sample was not randomly drawn from a list of all TC recipients, because the evaluators were not able to access the names and contact details of individuals without the individual's written consent for contact.  This was because privacy legislation in each of the jurisdictions limited the personal information that could be accessed by the evaluators.

Consent to a telephone interview was provided by recipients at discharge from TC, and recipients who were discharged to hospital or residential aged care may have been discharged from TC quickly without discussions concerning the evaluation taking place.  This method of seeking consent also relied on TC services, and it is possible that some recipients were not approached if they had been recalcitrant or dissatisfied while in receipt of TC.  Thus the interviewed sample does not appear representative of the population of TC recipients in terms of discharge reason.  There was also a discrepancy with coding of discharge reason in Victoria (National Evaluation of the Transition Care Program, 2007b) so that a large proportion of recipients were discharged to 'other', and a probably under-estimate of discharges to the community.  If correct discharge destination data were available, it is likely that for Victoria a better representation of interviewed recipients from the total of all TC recipients would have been found.

Furthermore, no recipients of TC in Western Australia or the Northern Territory were interviewed.  No Western Australian recipients were approached at the request of the Department of Health in Western Australia, while the Katherine Transitional Care Unit only commenced operation in February 2007 and had few discharges by 30 June 2007.  None of the recipients of TC from the Katherine Transitional Care Unit consented to a telephone follow-up interview.

The results suggest that the interviewed sample had less functional dependence and were discharged to the community at a higher rate than the population of TC recipients over the same period.

## 9.5. Controlled Comparison Study and Costs and Effects Study

There are a number of limitations that must be borne in mind in interpreting the results from the data linkage component of the evaluation.

One of the main limitations that must be considered is the validity of the control groups against whom the comparisons of TC recipients' outcomes are made.  Without data from randomized controlled trials, an assessment of both the effects and costs of the program are difficult because comparisons with unbiased control groups are not possible. The comparability of controls is further limited by the availability of data items to match the TC recipient, Control 1 and Control 2 groups.  The proposed methodology for this part of the NETCP was to control for comorbidity (including cognitive behaviours and continence) and demographic profile in the comparisons of the three groups of people.  However, data from Part 5 of the Aged Care Client Record (ACCR) are not entered in the Aged Care Assessment Program Minimum Dataset despite being collected by assessors.  The most relevant items concerning cognitive function were unavailable and so they could not be used to compare the three types of approvals with respect to this aspect of health.  Instead, the total number of Activity of Daily Living (ADL) items for which each individual in the cohort needed help was calculated based on Question 23 of the ACCR form.  The diagnosed diseases or disorders were used to code an individual as having a diagnosed cognitive impairment.

On balance the control groups appeared a reasonable match to the TC recipients group overall. However, within jurisdictions there was considerable variation between the three groups in terms of cognitive impairment, co-resident carer availability and ADL needs.  It remains unclear if this is a difference in selection practices by different ACAT teams or whether the background differences between ACAT regions in terms of services available for older people influences the operations of these programs.

A second important limitation in the results reported here is the large proportion of individuals (22%) for whom an index hospital event could not be ascertained.  The index hospitalization was defined as the hospital event during which the ACAT assessment took place, with a leeway of up to a week allowed for individuals with close matches on hospital episode dates and ACAT assessment dates.  The proportion of individuals with no match for an index hospitalization was greater in the Control 2 group (25%) than in the TC recipients group (19%) or Control 1 group (22%).  The members of the cohort without an index hospitalization were not significantly different in terms of activity limitations or the availability of a co-resident carer. There was, however, a significant difference in terms of cognitive impairment with 28% of those without an index hospitalization versus 24% of those with an index hospitalization indicated to have cognitive impairment in the health conditions on the ACCR form.

There are several reasons that may have contributed to the high proportion of individuals without an index hospitalization. Hospital records were extracted in ACT, NSW, SA, Tasmania, and Victoria for all hospital separations between 1 October 2006 and 30 September 2007 for persons aged 65 years or more (specific records were extracted for NT, Queensland, and WA).  Therefore an index hospitalization for those people with an ACAT approval in these five states who were aged less than 65 years could not be determined.

An additional limitation is that the availability of data from private hospitals differed between jurisdictions.  Data from private hospitals were not available from NSW, and the effect of this on the data linkage is not known.  Twenty five per cent of the NSW cohort could not be linked to an index hospitalization in comparison to 19% in SA where private hospital data were available.

It must also be borne in mind that the hospital morbidity data collections were accessed for the NETCP some four months before the same data are supplied to the Australian Institute of Health and Welfare.  The hospital data were analysed as supplied, and so differences between jurisdictions in the coding of administrative discharges, for example, may explain some of the differences observed here.  The pattern of hospital readmissions appears quite different for Tasmania compared to other jurisdictions.

The cost of each day in TC was estimated as $213.86 (that is, twice the flexible care subsidy for 2007/08 of $106.93; Australian Government Department of Health and Ageing, 2008).  However, different jurisdictions may have funded the community-based and residential-based TC places at different rates, but these differential rates were not available for the evaluation.  Nevertheless, the total program costs to both Commonwealth and State or Territory providers are accurately reflected in the costing method used in this evaluation.

The economic analyses have used days of survival without institutional care as the effect.  Other important outcomes, such as the cost to achieve a one unit improvement in function (MBI) or quality of life, were not possible to examine as the data for the two control groups were not available.  Annual Accountability Reports that are completed by TC services were not included in the analyses and this may be an area for future work in informing the economic analyses.

Finally, the three and six month follow-up periods were based on time from ACAT approval, not discharge from TC, which does not provide a particularly lengthy follow-up period following completion of TC.

## 9.6. Overall strengths and limitations

One notable overall limitation is the lack of independence between the TC services and the measurement and reporting of data for the evaluation.  The evaluation design deliberately imposed as little burden as possible on individual TC recipients or TC services.  This meant that making maximum use of existing TC administrative program data was an essential part of the evaluation.

The evaluation had to balance burden on TC services and individuals with the collection of quality data.  One casualty of minimising the burden is the relatively small amount of information that was able to be collected from TC services.  Important local issues in terms of TC implementation and service delivery that were not captured in the performance indicators of function and institutional care use are therefore not addressed in the evaluation.

The integrity of administrative data bases that are not collected for the primary purpose of evaluation has been raised by other authors (Kelman and Smith 2000).  The TCP database draws data from the TC claim forms, which directly inform the financial management of the program.  As noted in the limitations concerning the Models of Transition Care Report, some of these administrative data appeared inaccurate.

A second important limitation of the evaluation overall is the limited qualitative data that were collected from individual recipients of TC.  The journey of individual TC recipients was not mapped as part of the evaluation, and this would have added strength to our ability to describe the elements of TC which were associated with successful outcomes as well as chart individuals' trajectories through the emergency, acute, rehabilitation, and aged care sectors.

It is also important to note that the hospital readmissions considered in this report included all inpatient episodes.  Some of these episodes may have been for reasons or conditions unrelated to the original index hospitalization. In addition, a distinction between emergency and elective episodes has not been made so that the overall use of the hospital system as inpatients by TC recipients and control groups was estimated.

These are balanced to some extent by one of the major strengths of the evaluation, the synthesis of findings from different studies that examined the individual, service, regional and jurisdictional level factors that were important in the delivery and experience of TC.  Furthermore, all TC services that were operational at the time of conducting the evaluation were included, rather than just a sample of TC services.

All data that were available from TC recipients were analysed.  While only a sample of TC recipients took part in telephone interviews, the data linkage methodology ensured that important outcomes of hospital readmissions, residential care admissions, and deaths were examined for all recipients of TC. One of the major strengths of the evaluation is the data linkage methodology that used current best practice.  This evaluation was the first study to link together the datasets that covered residential aged care, hospital use, mortality, and TC use on a national scale.

# 10. Summary and future directions

## 10.1. Discussion

We found that the TCP was highly valued by both recipients and carers and that during the evaluation period which covered July 2006 - September 2007 the program had successfully assisted older Australians to remain in their own homes.  Our results suggest that the target group of frail older people are being identified and offered the program across Australia and that TC is preventing hospital readmissions and transfers to residential aged care.  We have summarized the evidence found for the TC models in Table 10.1.  The current configuration of the program is constraining its efficiency so the positive effects achieved by the program are being delivered at a significant cost.  This is not surprising in a new program which is tackling a complex policy area so these costs are likely to reduce with further development of the program.  Older people moving out of hospital are at risk of experiencing fragmented services associated with the complex governance arrangements in Australia.  The program has emerged from a policy commitment to improving the integration of older people's services but translating this policy intent into an efficient operational program is likely to be an iterative process taking three to five years.

Defining the interface between rehabilitation and TC appears an important issue.  Issues of local governance will need to be considered as the program is currently at risk of setting up another post acute care silo with its own assessment processes, its own queues and introducing further fragmentation.  In some states subacute care is part of acute hospital services and TC falls under the umbrella of primary care service structures; the interface is poor and there is early evidence of problems.  If the services are to be considered a continuum then the establishment of rehabilitation bed benchmarks may need to be part of the development of TC.  The variation in rehabilitation bed provision was clearly distorting the implementation phase, exaggerating state differences and leading to inefficiencies manifest in both queues and case selection.

A more complex issue is around the emphasis in the program on change outcomes i.e. improvements in physical function, confidence and morale rather than on maintenance outcomes i.e. outcomes which prevent or delay deterioration in health, well being or quality of life (Qureshi, Patmore et al. 1998). This emphasis appears to have led to the selection of recipients who are able to achieve change outcomes, in a comparatively short period of time and probably resulted in the exclusion of many people with dementia.  Data from Victoria on recipient MBIs suggest that in their services there was less emphasis on physical function as an outcome and a greater emphasis on maintaining quality of life. However, Victorian services were penalized in our assessments of MBI efficiency (changes in function per day).

There is comparatively little emphasis in the program on process outcomes such as feeling valued and respected, having a say over the timing and type of services and the way that the funds were allocated (Qureshi, Patmore et al. 1998).  The TC interventions had the potential to be more flexible than was observed. The close alignment of most programs to conventional physical rehabilitation programs has led to less emphasis on active participation by recipients than is stated in the program guidelines.  Recipients' responses to the telephone survey indicated that the model has been implemented with the TC services allocating services to the older adult after a negotiation but these goals are constrained by the staffing mix in place. As a result, the decision on the type and amount of therapy was usually made by TC services.  In many areas competitive tendering has established panels of aged care providers to provide personal care while hospitals provide therapists and so the service is complicated and non transparent to hospital staff, patients and families.  The program is tending to use conventional health "prioritization approaches" for entry and then providing a service mix akin to hospital rehabilitation services.  There are limitations to this approach as it depends on a skilled work force, is inevitably associated with queues and there are incentives which encourage the staff to influence negotiations about what types of services will be delivered.

There is currently debate in the UK around whether Intermediate Care (a similar although different approach to post acute care) is over-emphasising physical maintenance outcomes instead of other maintenance outcomes such as sustaining social contacts and being able to stay alert and active (Glendinning, Clarke et al. 2008). There have been suggestions that leaving the house should be a key outcome of community interventions for older people rather than the outcome currently given the highest priority by both researchers and policy makers - staying out of an institution (hospital or residential aged care) (Close, Ellis et al. 1999; Beswick, Rees et al. 2008).  Given that an outcome focused approach is likely to continue, a broadening of key outcomes to align with older people's values could be considered.  In the Australian context, one of the stated aims of the TCP is to improve psycho-social functioning, with services contracted to provide activities to prevent social isolation and facilitate social contact.  A more flexible interpretation of the TC entry criteria may result in a broadening of access to the program to include those with complexity, mental health, and cognitive problems.

The analyses (although limited by reliance for comparisons on administrative data rather than appropriately selected controls) also suggested that the use of TC only in a residential setting as sites for geriatric evaluation and management by many states was probably not efficient or effective.  It took longer to get functional shifts in residential-based TC than in Victorian GEM units and this type of TC did not prevent transfer to residential aged care.  In some jurisdictions it is possible that patients in hospitals who were waiting for a place in a high level residential aged care were less likely to move to residential-based TC than patients who needed rehabilitation.  In these jurisdictions it is likely that their hospitals would still be occupied by people awaiting care while other patients likely to get home would be transferred to receive inefficient rehabilitation programs.

This issue overlaps with the problems associated with using TC to substitute for rehabilitation services and the more complex issue of how and where to deliver post acute care.  However, it also raises questions about whether the outcomes selected for performance monitoring, (which are similar to those used in rehabilitation units) are influencing the approach staff are taking to operationalize the program.  Residential-based TC offers a more appropriate environment for individuals finalizing their care arrangements than hospital wards and it allows maintenance of function and quality of life goals can be met.  However, our results suggest that while on the one hand caution should be observed in the use of these units as rehabilitation sites, on the other those jurisdictions who used residential-based TC to assist very dependent older people make long term arrangements for their care are penalized by the current performance measures focused on functional improvement.

The efficiencies of the program need exploration particularly those at the front end of the program and those factors affecting total episode costs.  Our analyses suggested that paradoxically hospital delays were occurring in the process of moving older people out of hospital with TC.  We did not include the index hospital admission in our economic analyses so ignored the delays in discharge associated with entry.  As a result it is likely that the costs we estimated are at the lower end of the spectrum.  Another strategy for decreasing costs would be to reduce the TC episode costs by examining incentives to increase turn over without decreasing the complexity of those selected.  In addition, the relative efficiencies of delivering post acute care in a home-based model (which involves therapists visiting older people at home) versus using hybrid models (e.g. home care plus centre based therapy, such as day centres/rehabilitation hospitals).

### Specific issues identified during the implementation

This evaluation focused on the period between July 2006 and September 2007 and so it represents a snapshot of the implementation phase.  We followed older people who were receiving the program from newly configured teams, at a time when they were still on a learning curve and were experimenting with triage processes and interventions.  Therefore, it is possible that some of the inefficiencies noted have reduced as staff and jurisdictional experience has increased.

- Case selection. The services and configurations of the program appeared flexible and allowed older people to receive a range of services in the community and in facilities.  However, case selection is important in determining the efficiency of the program.  There are elements of TC which have been imported from aged care services which are bureaucratic within a hospital setting.  Most home rehabilitation and discharge services involve a single assessment process rather than two assessments (ACAT assessment to approve eligibility and TC services to accept into the program).  Where recipients have no option for discharge to the community unless they receive the level of support in these programs this delay would not be a problem.  However, the high functional scores of some recipients (MBI greater than 90) suggest discharge might have been an option without the program.  Given that the program was set up to decrease time spent in hospital, the suggestion in some states and territories that the program is introducing delays in hospital discharge needs to be monitored.  Jurisdictions could also review case selection for community-based TC places and consider whether alternative services might achieve the same result in a more timely fashion.  Admission to the program is complex and the investment in supporting individuals comparatively high so the program could be reserved for more disabled individuals.  The eligibility requirements do not currently exclude older people with cognitive impairment yet it appeared that several jurisdictions were excluding people with dementia (although they are at particular risk of readmission to hospital and movement into residential aged care) and focusing on physical disability.  Consideration could be given to clarifying whether this group is intended to be excluded.

- The interface with subacute care. The variation faced by older Australians in access to subacute beds across Australia was one of the most striking findings of this evaluation.  The selection of cases (as evidenced by the recipients' disability levels) to receive TC places is likely to be influenced by the availability of other subacute services and cross state comparisons of disability levels suggested that TC was substituting for traditional subacute services in many jurisdictions.  For example, the program appeared to provide services in Queensland to older adults who would probably have received state funded Home Rehabilitation programs in other jurisdictions and in South Australia the residential-based units appeared to accept older adults who may have entered GEM units in Victoria (it was noteworthy that those entering residential-based TC in SA were less disabled (as measured by MBI) than those entering GEM in Victoria).  Based on the limited comparisons that we were able to make by using administrative data, it appeared that by using TC as a substitution for conventional rehabilitation approaches these states had settled for less efficient approaches (e.g. longer stays in residential-based TC than in GEM, longer delays to accessing community TC for older people) and this is likely to be contributing to the high costs of the program.  As a result, it also seems that groups of very disabled older adults who might access TC in regions with strong subacute services access are not entering TC in states such as Queensland where the TC places are occupied by less disabled patient groups.  This is a complex area and it is unlikely that the services will ever accept the same cases in each state.  However, the boundary between subacute care and TC was very unclear in several states and unless this interface is clarified it is likely to confound improvements in efficiency.  The definition of a rehabilitation episode of care includes psychiatric rehabilitation which appears to have led to some differences in reporting approaches from jurisdictions, as some states included psychiatric rehabilitation episodes of care in their count of rehabilitation episodes of care while others did not.  It would be helpful if reporting allowed national comparisons, longitudinal reporting of changes in bed stock and to allow for accurate workforce planning.  This would be consistent with Principle 5 of the National Action Plan for improving the care of older people across the acute-aged care continuum 2004-2008 "... all jurisdictions will develop and agree on standard definitions and consistent data collections and performance indicators to measure access to rehabilitation, geriatric evaluation and management, psychogeriatric, palliative care and other specialized health services for older people" (see Appendix 1).

- Allocation. Given the widespread shortages, access to TC places might be improved if a move was made to incorporate a population based allocation such as currently used by the Commonwealth to allocate aged care places i.e. per 1,000 population aged 70 years and over.  If this were not possible consideration should be given to allocation of TC places according to areas of need as assessed by the map of aged care places and subacute hospital beds provided in the Regional Characterization Report.  A state or territory based plan, taking into account local issues such as workforce and service, could also be explored. Many areas identified as particularly lacking in both aged care and subacute services were rural which will present workforce difficulties.  However, the program is flexible allowing a range of professions and organizations to deliver TC services.

- Hospital readmissions. The hospital readmission rate was high particularly in the community-based TC group. Access to a medical assessment and a pharmacy review of drugs is likely to reduce (although not eliminate) this rate.  Very few TC services had allocated funds to include medical or pharmacy staff in their programs.  Older adults with medication discrepancies on transfer are more likely to be re-hospitalized within 30 days than those without (Coleman, Mahoney et al. 2005).  In addition, a relationship between readmission rates and number of nursing staff was established.  Evidence that the team members providing services to recipients are broad and collected at the service level in Quarterly Reports, but are not available at the recipient level.  The governance structures and responsibility for clinical outcomes in residential-based TC units can be unclear and this has been identified in the UK as a problem.

- Leave rule. A substantial proportion of TC recipients (22%) ended their programs back in hospital and many subsequently reapplied to return to TC, adding burden to ACATs through the additional assessments required for many re-entries.  Acknowledging the frailty of this group and the high hospital readmission rates, the rule regarding transfer back to hospital which currently allows a leave period of only 24 hours could be reviewed and consideration given to allowing a longer period of leave.  For example, seven days would allow for a short hospital stay and return to TC service without creating the need for a second ACAT assessment.  This may also reduce the proportion who are ultimately discharged to hospital, with more discharged from the service to the community or residential aged care.  This would also allow a better assessment of the final residential outcome of TC recipients.

- Measures of Transition. Internationally the risks associated with transfer 'episodes' between institutions and systems of care in institutionalized older adults are high enough and occur frequently enough for the terms 'falling through the cracks" and "transfer trauma" to have entered the literature (Coleman 2003; Sherman 2006).  The US is using a 'pay for performance' strategy for managing transfer outcomes (Sherman 2006).  Recognising that older patients with complex conditions require care from a variety of settings and that poor transitions between these settings threaten safety and increases costs, there has been considerable focus in the US on guidelines to improve the transfer and on a patient tool (the Care Transition Measure) which assess change in health system performance (Coleman, Boult et al. 2003; Coleman, Mahoney et al. 2005).  The Care Transition Measure is currently being trialled in 200 hospitals in 10 European countries as a quality indicator of transfer from hospital (Coleman, Parry et al. 2007).  We trialled this tool in the telephone survey of recipients and we found that the scores were suggesting problems with medication management.  However, scores did not predict rehospitalization so further work is needed to identify an indicator that has predictive validity.

- End of life care.  Achieving a good death e.g. advance directives could be reasonably considered with certain patients.  Twenty percent of those over 80 who received TC only in a residential setting were dead at six months suggesting end of life issues were important.  In the UK, programs have been developed to ask doctors to identify patients using the questions "would you be surprised if this patient died within the next year?"  Patients identified in this way then have differing quality measures applied (Dy and Lynn 2007).  Consideration could be given to including end of life quality measures in residential-based TC.

- Workforce has been a significant barrier in the US to providing post acute care.  In particular, many doctors are not prepared to work in geriatrics and long term care and this lack of medical practitioner interest is viewed as a greater impediment than the financial and delivery problems (Anonymous 2008).  Disease management programs have been in place in the US since the 1990s and more recently variations of these chronic care models with strategies to increase the level of medical involvement have been described (e.g. telemedicine, Advanced Medical Homes) in the US (Wagner, Austin et al. 2001; Bodenheimer, Lorig et al. 2002).  There may need to be some exploration of these new models to allow rural areas to deal with accessing specialist staff.

- Residential-based TC - minimum size. We were unable to answer the question around whether TC provided in a residential-based setting should be offered as single places in aged care settings or whether larger numbers of co-located clients will achieve greater outcomes.  We were also unable to find differences in outcomes of residential sites provided on hospital grounds compared with residential-based TC in existing facilities.  Without critical mass it seems unlikely that older adults are receiving adequate therapy and nursing levels, the facilities are unlikely to have appropriate equipment and gyms for one or two clients and more importantly the interface with acute care is more likely to improve with higher numbers of TC recipients.

- Access to other aged care services. At a recipient level the long-term effectiveness of the program is largely dependent on the ability for the individual to transition to long-term care support, whether this is in the community or in a residential care setting.  Access to supports such as HACC, CACP, EACH, low and high care places is essential in supporting and maintaining the goals achieved for the TCP recipient.  The current levels of service provision are potentially limiting the benefit of the program, especially where recipients are unable to access a CACP or EACH and therefore require residential aged care.

- Reducing out-of-pocket costs.  Developing a funding method to reduce out-of-pocket costs for TC recipients with extensive equipment needs, especially where it is unlikely that other resource programs will be in a position to intervene in time, is another potential area for consideration.

- A future evaluation of the TCP could include an analysis of the financial data included in the Annual Accountability reporting that all TC services have to submit.  This could usefully supplement the other resource use estimates that were used in the evaluation.  While the Annual Accountability Reports do not include patient level data, the reports demonstrate the wide variability in expenditure by TC services with different models.

- Longer-term follow-up. A longitudinal study involving either the client group included in the Recipient Snapshot Study or the client group included in the data linkage study (Controlled Comparison Study and Costs and Effects Study) may provide useful data about the longer term effect of the TCP, particularly if combined with several years of Annual Accountability Reporting.

### Table 10.1:  Transition Care Program: assumptions behind the model and evidence for these assumptions.

| No. | Assumption | Evidence |
| --- | --- | --- |
| 1 | The planning benchmark for residential aged care is not being met in a number of regions (Principle 1 page 5 (Australian Health Ministers' Advisory Council 2004)). | We identified regions where the planning benchmarks for residential aged care were not met. |
| 2 | Provision of step-down and rehabilitation is variable and few jurisdictions have known benchmarks for estimating the level of provision (Principle 1 page 5 (Australian Health Ministers' Advisory Council 2004)) | We confirmed that provision of rehabilitation beds was variable but across Australia was around 3.0 per 1,000 older people aged 70 plus for the 2005/06 period. Victoria had a substantially larger subacute sector than other jurisdictions. |
| 3 | Alternate models of care in settings other than hospitals can lead to improvements in functional status from an additional period of time limited low intensity therapy and care. | We confirmed that improvements in functional status occurred |
| 4 | The alternative models should be in additional to the other existing services jurisdictions provide to support older people moving from hospital to home. | We found that these older people entered these services at the end of existing hospital services. There was much variation in the point at which this occurred and in jurisdictions where there were limited rehabilitation services TC appeared to substitute for rehabilitation services. |
| 5 | Older people waiting for residential aged care are “blocking” hospital beds (Service provision for older people in the acute – aged care system (Gray, Dorevitch et al. 2002). | No evidence was provided on this issue. |
| 6 | TC services should have a focus on recovery or maintaining function as well as facilitating long-term care arrangements. | There was evidence that the units focused on recovery and maintaining function. |
| 7 | TC services should have interdisciplinary input, coordinated by a case manager where possible. | It was not clear that interdisciplinary input occurred. Many services used a team approach. However, brokerage services were often in place for personal care and some services were limited (medical, nursing, pharmacy). Staffing levels varied. Lower levels of allied health staff predicted transfer to care and lower levels of nursing staff predicted hospital readmission. It was unclear whether an interdisciplinary model was in place (i.e. no evidence of team case meetings and shared goal setting) but there did appear to be a multidisciplinary team in most areas. |
| 8 | TC is likely to be providing care [rehabilitation] at a lower cost than hospital based care (ICRS (Department of Health and Ageing 2005)). | Our results suggest that individuals with similar levels of disability at entry spend longer in TC units and have less efficient functional gain that those in rehabilitation units and GEM units. |
| 9 | A consistent application of data definitions and appropriate data items are fundamental to a robust service planning process. Nationally consistent application of existing definitions for subacute services is therefore a priority. | We identified inconsistencies in the reporting of rehabilitation beds with some states including psychiatric rehabilitation beds in their count of rehabilitation beds while others did not. |
| 10 | A model for data linkage to include the acute, subacute aged care and community care data sets should be established in every linkage jurisdiction. | The feasibility of data linkage of these data sets was demonstrated. |

## 10.2. Comparison of the Innovative Care Rehabilitation Services pilot and the National Evaluation of the Transition Care Program

Table 10.2 presents a comparison of the findings from the ICRS report and the present NETCP report.  Given that the ICRS evaluation was used to develop the TC funding model and the current evaluation of the implementation phase has demonstrated that the costs are high, detailed comparisons of the two approaches are included to assist policy makers' assessments.  There are many similarities between ICRS and the NETCP.  Both the demographics of the recipients and the functional changes that were achieved are comparable.  Differences between the two evaluations result from the sampling methodologies, the retention rates of participants, and the approach to the economic evaluation.  The strength of the ICRS evaluation is the significantly richer data for the TC experience, in terms of the characteristics of the services, the type, and duration of therapy.  In contrast, the NETCP was able to sample and follow-up a large percentage of TC recipients which provides a more comprehensive picture of the outcomes of TC.

The two reports used different approaches to the economic evaluation.  Strong assumptions concerning residential aged care use were inherent in the ICRS report, and their conclusion heavily relies on the assumption that in the absence of TC, people would have received residential aged care for the entire period.  In contrast, the NETCP compared program costs and cost offsets for TC recipients and people approved for CACP, and this showed that only 28% of TC recipients were admitted to residential aged care in the six months post ACAT approval.  A fuller description of the differences is presented in Appendix 2.

Finally, the analysis of the linked datasets gave many opportunities for analysing the health outcomes of both TC recipients and other frail older people who had recently been hospitalized.  As noted by Kelman, Bass and Holman (Kelman, Bass et al. 2002), the increasing number and availability of health data resources in Australia provides an opportunity for significant advances in the monitoring and evaluation of health outcomes, and thus could lead to improvements in the quality of health care.  The investment in the national 'Population health and clinical data linkage' funded from the National Collaborative Research Infrastructure Strategy will help to realize the full potential of health data linkage in evaluations of new health services and programs such as the TCP.  A data linkage approach is particularly attractive in evaluations that involve older groups of people, because cognitive and other health issues can lead to significant difficulties in interviewing a representative sample of people.  Further analysis of the linked data sets from the national evaluation will help to fully realize the potential that exists with this approach.

This evaluation of the implementation phase of TC provides evidence that the current TC model is reaching an appropriate group and delivering positive outcomes, our estimates around program efficiency suggest that piloting of different interventions, and different delivery approaches with rigorous economic evaluations should be considered.

### Table 10.2: Comparison between the results from the National Evaluation of Innovative Care Rehabilitation Services and the National Evaluation of the Transition Care Program

| Item | ICRS | NETCP | Comment |
| --- | --- | --- | --- |
| Sample | • 2001-2004 • 1,810 completed episodes • 170 excluded from the analysis as they did not meet eligibility criteria • Final dataset 1,640 episodes | • 2006-2007 • 3,206 ACAT approvals for TC • Final linked data available for 2,443 • 879 Control 1. • 2,188 Control 2. | • ICRS sample of 907 represents 55% of eligible episodes • NETCP sampled 76% of TC approvals |
| Follow-up and retention | • 3 months post discharge • 6 months post discharge • At discharge n= 907 • 3 month n=350 • 6 month n=309 | • 3 months post ACAT approval • 6 months post ACAT approval • All 2,443 recipients included | • ICRS retention rate was 39% at 3 months and 34% at 6 months |
| Demographics | • 70% female • Mean age 81.5 years • 46% had a carer • 64% aged 80+ | • 64% female • Mean age 82.2 years • 41% had a co-resident carer • 61% aged 80+ | • The groups appear similar |
| Service characteristics | • Community 54.9 mins/day • Residential 38.7 mins/day • Combination 60.3 mins/day | • 1203 Community places • 1026 Residential places • 213 Combination places | • Comparable data on therapy time per day not available |
| Functional Change (as measured using the MBI at admission and discharge for the TC episode) | • Overall - Mean admission MBI 67.3 - Mean discharge MBI 79.1 • Community - Mean admission MBI 77.1 - Mean discharge MBI 85.8 • Residential - Mean admission MBI 60.5 - Mean discharge MBI 72.3 | • Overall - Mean admission MBI 64.3 - Mean discharge MBI 76.9 • Community - Mean admission MBI 73.7 - Mean discharge MBI 84.8 • Residential - Mean admission MBI 51.1 - Mean discharge MBI 65.0 | • Overall the groups appear similar, however, the functional status at entry of residential based TC and community-based TC recipients in the NETCP appears lower than the ICRS sample |
| Hospital Readmission (one or more times in the follow-up period) | • 3 months follow-up - Overall 21% • 6 month follow-up - Overall 22% • A breakdown by type of TC was not presented in the ICRS report | • 3 months post ACAT approval - Overall 37% - Community 39% - Residential 35% • 6 months follow-up - Overall 47% - Community 51% - Residential 43% | • ICRS used self-reported data for hospital readmissions which may have underestimated the true incidence |
| Living at home at follow-up | • 3 months follow-up - Overall 81.6% • 6 months follow-up - Overall 81.5% • A breakdown by type of TC was not presented in the ICRS report | • 3 months post ACAT approval - Overall 78% - Community 96% - Residential 55% • 6 months post ACAT approval - Overall 70% - Community 93% - Residential 42% | • The difference between ICRS and NETCP possibly reflects the higher proportion of community dwelling TC recipients in ICRS |
| Economic analysis | • Cost-benefit approach • Residential costs $236 per day or 10,500 per episode • Community costs $86 per day (5,300 per episode) • Overall cost benefit of 4.7 million in savings | • Cost-effectiveness approach • Taking into account costs of hospital readmissions and residential aged care admissions in the follow-up period, at six months post ACAT approval TC cost $344 per additional day of survival without institutional care compared with Control 2 | • Two different approaches were used. ICRS implicitly assumed that the average 65 day LOS in TC would have been spent entirely in residential aged care in the absence of TC. Hospital costs were not taken into account in ICRS |

## 10.3. Areas for future work

A number of areas have been identified as important for further work that may lead to improvements in the TCP:

- There is considerable uncertainty around the effectiveness and resource implications of model configurations and delivery approaches. This evaluation failed to produce information on the impact on costs of different governance and brokerage arrangements across Australia and their impact on costs. A detailed economic analysis of differing models of delivery (e.g. voucher system versus conventional TC) which included Medicare Australia data items at an individual level would significantly contribute to a better understanding of key areas of decision-making uncertainty.

- Modelling could be undertaken to assess costs by week to explore the MBI shifts per week. Exploration of ideal lengths of stay could be undertaken e.g. can you truncate the episode cost without losing the effect?

- Very little qualitative data was collected in this evaluation and very little information was available on the differences in the approach to implementation which occurred in each state. It is unclear what role the state policy makers and context had on the approach. The definition of the target population, approach to assessment, care planning, and composition of the teams differed substantially in each state. There was no information on the background services against which the program was introduced or on barriers to success. Finally, there was no information on which organizational structures appeared to work well or on processes e.g. what happened when deteriorations occurred, which might have informed our understanding of the readmission rates. Overall, there appeared to be poor engagement with GPs and local hospital elderly care units – it is unclear why. Information on these issues would enhance development of the program.

- More work on appropriate outcomes should be undertaken. Using the model of outcomes put forward by Qureshi (Qureshi, Patmore et al. 1998) where there are three types of outcomes, namely change outcomes, maintenance outcomes, and process outcomes, the program is currently very focused on change outcomes. Inclusion of additional outcomes of relevance to older people such as being able to go out or having an appropriate environment should be explored. More work on quality indicators for these types of services is required.

- Further investigation of the types of intervention that should be offered is necessary. For example, case management may have been a key intervention with navigation provided through the complex health and social care systems providing information on referrals and ensuring that follow-up care occurred.  Evidence on this approach from the UK and US is mixed but reviews could be sought to assist in evaluating the approach.

- Work could be undertaken to gain a better understanding of readmissions in the frail elderly. UK data suggests that there is no stable pool of “frequent flyers”. A cohort of patients with two unplanned admissions in a year reverts over four years to the same level of unplanned readmissions for that age group (Roland, Dusheiko et al. 2005). It is not clear what happens in Australia and information on this issue would inform interventions.

- TC delivered in a residential setting ge TC delivered in a residential setting generally needed more investigation as there is much uncertainty around this model e.g. the types of cases who benefit most, appropriate staffing levels and competencies, quality approaches.

## 10.4. Summary

This evaluation of the implementation phase found evidence that TC is improving the experiences of older people at the interface between acute and aged care services.  Individual outcomes are improving and system processes are evolving.  Meeting the needs of the ageing population cost effectively without compromising on quality is difficult and it appears at this stage the program is trading off higher costs to ensure quality services which is a reasonable approach for a new program focusing on vulnerable older people.  Over time efficiencies are very likely and evaluation of costs at a later date with longer follow-up (e.g. 12 months) and greater coverage (e.g. medications) would very likely show reductions in the costs.  There were surprising differences between jurisdictions in the availability of subacute rehabilitation and geriatric services which did affect the implementation, as TC was often required to fill a pre-existing gap in state and territory services.  This does raise questions about the level of improvement that can be made by simply adding one program and whether a larger review of post acute services may be necessary.  The risk of setting up an additional post acute silo has been identified and evidence provided on queues and inconsistent case selection across jurisdictions.  Nevertheless our evaluation found that the program has made a significant contribution to post acute options for older people and appears to be successfully assisting older people to stay living independently in the community.

# 11. References

Anonymous (2008). "Who cares for the elderly?" Lancet 371(9617): 959.

Australian Government Department of Health and Ageing (2005). "Transition Care Program Guidelines." Department of Health and Ageing, Canberra, Australia.

Australian Government Department of Health and Ageing (2007). "Securing the future of aged care for Australians." Department of Health and Ageing, Canberra, Australia.

Australian Health Ministers' Advisory Council (2004). "From hospital to home: Improving care outcomes for older people." Victorian Department of Human Services, Melbourne, Australia.

Australian Institute of Health and Welfare (2005). "METeOR: Metadata online registry (Hospital service - care type, code)." Australian Institute of Health and Welfare, Canberra, Australia http://meteor.aihw.gov.au/content/index.phtml/itemId/270174.

Australian Institute of Health and Welfare (2007). "Older Australians in hospital.  Bulletin 53, Cat. No. AUS 92." Australian Institute of Health and Welfare, Canberra, Australia.

Ayis, S., R. Gooberman-Hill, et al. (2006). "Predicting catastrophic decline in mobility among older people." Age & Ageing 35(4): 382-7.

Battersby, M., P. Harvey, et al. (2007). "SA HealthPlus: a controlled trial of a statewide application of a generic model of chronic illness care." Milbank Quarterly 85(1): 37-67.

Beland, F., H. Bergman, et al. (2006). "Integrated services for frail elders (SIPA): a trial of a model for Canada." Canadian Journal on Aging 25(1): 5-42.

Beswick, A. D., K. Rees, et al. (2008). "Complex interventions to improve physical function and maintain independent living in elderly people: a systematic review and meta-analysis." Lancet 371(9614): 725-35.

Black, D. A. (2007). "Case management for elderly people in the community." BMJ 334(7583): 3-4.

Bodenheimer, T., K. Lorig, et al. (2002). "Patient self-management of chronic disease in primary care." JAMA 288(19): 2469-75.

Branch, L. G., R. F. Coulam, et al. (1995). "The PACE evaluation: initial findings." Gerontologist 35(3): 349-59.

Buntin, M. B. (2007). "Access to postacute rehabilitation." Archives of Physical Medicine & Rehabilitation 88(11): 1488-93.

Byles, J. E., M. Tavener, et al. (2004). "Randomised controlled trial of health assessments for older Australian veterans and war widows." Medical Journal of Australia 181(4): 186-90.

Cameron, I. D. and O. Davies (2007). "Transition Care: what is it and what are its outcomes?" Medical Journal of Australia 187(3): 197-8.

Carpenter, I., J. R. Gladman, et al. (2002). "Clinical and research challenges of intermediate care." Age & Ageing 31(2): 97-100.

Centers for Medicare and Medicaid Services (2006). "Post-acute care reform plan." Centers for Medicare and Medicaid Services, Baltimore, US http://www.cms.hhs.gov/SNFPPS/Downloads/pac_reform_plan_2006.pdf.

Chappell, N. L., B. H. Dlitt, et al. (2004). "Comparative costs of home care and residential care." Gerontologist 44(3): 389-400.

Chen, Q., R. L. Kane, et al. (2000). "The cost effectiveness of post-acute care for elderly Medicare beneficiaries." Inquiry 37(4): 359-75.

Close, J., M. Ellis, et al. (1999). "Prevention of falls in the elderly trial (PROFET): a randomised controlled trial." Lancet 353(9147): 93-7.

Coleman, E. A. (2003). "Falling through the cracks: challenges and opportunities for improving transitional care for persons with continuous complex care needs." Journal of the American Geriatrics Society 51(4): 549-55.

Coleman, E. A., C. Boult, et al. (2003). "Improving the quality of transitional care for persons with complex care needs." Journal of the American Geriatrics Society 51(4): 556-7.

Coleman, E. A., E. Mahoney, et al. (2005). "Assessing the quality of preparation for posthospital care from the patient's perspective: the care transitions measure." Medical Care 43(3): 246-55.

Coleman, E. A., C. Parry, et al. (2007). "The central role of performance measurement in improving the quality of transitional care." Home Health Care Services Quarterly 26(4): 93-104.

Council of Australian Government (1995). "Task force on health and community services. Health and community services: meeting people's needs better. A discussion paper." Commonwealth of Australia, Canberra.

Crotty, M., C. H. Whitehead, et al. (2005). "Transitional care facility for elderly people in hospital awaiting a long term care bed: a randomised controlled trial." Br Med J 331(7525): 1110-1113.

Daff, D., J. M. Stepien, et al. (2006). "Moving from hospital to a transitional care unit: carers' views." Qualitative Health Research 16(2): 189-205.

Dale, S. B. and R. S. Brown (2007). "How does Cash and Counseling affect costs?" Health Services Research 42(1 Pt 2): 488-509.

Department of Health and Ageing (2005). "National evaluation of the Innovative Care Rehabilitation Services (ICRS) pilot program." Department of Health and Ageing, Canberra, Australia.

Department of Health and Ageing (2008). "Transition Care Program COGNOS database." Department of Health and Ageing, Canberra, Australia.

Dwyer, J. and T. Jackson (2001). "Literature review: Integrated bed and patient management." Department of Human Services Victoria.

Dy, S. and J. Lynn (2007). "Getting services right for those sick enough to die." BMJ 334(7592): 511-3.

Eagar, K., R. Gordon, et al. (2001). "The Australian Sub-Acute and Non-Acute patient Classification (ANSNAP): report on the National Sub-Acute and Non-Acute Casemix Study." Centre for Health Service Development, University of Wollongong.

Esterman, A. J. and D. I. Ben-Tovim (2002). "The Australian coordinated care trials: success or failure? The second round of trials may provide more answers." Medical Journal of Australia 177(9): 469-70.

Evans, R. L., R. T. Connis, et al. (1995). "Multidisciplinary rehabilitation versus medical care: a metaanalysis." Social Science & Medicine 40(12): 1699-706.

Freedman, V. A., N. Hodgson, et al. (2006). "Promoting declines in the prevalence of late-life disability: comparisons of three potentially high-impact interventions." Milbank Quarterly 84(3): 493-520.

Fried, L. P., L. Ferrucci, et al. (2004). "Untangling the concepts of disability, frailty, and comorbidity: implications for improved targeting and care." Journals of Gerontology Series A-Biological Sciences & Medical Sciences 59(3): 255-63.

Gadzhanova, S. and R. Reed (2007). "Medical services provided by general practitioners in residential aged-care facilities in Australia." Medical Journal of Australia 187(2): 92-4.

Glendinning, C., S. Clarke, et al. (2008). "Progress and problems in developing outcomes-focused social care services for older people in England." Health & Social Care in the Community 16(1): 54-63.

Godfrey, M., J. Keen, et al. (2005). "An evaluation of Intermediate Care for older people." Institute of Health Sciences and Public Health Research Leeds, UK.

Gravelle, H., M. Dusheiko, et al. (2007). "Impact of case management (Evercare) on frail elderly patients: controlled before and after analysis of quantitative outcome data." BMJ 334(7583): 31.

Gray, L., M. Dorevitch, et al. (2002). "Service provision for older people in the acute-aged care system." Victorian Department of Human Services, Melbourne, Australia.

Gray, L. C., C. M. Travers, et al. (2008). "Transition care: will it deliver?" Medical Journal of Australia 188(4): 251-3.

Gross, D. L., H. Temkin-Greener, et al. (2006). "The growing pains of integrated health care for the elderly: Lessons from the expansion of PACE." Milbank Quarterly 82(2): 257-82.

Harrington, C., C. Cassel, et al. (1991). "A national long-term care program for the United States. A caring vision. The Working Group on Long-term Care Program Design, Physicians for a National Health Program." JAMA 266(21): 3023-9.

Hebert, R., P. J. Durand, et al. (2003). "PRISMA: a new model of Integrated Service Delivery for the frail older people in Canada." International Journal of Integrated Care 3: e08.

Heggestad, T. (2002). "Do hospital length of stay and staffing ratio affect elderly patients' risk of readmission? A nation-wide study of Norwegian hospitals." Health Services Research 37(3): 647-65.

Hofmarcher, M. M., H. Oxley, et al. (2007). "Improved health system performance through better care coordination." OECD Health Working Paper No. 30.

Hughes, S. L., A. Ulasevich, et al. (1997). "Impact of home care on hospital days: a meta analysis." Health Services Research 32(4): 415-32.

Hutt, R., R. Rosen, et al. (2004). "Case-managing long-term conditions: What impact does it have in the treatment of older people?" King's Fund, London, UK.

Kane, R. L. (2007). "Assessing the effectiveness of postacute care rehabilitation." Archives of Physical Medicine & Rehabilitation 88(11): 1500-4.

Kane, R. L., Q. Chen, et al. (1998). "Functional outcomes of posthospital care for stroke and hip fracture patients under medicare." Journal of the American Geriatrics Society 46(12): 1525-33.

Kane, R. L., M. Finch, et al. (1996). "Use of post-hospital care by Medicare patients." Journal of the American Geriatrics Society 44(3): 242-50.

Kane, R. L., W.-C. Lin, et al. (2002). "Geographic variation in the use of post-acute care." Health Services Research 37(3): 667-82.

Kaplan, S. J. (2007). "Growth and payment adequacy of medicare postacute care rehabilitation." Archives of Physical Medicine & Rehabilitation 88(11): 1494-9.

Kardamanidis, K., K. Lim, et al. (2007). "Hospital costs of older people in New South Wales in the last year of life." Medical Journal of Australia 187(7): 383-6.

Kauh, B., T. Polak, et al. (2005). "A pilot study: post-acute geriatric rehabilitation versus usual care in skilled nursing facilities." Journal of the American Medical Directors Association 6(5): 321-6.

Kelman, C. and L. Smith (2000). "It's time: record linkage--the vision and the reality." Australian & New Zealand Journal of Public Health 24(1): 100-1.

Kelman, C. W., A. J. Bass, et al. (2002). "Research use of linked health data - a best practice protocol." Australian & New Zealand Journal of Public Health 26: 251-255.

Kodner, D. L. and C. K. Kyriacou (2003). "Bringing managed care home to people with chronic, disabling conditions: prospects and challenges for policy, practice, and research." Journal of Aging & Health 15(1): 189-22.

Kramer, A. M., J. F. Steiner, et al. (1997). "Outcomes and costs after hip fracture and stroke. A comparison of rehabilitation settings." JAMA 277(5): 396-404.

Leutz, W. N. (1999). "Five laws for integrating medical and social services: lessons from the United States and the United Kingdom." Milbank Quarterly 77(1): 77-110.

Lim, W. K., S. F. Lambert, et al. (2003). "Effectiveness of case management and post-acute services in older people after hospital discharge." Medical Journal of Australia 178(6): 262-6.

Liu, Z., P. Braun, et al. (2001). "The probability of using an aged care home over a lifetime.  AIHW cat, no. AGE 21." Australian Institute of Health and Welfare, Canberra, Australia.

Lunney, J. R., J. Lynn, et al. (2002). "Profiles of older medicare decedents." Journal of the American Geriatrics Society 50(6): 1108-12.

Murray, S. A., M. Kendall, et al. (2005). "Illness trajectories and palliative care." BMJ 330(7498): 1007-11.

National Evaluation of the Transition Care Program (2007a). "Models of Transition Care." Department of Health and Ageing, Canberra, Australia.

National Evaluation of the Transition Care Program (2007b). "Recipient Snapshot Study." Department of Health and Ageing, Canberra, Australia.

National Evaluation of the Transition Care Program (2007c). "Regional Characterization Report." Department of Health and Ageing, Canberra, Australia.

National Evaluation of the Transition Care Program (2008). "Data Linkage Components:  Controlled Comparison Study, Costs and Effects Study." Department of Health and Ageing, Canberra, Australia.

Naylor, M. D., D. Brooten, et al. (1999). "Comprehensive discharge planning and home follow-up of hospitalized elders: a randomized clinical trial." JAMA 281(7): 613-20.

Neu, C. R., S. Harrison, et al. (1989). "Medicare patients and post-acute care: Who goes where? Report no. R-3780-MN. Rand Corp, Santa Monica, US.

Parker, G., P. Bhakta, et al. (2000). "Best place of care for older people after acute and during subacute illness: a systematic review." Journal of Health Services & Research Policy 5(3): 176-89.

Parker, S. G., S. D. Lee, et al. (2004). "The benefits of joined up care: Coordinated discharge procedures in the elderly." Evidence-Based Healthcare and Public Health 8(6): 323-4.

Parker, S. G., S. M. Peet, et al. (2002). "A systematic review of discharge arrangements for older people." Health Technology Assessment (Winchester, England) 6(4): 1-183.

Pit, S. W., J. E. Byles, et al. (2007). "A Quality Use of Medicines program for general practitioners and older people: a cluster randomised controlled trial." Medical Journal of Australia 187(1): 23-30.

Preen, D. B., B. E. S. Bailey, et al. (2006). "Willingness of general practitioners to participate in enhanced primary care discharge care planning." Medical Journal of Australia 184(2): 90-1.

Qureshi, H., C. Patmore, et al. (1998). "Outcomes in community care practice. Overview: Outcomes of social care for older people and carers. Report no. 5." Social Policy Research Unit, University of York, York, UK.

Rigby, D. (2006). "Residential MMRs leading the way [Pharmacists have been remunerated for Residential Medication Management Reviews (RMMRs) by the Australian government since 1997]." Australian Pharmacist 25(10): 766-70.

Roland, M., M. Dusheiko, et al. (2005). "Follow up of people aged 65 and over with a history of emergency admissions: analysis of routine admission data." BMJ 330(7486): 289-92.

Rolland, Y., F. Pillard, et al. (2007). "Exercise program for nursing home residents with Alzheimer's disease: a 1-year randomized, controlled trial." Journal of the American Geriatrics Society 55(2): 158-65.

Shepperd, S. and S. Iliffe (1998). "The effectiveness of hospital at home compared with in-patient hospital care: A systematic review." Journal of Public Health Medicine 20(3): 344-50.

Sherman, F. T. (2006). "Don't let transitional care fall through the cracks." Geriatrics 61(4): 9-10.

Shortus, T. D., M. L. Coulson, et al. (2005). "An aged care liaison nurse can facilitate care planning using the Enhanced Primary Care items." Australasian Journal on Ageing 24(2): 67-8.

Steering Committee for the Review of Government Service Provisions (2007). "Report on Government Services 2007." Productivity Commission, Canberra, Australia.

Stone, R. I. (2000). "Long-term care for the elderly with disabilities: current policy, emerging trends, and implications for the twenty-first century." Milbank Memorial Fund, New York, USA.

Stott, D. J., P. Langhorne, et al. (2008). "Multidisciplinary care for elderly people in the community." Lancet 371(9614): 699-700.

Stuck, A. E., A. L. Siu, et al. (1993). "Comprehensive geriatric assessment: a meta-analysis of controlled trials." Lancet 342(8878): 1032-6.

Stuck, A. E., J. M. Walthert, et al. (1999). "Risk factors for functional status decline in community-living elderly people: a systematic literature review." Social Science & Medicine 48(4): 445-69.

Tappen, R. M., K. E. Roach, et al. (2000). "Effect of a combined walking and conversation intervention on functional mobility of nursing home residents with Alzheimer disease." Alzheimer Disease & Associated Disorders 14(4): 196-201.

United Health Europe (2005). "Assessment of the Evercare Programme in England 2003-2004." Department of Health, London, UK.

Wagner, E. H., B. T. Austin, et al. (2001). "Improving chronic illness care: translating evidence into action." Health Affairs 20(6): 64-78.

Walker, A. and C. Hennessy (2004). "Growing older: Quality of life in old age." Open University Press, Maidenhead.

Weaver, F. M., E. C. Hickey, et al. (2008). "Providing all-inclusive care for frail elderly veterans: evaluation of three models of care." Journal of the American Geriatrics Society 56(2): 345-53.

# Appendix 1: Extracts from From Hospital to home – Improving care outcomes for older people, a National Action Plan for improving the care of older people across the acute-aged care continuum 2004 – 2008

## Principle 1: Older people have access to an appropriate level of health and aged care 	services that match their changing needs.

Key stakeholders: State/territory governments, Australian Government

| Statements of intent | Actions and milestones |
| --- | --- |
| 1. State/territory governments commit to an adequate level and mix of inpatient and ambulatory services including rehabilitation, geriatric evaluation management, psychogeriatric services and palliative care and other specialised health services for older people. This includes: - Developing planning guides that identify the adequate level and mix of inpatient and ambulatory services including rehabilitation, geriatric evaluation management psychogeriatric services and palliative care and other specialised health services for older people by geographic region - Ensuring service levels increase in line with the planning guides and the growth of the target population. | Each state and territory government will develop planning guides that define the adequate level and mix of inpatient and ambulatory services including rehabilitation, geriatric evaluation and management, psychogeriatric services and palliative care and other specialised health services for older people by geographic region by 30 June, 2005. Where adequate levels of levels of services are not being provided for older people in each region, each state and territory government will introduce measures to progressively meet the defined level by 30 June, 2008. Each state and territory government will report annually on the level and mix of inpatient and ambulatory services including rehabilitation, geriatric evaluation and management, psychogeriatric services and palliative care and other specialised health services being provided to older people in each geographic region and on progress to meeting the defined level of services in each region. |
| 2. The Australian Government commits to an adequate level of operational aged care places including: - Achieving the new benchmarks for supply of aged care places within a reasonable timeframe. - Ensuring new places are equitably distributed across aged care planning regions. | The Australian Government will operationalise an adequate level of aged care places including achieving the new aged care planning benchmarks by 30 June 2008. The Australian Government will report annually on the ratio of operational residential aged care beds and packages by geographic region. State and territory governments will work with the Australian Government to reduce delays that prevent allocated residential aged care places becoming operational. |
| 3. State/territory governments and the Australian Government commit to ensure that Aboriginal and Torres Strait Islander people have access to culturally appropriate health and aged care services. | The Australian Government will work to increase the number of new aged care places targeted to the needs of Aboriginal and Torres Strait Islander people. Jurisdictions will report on measures that improve the availability of and Aboriginal and Torres Strait Islander people’s access to culturally appropriate health and aged care services. |

### Principle 5: 	The health and aged care system operate to deliver an integrated suite of 	services and care for older people.

Key stakeholders: state/territory governments, Australian Government, health and aged care providers, COAWG

| Statements of intent | Actions and milestones |
| --- | --- |
| 1. States/territories commit to promote the adoption of best practice assessment processes by Health Services in their jurisdiction. | - State and territory governments will: promote adoption of the Best Practice Assessment Guide for the Care of Older People in Health Service Settings - report on measures to promote implementation of principles and practices outlined in the best practice assessment guide by 30 June 2005. |
| 2. States/territories and the Australian Government commit to facilitate uptake and use of care pathways by health services and aged care providers. | The Australian Government and all state and territory governments will work together to: - develop care pathways - promote their uptake and use by health services and aged care providers - promote training for staff in health and aged care facilities to assist uptake. All jurisdictions will report on measures taken to promote uptake of care pathways (stroke by 30 June 2005 and delirium clinical guidelines and care pathways by 30 June 2007). |
| 3. States/territory governments and the Australian Government commit to develop consistent definitions and data collections that allow the level and mix of inpatient and ambulatory services including rehabilitation, geriatric evaluation and management, psychogeriatric, palliative care and other specialised health services for older people to be measured and reported. | By 30 December 2004, all jurisdictions will develop and agree on standard definitions and consistent data collections and performance indicators to measure access to rehabilitation, geriatric evaluation and management, psychogeriatric, palliative care and other specialised health services for older people. |
| 4. State/territory governments and the Australian Government commit to work together to link datasets in order to provide information across service boundaries. | State and territory governments and the Australian Government will pursue linkage of national minimum datasets (including those capturing hospital morbidity, residential aged care and community care data) at the jurisdictional level to provide information across service boundaries. All jurisdictions will report annually on progress on linking datasets at the individual jurisdictional level. |

# Appendix 2

The analysis of incremental costs in the ICRS report is based on pre-post estimates of:

- Direct costs on number of days and "pilot program derived" costs per day of ICRS Residential Aged Care and ICRS Community Aged Care.

- Incremental cost offsets for residential aged care use on observed number of days in residential aged care in ICRS less an assumption (rather than evidence from a comparator) based estimate of days in residential aged care without ICRS.

The cost per day in i) averages out to $149.75 per day of ICRS care over 106,601 observed days in ICRS (65.00 = 106601/1640 days/patient), with "pilot derived" program costs of $86 per day for 45,302 days in ICRS in a community-based setting and $236 per day for 61,299 days in ICRS in a residential-based setting.  The $9,733 ($15,962,986/1640) direct costs per person presented in the ICRS report implicitly would increase to an average of $13,901 per person ($22,797,690/1640) if the daily cost was estimated at $213.86 (i.e. twice the 2006/07 flexible care subsidy).

To estimate the incremental residential aged care costs up to three months, the ICRS analysis implicitly assumed that the number of additional days in residential aged care exactly matched the number of additional days of ICRS, with 106,601 additional days saved (106,601 = "48,573 high care" plus "58,028 low care").  That is, it is assumed that up to three months the average 65.00 days of ICRS per person would all have been spent in residential aged care in the absence of ICRS.  However, a high proportion of patients without ICRS end up in the community and there are a proportion of patients who despite ICRS for three months end up in residential aged care.

Evidence relative to a real comparator group in our study suggests that while the 65 days of stay in Transition Care per person reported in the ICRS study is reasonable, residential aged care use can be expected to be reduced by only 8.10 days (9.52 vs. 1.42 days) up to three months or approximately one eighth of the 65 days assumed.  Hence with an evidence-based, rather than assumption-based, estimate of the number of days in residential aged care, and the same assumption about the proportion and cost per day of residential days in high and low care, incremental cost savings from reduced residential aged care up to three months are reduced from $10.426 million ($6.654 million in high care and $3.772 million in low care) to $1.299 million.  Brought back to a per person estimate, the cost saving reduce from $6,358 per person to $792 per person.

However, this may still overestimate of the cost savings, given that the ICRS report did not use the seven distinct Resident Classification Scale (RCS) subsidies but a dichotomy of high/low.  If the difference in payment is estimated using the full spectrum of RCS amounts, then this gives an estimate in cost saving of $467 per person ($587 vs. $120) with the reduction in residential aged care use from 9.52 to 1.42 days.  This equates to a reduction of $0.766 million across 1640 people.  Hence cost offsets to 3 months may be overestimated by $5,891 ($6,358-$467) per person or $9.66 million across 1640 individuals.

Similar issues arose in the analysis of six months follow-up in the ICRS report.  The modelled assumption-based estimate of cost savings from modelled reduction in use of residential aged care days appear to have been based on an even stronger assumption about the reduction in average residential aged care from three to six months than that up to three months (i.e. greater than 65 days).  An evidence-based, rather than assumption-based, estimate from the current study suggests that at six months residential aged care use is reduced by 15.55 days (24.22 vs. 6.67 days) and $866 per person ($1,437 vs. $571).  Hence, from 3 to 6 months there is estimated to be a reduction in residential days of 7.45 days (15.55-8.10) and $399 per person. Consequently, the assumption-based cost saving from reduced residential aged care of $7,750 per person and $12.7 million for 1,640 people from 3 to 6 months is reduced to $399 per person and $0.654 million.

Another important difference between NETCP and ICRS is the follow-up period.  The ICRS reported on interviews at three and six months post discharge from the ICRS program, whereas the follow-up period in the NETCP was three and six months post approval.

In summary, in the ICRS report the direct costs are possibly underestimated by $6.84 million or $4,168 per person in having an average total cost per patient of $149.75 rather than $213.86 per patient and residential aged care cost offsets are possibly overestimated by $9.66 million in the three month follow-up period and $12.05 million in the six month follow-up period across the population of 1640 individuals, when using evidence rather than assumption based estimates of number of residential aged care days avoided.  Hence the total incremental cost estimate is increased by $28.55 million ($17,410 per person) from that estimated in the ICRS report.

# Appendix 3: Episodes of care definition according to the Meteor data dictionary

## Hospital service-care type, code N[N].N

Identifying and definitional attributes

Metadata item type	Data Element

Short name: 	Care type

METeOR identifier: 	270174

Registration status: 	Health, Standard 01/03/2005

Definition: 	The overall nature of a clinical service provided to an admitted patient 	during an episode of care (admitted care), or the type of service provided 	by the hospital for boarders or posthumous organ procurement (other 	care), as represented by a code.

Data Element Concept:	Hospital service—care type

## Value domain attributes

Representational attributes

Representation class: 	Code

Data type: 		Number

Format: 		N[N].N

Maximum character length: 3

Permissible values: 	Value 	Meaning

1.0 	Acute care (Admitted care)

2.0 	Rehabilitation care (Admitted care)

2.1 	Rehabilitation care delivered in a designated unit (optional)

2.2 	Rehabilitation care according to a designated program (optional)

2.3	Rehabilitation care is the principal clinical intent (optional)

3.0 	Palliative care

3.1 	Palliative care delivered in a designated unit (optional)

3.2 	Palliative care according to a designated program (optional)

3.3 	Palliative care is the principal clinical intent (optional)

4.0	Geriatric evaluation and management

5.0 	Psychogeriatric care

6.0 	Maintenance care

7.0 	Newborn care

8.0 	Other admitted patient care

9.0 	Organ procurement - posthumous (Other care)

10.0	Hospital boarder (Other care)